## Introduction
[Insert Department/Project Logo] |  | [Insert Department Name] [Insert Project Name]
Introduction to the Change Request Log Template
The Change Request Log Template provides a centralized view of the current status of project change requests. It is used to communicate a simple, summarized view of the number and nature of change requests currently being managed by the project. The Change Request Coordinator is responsible for maintaining the Change Request Log on behalf of the Change Management Lead.
The Change Request Log documents:
- The complete inventory of project change requests
- Staffing associated with each of the Change Requests
- Status of each individual Change Request
- Planned completion for each of the Change Requests
This Change Request Log Template with Instructions contains directions for properly initiating and maintaining the Change Request Log As you complete the template, please remember to delete all instructional text (including this "Introduction" tab and the "Instructions" tab) and update the header and footer. Update the document to a minor version (e.g., 1.1, 1.2) when minimal changes are made and a major version (e.g., 2.0, 3.0) when significant change are made.
Template style conventions are as follows:
Style | Convention
Normal text | Indicates placeholder text that can be used for any project
[Instructional text in brackets] | [Indicates text that is to be replaced/edited/deleted by document author]
Example text in italics | Indicates example text that might be replaced/edited/deleted by user

## Instructions
[Insert Department/Project Logo] | [Insert Department Name] [Insert Project Name]
Change Request Log Template
1 Introduction
The Change Request Log provides an at-a-glance view of the number and types of changes currently being considered by the project. Because it is a summary, it gives the project manager and other decision-makers a quick sense of how much change is occurring within the project. A significant number of high-impact changes could be a sign of a project at risk from a scope, time or cost perspective. It can also point out change requests that are not being addressed in a timely manner. Untimely decision making regarding changes can result in lost opportunities to improve overall probability of success and/or avoid negative project impacts. The Change Request Summary Report consists of the following fields:
• Date of Request – The request date associated with the specific Change Request
• Change Request Number – The unique number assigned to identify the specific Change Request
• Change Request Title – The unique name for the change request
• Assigned to – The name of the lead Change Request Analysis / Implementation resource
• Description of Change – Narrative describing the requested change
• Current Status – The current workflow step or disposition for the change request. Typically, one of the following:
- Submitted - The change request has been developed and submitted for consideration
- Accepted - The Change Control Board has accepted the change request and has approved use of project resources for analysis
- Assigned - The Change Request Analysis / Implementation team has been assigned to the Change Request
- Rework - The Change Request has been sent back to a previous step for additional information
- Withdrawn - The Change Request Originator has withdrawn the request
- Deferred - The Change Request has been put on hold until later in the project
- Approved - The Change Control Board has approved the Change Request and the Change Request Analysis / Implementation team's recommendation
- Completed - the Change Request has been implemented
2 Creating the Change Request Log
2.1 Personalize the Change Request Log
Update the upper left corner of the Change Request Log with the project's specific logo or name.
2.2 Populate the Change Request Log
Transfer the Date of Request, Change Request #, Change Request Title, the resource assigned to the change request, the description of the change requested, current status and implementation date from the change request form for each specific change request. Add rows as needed.
2.3 Maintain the Change Request Log
As change requests progress through the change request process, keeping the log updated is critical to communicating accurately the state of change in the project. This task is typically handled by the Change Request Coordinator on behalf of the Change Management Lead.
3 Example
An example Change Log entry is provided on the Change Request Log tab in this workbook. The requested change is to add an additional technical resource to accommodate project workload.

## Change Request Log
[Insert Department/Project Logo] | [5 empty] | [Insert Department Name] [Insert Project Name]
<Project Logo> |  | Change Request Log
Date of Request | CR# | Change Request Title | Assigned To | Description of Change | Current Status | Implementation Date
2015-12-22 | 1 | Addition of 1 full time DBA | J. Smith | Staffing increase to accommodate level of effort in data conversion tasks | Approved | 2016-01-31