## Summary
SUMMARY OF NON-STATE FUNDED PROJECTS
2000-2001 NON-STATE CAPITAL BUDGET
($ in thousands)
| UCB | UCD | UCI | UCLA | UCM | UCR | UCSD | UCSF | UCSB | UCSC | DANR | OP | TOTAL | Percent of Total
Bank Loans or Bonds (LB) | 25000 | 14265 | 29341 | 210536 | 0 | 43205 | 56772 | 0 | 48474 | 61019 | 0 | 0 | 488612 | 42.26%
Internal Loans (*LB) | 0 | 0 | 0 | 0 | 0 | 13000 | 0 | 0 | 1866 | 3800 | 0 | 0 | 18666 | 1.614%
Other (X) | 26433 | 18812 | 12425 | 13695 | 0 | 8654 | 5962 | 34596 | 2560 | 490 | 0 | 3031 | 126658 | 10.95%
Gifts (G) | 20580 | 22611 | 19110 | 195857 | 0 | 100 | 100458 | 11768 | 80 | 978 | 0 | 0 | 371542 | 32.13%
Federal (F) | 0 | 945 | 0 | 17096 | 0 | 1117 | 740 | 1000 | 0 | 499 | 0 | 0 | 21397 | 1.851%
Hospital Reserves (HR) | 0 | 29841 | 421 | 16299 | 0 | 0 | 5768 | 14428 | 0 | 0 | 0 | 0 | 66757 | 5.774%
Registration Fees (R) | 0 | 0 | 0 | 1208 | 0 | 500 | 0 | 0 | 374 | 0 | 0 | 0 | 2082 | 0.1801%
Reserves other than Registration Fees (N) | 21246 | 2102 | 3830 | 17717 | 0 | 0 | 3169 | 0 | 4595 | 5600 | 0 | 0 | 58259 | 5.039%
University Funds or Educational Funds (U) | 250 |  | 2000 |  |  | 0 |  |  |  |  | 0 | 0 | 2250 | 0.1946%
TOTAL | 93509 | 88576 | 67127 | 472408 | 0 | 66576 | 172869 | 61792 | 57949 | 72386 |  | 3031 | 1156223 | 100%
INDIVIDUAL CAMPUS PERCENT OF TOTAL | 8.087% | 7.661% | 5.806% | 40.86% | 0% | 5.758% | 14.95% | 5.344% | 5.012% | 6.261% |  | 0.2621% | 100%
STATE FUNDS | 5787 | 51821 | 30602 | 185119 | 0 | 0 | 91500 | 12359 | 2384 | 1692 |  | 0 | 381264

## Berkeley
BERKELEY CAMPUS
2000-2001 NON-STATE CAPITAL BUDGET
($ in thousands)
C U R R E N T S T A T U S
| Project | Project Cost |  |  | Prefunded |  |  | 2000-2001 |  |  | Beyond |  |  | Date | Action | Approval Letter | Date | Action | Cost
[11 empty] | 2000-2001 | [6 empty] | Action | Cost
| Central Dining and Office Facility |  | 22000 | LB | P | 3360 | N | P | 840 | N |  |  |  | 9/00 | Regents | 10/25/00 | 9/6/00 | P,W,C and E | 41593000
|  |  | 19593 | N |  |  |  | W | 3450 | LB
|  |  | 41593 |  |  |  |  | C | 15218 | N
[8 empty] | C | 18550 | LB
[8 empty] | E | 175 | N
38233
| Oxford Tract Parking Facility |  | 3000 | LB |  |  |  | P | 314 | N |  |  |  | 9/00 | President's Authority | 09/11/00 | 9/5/00 | P,W,C and E | 7145000
|  |  | 4145 | N |  |  |  | W | 364 | N
|  |  | 7145 |  |  |  |  | C | 3337 | N
[8 empty] | C | 3000 | LB
[8 empty] | E | 130 | N
7145
| Stanley Hall (912040) |  | 5787 |  |  |  |  | P | 5787 |  |  |  |  | 1/01 | Regents | 2/28/01 | 1/18/01 | CISI/State Funds | 5787000
"P" Only
| Goldman School of Public Policy |  | 4782 | G | P | 487 | G | W | 487 | G |  |  |  | 2/01 | Admin. Approval | 3/9/01 | 2/27/01 | W and C | 2087000
| Expansion (912957) |  | 1800 | X | W | 378 | G | C | 400 | G
|  |  | 6582 |  | C | 3030 | G | C | 1200 | X
[5 empty] | C | 600 | X |  | 2087
4495
| Hargrove Music Library Building |  | 11000 | G |  |  |  | P | 1002 | G |  |  |  | 4/01 | Regents | 6/11/01 | 4/27/01 | P,W,C and E | 12219000
| (912780) |  | 1219 | X |  |  |  | W | 853 | G
|  |  | 12219 |  |  |  |  | C | 9145 | G
[8 empty] | C | 549 | X
[8 empty] | E | 670 | X
12219
| Seismic Safety Corrections, |  | 13946 | ( ) | P | 589 | ( ) | C | 4175 | X |  |  |  | 6/01 | Regents | 7/19/01 | 6/25/01 | C only | 4175000
| Barker Hall (912635) |  | 4175 | X | W | 758 | ( )
|  |  | 18121 |  | C | 12599 | ( )
13946
| Barker Hall Renovations |  | 12518 | X | P | 335 | X | C | 3018 | X |  |  |  | 6/01 | Regents | 7/19/01 | 6/25/01 | C only | 3018000
[5 empty] | W | 750 | X
[5 empty] | C | 8415 | X
9500
| 2200 Bancroft Seismic and Program Upgrade |  | 1166 | X |  |  |  | P | 82 | X |  |  |  |  | Chancellor Approved
|  |  | 1166 |  |  |  |  | W | 87 | X
| (Account 912114) | [6 empty] | C | 997 | X
1166
| 2350 Bowditch, Relocation of Building from 2612 Channing Way |  | 750 | N |  |  |  | P | 72 | N |  |  |  |  | Chancellor Approved
|  |  | 750 |  |  |  |  | W | 48 | N
| (Account 912108) | [6 empty] | C | 630 | N
750
| 2547 Channing Renovations |  | 506 | X |  |  |  | P | 28 | X |  |  |  |  | Chancellor Approved
| (Account 912250) |  | 506 |  |  |  |  | W | 30 | X
[8 empty] | C | 448 | X
506
| Barrows Hall Communications Infrastructure Improvements |  | 734 | X |  |  |  | P | 14 | X |  |  |  |  | Chancellor Approved
|  |  | 734 |  |  |  |  | W | 90 | X
| (Account 912153) | [6 empty] | C | 630 | X
734
| Birge Hall Ground Floor Electronics Shop Relocation |  | 400 | X |  |  |  | P | 10 | X |  |  |  |  | Chancellor Approved
|  |  | 400 |  |  |  |  | W | 50 | X
| (Account 912116) | [6 empty] | C | 340 | X
400
| Botanical Garden Plant Conservation Research Greenhouse |  | 1100 | G |  |  |  | P | 100 | X |  |  |  |  | Chancellor Approved
|  |  | 800 | X |  |  |  | W | 200 | X
|  |  | 1900 |  |  |  |  | C | 1100 | G
| (Account 912085) | [6 empty] | C | 500 | X
1900
| Calvin Laboratory Fire and Life Safety Improvements, Step 1 |  | 400 | X |  |  |  | W | 35 | X |  |  |  |  | Chancellor Approved
|  |  | 400 |  |  |  |  | C | 365 | X
| (Account 912128) | [7 empty] | 400
| Cory Hall Rooms 121-143 Instructional Laboratory Renovation |  | 850 | G |  |  |  | P | 50 | G |  |  |  |  | Chancellor Approved
|  |  | 100 | X |  |  |  | W | 100 | X
| (Account 912152) |  | 950 |  |  |  |  | C | 630 | G
[8 empty] | E | 170 | G
950
| Haas Pavilion Landscape Improvements |  | 1600 | X |  |  |  | W | 100 | X |  |  |  |  | Chancellor Approved
|  |  | 1600 |  |  |  |  | C | 1500 | X
| (Account 912747) | [7 empty] | 1600
| Interbuilding Campus Communications System, Step 3 |  | 600 | X |  |  |  | W | 30 | X |  |  |  |  | Chancellor Approved
|  |  | 600 |  |  |  |  | C | 570 | X
| (Account 912106) | [7 empty] | 600
| Interbuilding Campus Communications System, Step 3B |  | 1250 | X |  |  |  | P | 100 | X |  |  |  |  | Chancellor Approved
|  |  | 1250 |  |  |  |  | W | 50 | X
| (Account 912125) | [6 empty] | C | 1100 | X
1250
| Latimer Hall Eighth Floor Laboratory Renovations for Chemical Biology, Phase 2 |  | 2082 | G |  |  |  | P | 275 | G |  |  |  |  | Chancellor Approved
|  |  | 118 | N |  |  |  | W | 129 | G
|  |  | 2200 |  |  |  |  | C | 1583 | G
| (Account 912127) | [6 empty] | C | 118 | N
[8 empty] | E | 95 | G
2200
| Lewis Hall Rooms 201-206 Laboratory Renovations |  | 1424 | G |  |  |  | P | 110 | G |  |  |  |  | Chancellor Approved
|  |  | 150 | X |  |  |  | W | 126 | G
| (Account 912142) |  | 1574 |  |  |  |  | C | 1188 | G
[8 empty] | C | 150 | X
1574
| Minor Hall Fourth Floor Renovation of Fong Library and Lecture Hall |  | 1400 | G |  |  |  | P | 150 | G |  |  |  |  | Chancellor Approved
|  |  | 1400 |  |  |  |  | W | 100 | G
[8 empty] | C | 1100 | G
| (Account 912095) | [6 empty] | E | 50 | G
1400
| Oxford Tract Insectary and Greenhouse Replacement Facility |  | 3200 | X |  |  |  | P | 96 | X |  |  |  |  | Chancellor Approved
|  |  | 3200 |  |  |  |  | W | 158 | X
| (Account 912099) | [6 empty] | C | 2946 | X
3200
| UC Berkeley Art Museum Interim Seismic Corrections |  | 4213 | X |  |  |  | P | 350 | X |  |  |  |  | Chancellor Approved
|  |  | 4213 |  |  |  |  | W | 363 | X
| (Account 912094) | [6 empty] | C | 3500 | X
4213
| Valley Life Sciences Building Air Supply System Improvements |  | 1452 | X |  |  |  | P | 100 | X |  |  |  |  | Chancellor Approved
|  |  | 1452 |  |  |  |  | W | 125 | X
| (Account 912101) | [6 empty] | C | 1227 | X
1452
| Wurster Hall Environmental Design Library Redesign |  | 689 | G |  |  |  | P | 115 | G |  |  |  |  | Chancellor Approved
|  |  | 689 |  |  |  |  | W | 116 | G
| (Account 912126) | [6 empty] | C | 458 | G
689
| Wurster Hall Fourth Floor Link Structure, Phase 1 |  | 410 | G |  |  |  | P | 22 | G |  |  |  |  | Chancellor Approved
|  |  | 410 |  |  |  |  | W | 30 | G
| (Account 912109) | [6 empty] | C | 358 | G
410
| Wurster Hall Room 501 Undergraduate Environmental Design Studio Renovation |  | 38 | G |  |  |  | P | 26 | G |  |  |  |  | Chancellor Approved
|  |  | 250 | X |  |  |  | W | 12 | G
|  |  | 288 |  |  |  |  | W | 11 | X
| (Account 912104) | [6 empty] | C | 181 | X
[8 empty] | E | 58 | X
288
| Zellerbach Hall Northeast Balcony Enclosure and Accessibility Upgrades |  | 700 | G |  |  |  | P | 75 | G |  |  |  |  | Chancellor Approved
|  |  | 250 | U |  |  |  | P | 27 | U
|  |  | 950 |  |  |  |  | W | 62 | G
| (Account 912977) | [6 empty] | W | 22 | U
[8 empty] | C | 563 | G
[8 empty] | C | 201 | U
950
| Banks Loans or Bonds (LB) |  | 25000 |  |  | 0 |  |  | 25000 |  |  | 0 |  |  | 0
*Internal Loans (LB*)
| Other (i.e. Campus Funds) (X) |  | 36533 |  |  | 10100 |  |  | 26433 |  |  | 0 |  |  | 0
| Gifts (G) |  | 24475 |  |  | 3895 |  |  | 20580 |  |  | 0 |  |  | 0
| Federal (F) |  |  |  |  | 0 | [5 empty] | 0 |  |  | 0
| Hospital Reserves (HR) |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
| Registration Fees (R) |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
| Reserves other than University Fees (N) |  | 24606 |  |  | 3360 |  |  | 21246 |  |  | 0 |  |  | 0
| University or Educational Funds (U) |  | 250 | [5 empty] | 250
| TOTAL |  | 110864 |  |  | 17355 |  |  | 93509 |  |  | 0 |  |  | 0
| STATE FUNDS | ( | 19733 | ) | ( | 13946 | ) | ( | 5787 | ) | ( | 0 | ) |  | 0

## Davis
DAVIS CAMPUS
2000-2001 NON-STATE CAPITAL BUDGET
($ in thousands)
C U R R E N T S T A T U S
| Project | Project Cost |  |  | Prefunded |  |  | 2000-2001 |  |  | Beyond |  |  | Date | Action | Approval Letter | Date | Action | Cost
[11 empty] | 2000-2001 | [6 empty] | Action | Cost
| Tahoe Environmental Research |  | 10960 | G |  |  |  | P | 1200 | G |  |  |  | 9/00 | Regents | 11/15/00 | 9/15/00 | P,W,C and E | 10960000
| Center (931980) | [6 empty] | W | 676 | G
[8 empty] | C | 9070 | G
[8 empty] | E | 14 | G
10960
| Center for Companion Animal |  | 7893 | G |  |  |  | P | 581 | G |  |  |  | 9/00 | Regents | 12/8/00 | 9/15/00 | P,W and C | 12235000
| Health (954040) |  | 4342 | X |  |  |  | W | 606 | G
|  |  | 12235 |  |  |  |  | C | 6706 | G
[8 empty] | C | 600 | X
[8 empty] | C | 3742 | X
12235
| UCDMC M.I.N.D. Institute |  | 1600 | LB |  |  |  | P | 1600 | LB |  |  |  | 1/01 | Regents |  | 1/17/01 | P Only | 1600000
(9549400)
|  |  | 28566 | ( ) |  |  |  | P | 1600 | ( ) |  |  |  | 5/01 | Regents |  | 5/16/01 | P,W and C | 38840000
|  |  | 3728 | HR |  |  |  | W | 1946 | ( )
|  |  | 6546 | ( ) |  |  |  | C | 31566 | ( )
|  |  | 38840 |  |  |  |  | C | 3728 | HR
38840
| UCDMC Tower II, Phase III |  | 18593 | HR |  |  |  | P | 1784 | HR |  |  |  | 1/01 | Regents | 6/29/01 | 1/17/01 | P, W, C and E | 26858000
| (9549000) |  | 8265 | LB |  |  |  | W | 1607 | HR
|  |  | 26858 |  |  |  |  | C | 8265 | LB
[8 empty] | C | 11764 | HR
[8 empty] | E | 3438 | HR
26858
| Center for Comparative Medicine |  | 11717 | LB | P | 585 | LB | C | 945 | F |  |  |  | 1/01 | Admin. Approval | 2/21/01 | 1/3/01 | C | 945000
| (935070) |  | 1400 | F | P | 40 | F
|  |  | 2746 | X | W | 406 | LB
|  |  | 15863 |  | W | 80 | F
[5 empty] | C | 9951 | LB
[5 empty] | C | 335 | F
[5 empty] | C | 2746 | X
[5 empty] | E | 775 | LB
14918
| Aquatics Center (950020) |  | 1300 | G |  |  |  | P | 280 | G |  |  |  | 1/01 | President's Auth. | 2/21/01 | 1/24/01 | P,W,C and E | 7300000
|  |  | 6000 | LB |  |  |  | W | 297 | G
|  |  | 7300 |  |  |  |  | C | 423 | G
[8 empty] | C | 6000 | LB
[8 empty] | E | 300 | G
7300
| Chemistry Annex Alterations |  | 2802 | ( ) | P | 93 | ( ) | C | 2564 | ( ) |  |  |  |  | State Approval | 6/13/01
| (932150) |  | 467 | X | W | 145 | ( ) | C | 467 | X
|  |  | 3269 |  |  | 238 |  |  | 3031
| Genome Launch Facility (954160) |  | 8000 | X |  |  |  | P | 528 | X |  |  |  | 4/01 | Admin. Approval | 4/24/01 | 4/16/01 | P,W and C | 9600000
|  |  | 1600 | G |  |  |  | W | 480 | X
|  |  | 9600 |  |  |  |  | C | 6992 | X
[8 empty] | C | 1600 | G
9600
| UCDMC Tower II, Phase II |  | 5826 | HR |  |  |  | P | 1073 | HR |  |  |  | 4/01 | Regents | 6/29/01 | 4/27/01 | P,W and C | 19971000
| (935660) |  | 9145 | ( )* |  |  |  | W | 1426 | HR | [7 empty] | *SB 1953 Funds
|  |  | 5000 | ( )* |  |  |  | C | 3327 | HR
|  |  | 19971 |  |  |  |  | C | 5000 | ( )*
[8 empty] | C | 9145 | ( )*
19971
| Baseball/Soccer Complex |  | 570 | G |  |  |  | P | 21 | G |  |  |  |  | Chancellor Approved
| Improvements |  | 18 | X |  |  |  | W | 29 | G
| -932190 |  | 588 |  |  |  |  | C | 520 | G
[8 empty] | C | 18 | X
588
| Chilled Water System Improvements: |  | 2160 | X |  |  |  | P | 105 | X |  |  |  |  | Chancellor Approved
| Phase V | [6 empty] | W | 108 | X
| (936063) | [6 empty] | C | 1947 | X
2160
| South Entry Utility Extension and |  | 275 | X |  |  |  | P | 14 | X |  |  |  |  | Chancellor Approved
| Expansion | [6 empty] | W | 15 | X
| (932270) | [6 empty] | C | 246 | X
275
| Wellman Hall Classroom Alterations - |  | 370 | X |  |  |  | P | 17 | X |  |  |  |  | Chancellor Approved
| Rooms 230 and 234 | [6 empty] | W | 17 | X
| (950180) | [6 empty] | C | 336 | X
370
| Student Health Modular Building |  | 398 | X |  |  |  | P | 8 | X |  |  |  |  | Chancellor Approved
| (954170) | [6 empty] | C | 390 | X
398
| Recreation Hall Seismic Renovation |  | 2102 | N |  |  |  | P | 245 | N |  |  |  |  | Chancellor Approved
| (932360) | [6 empty] | W | 165 | N
[8 empty] | C | 1692 | N
2102
| Eichhorn Family House |  | 130 | X |  |  |  | P | 12 | X |  |  |  |  | Chancellor Approved
| (950130) |  | 288 | G |  |  |  | P | 12 | G
|  |  | 418 |  |  |  |  | W | 13 | X
[8 empty] | W | 13 | G
[8 empty] | C | 105 | X
[8 empty] | C | 263 | G
418
| Tupper Hall - 4th Floor Laboratory |  | 1033 | X |  |  |  | S | 20 | X |  |  |  |  | Chancellor Approved
| Remodel for the Dept. of Biological | [6 empty] | P | 37 | X
| Chemistry | [6 empty] | W | 39 | X
| (954110) | [6 empty] | C | 937 | X
1033
| Architects & Engineers Barn Remodel |  | 416 | X |  |  |  | P | 22 | X |  |  |  |  | Chancellor Approved
| (932400) | [6 empty] | W | 22 | X
[8 empty] | C | 372 | X
416
| Campus Landfill Waste Management |  | 548 | X |  |  |  | P | 33 | X |  |  |  |  | Chancellor Approved
| Unit 2 (Cell 6) | [6 empty] | W | 35 | X
| (950100) | [6 empty] | C | 480 | X
548
| UCDHS Central Sterile Processing |  | 387 | HR |  |  |  | P | 8 | HR |  |  |  |  | Chancellor Approved
| Repairs | [6 empty] | W | 53 | HR
| (9550500) | [6 empty] | C | 326 | HR
387
| UCDHS Multi PO&M Water Upgrade | [6 empty] | W | 203 | HR |  |  |  |  | Chancellor Approved
| (9548600) |  | 850 | HR |  |  |  | C | 647 | HR
850
| UCDHS East Campus Infrastructure |  | 364 | HR |  |  |  | P | 10 | HR |  |  |  |  | Chancellor Approved
| (9562000) | [6 empty] | W | 20 | HR
[8 empty] | C | 334 | HR
364
| Swine Teaching, Research, and |  | 2590 | X | P | 100 | X
| Extension Replacement Facility |  |  |  | W | 125 | X
| (932230) |  |  |  | C | 2180 | X | C | 185 | X |  |  |  |  | Chancellor Approved
2405
| New Natural Gas Fueled Boiler |  | 1170 | X | P | 45 | X | [7 empty] | Chancellor Approved
| at CHCP |  |  |  | W | 50 | X
| (932250) |  |  |  | C | 605 | X | C | 470 | X
700
| UCDHS Hazardous Rooms Upgrade |  | 856 | HR | P | 100 | HR | [7 empty] | Chancellor Approved
| (935560) |  |  |  | W | 15 | HR | W | 12 | HR
[5 empty] | C | 648 | HR | C | 81 | HR
[6 empty] | 763 |  |  | 93
| Banks Loans or Bonds (LB) |  | 25982 |  |  | 11717 |  |  | 14265 |  |  | 0 |  |  | 0
*Internal Loans (LB*)
| Other (i.e. Campus Funds) (X) |  | 24663 |  |  | 5851 |  |  | 18812 |  |  | 0 |  |  | 0
| Gifts (G) |  | 22611 |  |  | 0 |  |  | 22611 |  |  | 0 |  |  | 0
| Federal (F) |  | 1400 |  |  | 455 |  |  | 945 |  |  | 0 |  |  | 0
| Hospital Reserves (HR) |  | 30604 |  |  | 763 |  |  | 29841 |  |  | 0 |  |  | 0
| Registration Fees (R) |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
| Reserves other than University Fees (N) |  | 2102 |  |  | 0 |  |  | 2102 |  |  | 0
University or Educational Funds (U)
| TOTAL |  | 107362 |  |  | 18786 |  |  | 88576 |  |  | 0 |  |  | 0
| STATE FUNDS | ( | 52059 | ) | ( | 238 | ) | ( | 51821 | ) | ( | 0 | ) |  | 0

## Irvine
IRVINE CAMPUS
2000-2001 NON-STATE CAPITAL BUDGET
($ in thousands)
C U R R E N T S T A T U S
| Project | Project Cost |  |  | Prefunded |  |  | 2000-2001 |  |  | Beyond |  |  | Date | Action | Approval Letter | Date | Action | Cost
[11 empty] | 2000-2001 | [6 empty] | Action | Cost
| Croul Hall (991020) |  | 19600 | G |  |  |  | P | 1401 | X |  |  |  | 7/00 | Regents | 10/06/00 | 7/19/00 | P, W, C | 23756000
|  |  | 4156 | X |  |  |  | W | 1226 | X | [7 empty] | Campus, OP and
|  |  | 23756 |  |  |  |  | C | 1529 | X | [7 empty] | Gift Funds
[8 empty] | C | 19600 | G
23756
|  |  | 2000 | U |  |  |  | P | 1463 | X |  |  |  | 3/01 | Regents | 4/18/01 | 3/15/01 | P, W and C | 26807000
|  |  | 2156 | X |  |  |  | W | 693 | X
|  |  | 14341 | LB |  |  |  | W | 607 | U
|  |  | 8310 | G |  |  |  | C | 1393 | U
|  |  | 26807 |  |  |  |  | C | 8310 | G
[8 empty] | C | 14341 | LB
26807
| Anteater Recreation Center |  | 5000 | LB |  |  |  | P | 1238 | N |  |  |  | 1/01 | President's Auth. | 2/8/01 | 1/31/01 | P, W and C | 8830000
| Playing Fields (990098) |  | 3830 | N |  |  |  | W | 925 | N
|  |  | 8830 |  |  |  |  | C | 1667 | N
[8 empty] | C | 5000 | LB
8830
| Cal-(IT)2 Facility (991995) |  | 28500 | ( ) |  |  |  | P | 2153 | ( ) |  |  |  | 1/01 | Regents | 2/28/01 | 1/18/01 | CISI/State Funds | 2153000
|  |  | 10000 | LB | [13 empty] | "P" Only
|  |  | 10800 | G
|  |  | 5000 | X |  |  |  | W | 1120 | ( ) |  |  |  | 5/01 | Regents | 3/26/02 | 5/9/01 | P, W, C and E | 54300000
|  |  | 54300 |  |  |  |  | C | 25227 | ( )
[8 empty] | C | 10000 | LB
[8 empty] | C | 10800 | G
[8 empty] | E | 5000 | X
54300
| Undergraduate Housing Expansion |  | 53444 | LB | P | 3280 | LB |  | *see note |  |  |  |  | 6/01 | Admin. Approval | 7/2/01 | 6/28/01 |  | 53444000
| (996315) |  |  |  | W | 1264 | LB | [7 empty] | *this approval was for
[5 empty] | C | 47525 | LB | [7 empty] | breakdown of funds
[5 empty] | E | 1375 | LB | [7 empty] | distribution only for the
[6 empty] | 53444 | [8 empty] | purpose of drawdowns
| UCIMC Infrasturcture Project A (994520) |  | 2102 | ( )* |  |  |  | P | 65 | HR |  |  |  | 6/01 | President's Authority | 6/29/01 | 6/25/01 | P, W and C | 2167000
|  |  | 65 | HR |  |  |  | W | 98 | ( )* | [7 empty] | *Infrastructure Funds
|  |  | 2167 |  |  |  |  | C | 2004 | ( )*
2167
| Extended Day Care Center (990480) |  | 1200 | X |  |  |  | P | 46 | X |  |  |  |  | Chancellor Approved
[8 empty] | W | 52 | X
[8 empty] | C | 1102 | X
1200
| Multipurpose Academic & Administration |  | 4069 | X |  |  |  | P | 227 | X |  |  |  |  | Chancellor Approved
| Building Tenant Improvements (992111) | [6 empty] | W | 98 | X
[8 empty] | C | 3744 | X
4069
| UCIMC Opthalmology Expansion |  | 356 | HR |  |  |  | P | 27 | HR |  |  |  |  | Chancellor Approved
| (994159) | [6 empty] | W | 22 | HR
[8 empty] | C | 307 | HR
356
| Banks Loans or Bonds (LB) |  | 82785 |  |  | 53444 |  |  | 29341 |  |  | 0 |  |  | 0
*Internal Loans (LB*)
| Other (i.e. Campus Funds) (X) |  | 12425 |  |  | 0 |  |  | 12425 |  |  | 0 |  |  | 0
| Gifts (G) |  | 19110 |  |  | 0 |  |  | 19110 |  |  | 0 |  |  | 0
| Federal (F) |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
| Hospital Reserves (HR) |  | 421 |  |  | 0 |  |  | 421 |  |  | 0 |  |  | 0
| Registration Fees (R) |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
| Reserves other than University Fees (N) |  | 3830 |  |  | 0 |  |  | 3830 |  |  | 0 |  |  | 0
| University or Educational Funds (U) |  | 2000 | [5 empty] | 2000 | [5 empty] | 0
| TOTAL |  | 120571 |  |  | 53444 |  |  | 67127 |  |  | 0 |  |  | 0
| STATE FUNDS | ( | 30602 | ) | ( | 0 | ) | ( | 30602 | ) | ( | 0 | ) |  | 0

## Los Angeles
LOS ANGELES CAMPUS
2000-2001 NON-STATE CAPITAL BUDGET
($ in thousands)
C U R R E N T S T A T U S
| Project | Project Cost |  |  | Prefunded |  |  | 2000-2001 |  |  | Beyond |  |  | Date | Action | Approval Letter | Date | Action | Cost
[11 empty] | 2000-2001 | [6 empty] | Action | Cost
| Northwest Housing and Parking |  | 72029 | LB | P | 800 | N | C | 7056 | N |  |  |  | 8/00 | Administrative | 8/23/00 | 8/21/00 | C | 7056000
| Phase 2 (946480) |  | 16156 | N | P | 1947 | LB | [7 empty] | Approval
|  |  | 88185 |  | W | 3390 | LB
[5 empty] | C | 5344 | N
[5 empty] | C | 66355 | LB
[5 empty] | E | 2956 | N
[5 empty] | E | 337 | LB
81129
| Broad Art Center Seismic |  | 374 | X |  |  |  | P | 374 | X |  |  |  | 9/00 | Regents | 10/25/00 | 9/13/00 | P only | 1068000
| Reconstruction and Expansion |  | 694 | F |  |  |  | P | 694 | F
| (948731) |  | 1068 | [5 empty] | 1068
| Health Sciences Replacement |  | 23768 |  | P | 922 |  | C | 1480 | G | E | 450 | G | 9/00 | Regents | ------ | 9/6/00 | P,W,C and E | 59177000
| Building 1 (945950) |  | 35409 | G | P | 1318 | G
|  |  | 59177 |  | W | 1153
[5 empty] | W | 1647 | G
[5 empty] | C | 21693
[5 empty] | C | 30514 | G
57247
|  |  | 43179 | G | P | 922 | ( ) | C | 9250 | G | E | 450 | G | 6/01 | Admin. Approval | 6/26/01 | 6/20/01
|  |  | 23768 | ( ) | P | 1318 | G
|  |  | 66947 |  | W | 1153 | ( )
[5 empty] | W | 1647 | G
[5 empty] | C | 21693 | ( )
[5 empty] | C | 30514 | G
57247
| Westwood Replacement |  | 432900 | F | P | 23000 | F | P | 2000 | G |  |  |  | 9/00 | Regents | 11/1/00 | 9/6/00 | P,W,C and E | 672700000
| Hospital (945760) |  | 44100 |  | P | 3000 |  | W | 3000 | G
|  |  | 124900 |  | W | 30000 | F | C | 36800 | G
|  |  | 70800 | G | W | 3000 |  | C | 124900
|  |  | 672700 |  | C | 379900 | F | E | 29000 | G
[5 empty] | C | 38100 |  |  | 195700
477000
| Santa Monica/Orthopaedic |  | 72200 | F | P | 7700 | F | P | 2800 | G |  |  |  | 9/00 | Regents | 11/1/00 | 9/6/00 | P,W,C and E | 230861000
| Replacement Hospital and |  | 14900 | HR | W | 17100 | F | W | 6000 | G
| Parking Structure (945880) |  | 55100 |  | C | 47400 | F | C | 14900 | HR
|  |  | 88661 | G |  | 72200 |  | C | 55100
|  |  | 230861 |  |  |  |  | C | 77361 | G
[8 empty] | E | 2500 | G
158661
| Southwest Campus Housing |  | 143270 | LB | P | 1675 | N | P | 3325 | LB |  |  |  | 11/00 | Regents | 1/19/01 | 11/8/00 | P, W, C | 147770000
| and Parking Phase 1 (946390) |  | 4500 | N |  |  |  | W | 5000 | LB
|  |  | 147770 |  |  |  |  | C | 134945 | LB
[8 empty] | E | 2825 | N
146095
| Men's Gym Seismic Repair and |  | 13832 | F |  |  |  | P | 1379 | F |  |  |  | 11/00 | Regents | 12/8/00 | 11/8/00 | P, W, C | 37908000
| Program Improvements (948782) |  | 479 | X |  |  |  | P | 2160 | LB
|  |  | 23597 | LB |  |  |  | P | 48 | X
|  |  | 37908 |  |  |  |  | W | 1668 | F
[8 empty] | W | 2613 | LB
[8 empty] | W | 58 | X
[8 empty] | C | 10785 | F
[8 empty] | C | 18824 | LB
[8 empty] | C | 373 | X
37908
| Law Library Addition and Related |  | 13919 |  | P | 677 |  | C | 1921 | G |  |  |  | 10/00 | Administrative | 12/8/00 | 10/8/00 | C and E | 27355000
| Improvements (943080) |  | 13436 | G | P | 450 | G | E | 695 | G |  |  |  |  | Approval
|  |  | 27355 |  | W | 838 |  |  | 2616
[5 empty] | W | 556 | G
[5 empty] | C | 12404
[5 empty] | C | 9121 | G
[5 empty] | E | 693 | G
24739
| Plant Physiology Replacement |  | 3500 | G |  |  |  | P | 300 | G |  |  |  | 10/00 | Administrative | 10/20/00 | 10/18/00 | P, W, C AND E | 7000000
| Building (948357) |  | 2500 | F |  |  |  | W | 600 | G |  |  |  |  | Approval
|  |  | 1000 | X |  |  |  | C | 2600 | G
|  |  | 7000 |  |  |  |  | C | 810 | X
[8 empty] | C | 2500 | F
[8 empty] | E | 190 | X
7000
| Parking Structure 4 Expansion |  | 16179 | LB | P | 1000 | LB | C | 1172 | N |  |  |  | 11/00 | Administrative | 12/11/00 | 11/27/00 | C | 1172000
| (946680) |  | 1172 | N | W | 300 | LB | [7 empty] | Approval
|  |  | 17351 |  | C | 14879 | LB
16179
| Dance Building Seismic |  | 1264 | F | P | 114 | G | P | 1063 | G | C | 14297 |  | 1/01 | Regents |  | 1/17/01 | P, W and C | 36282000
| Renovation (Kaufman Hall) |  | 2487 | X | P | 601 | X | W | 700 |  | C | 1194 | F
| (948791) |  | 17534 | G |  | 715 |  | W | 70 | F | C | 1709 | X
|  |  | 14997 |  |  |  |  | W | 177 | X | C | 13125 | G
|  |  | 36282 |  |  |  |  | W | 574 | G |  | 2658 | G
[9 empty] | 2584 |  |  | 32983
| Kinsey Hall Seismic Corrections, |  | 3950 | F | P | 824 |  | P | 534 | X | W | 805 |  | 1/01 | Regents |  | 1/17/01 | P, W and C | 32260000
| Phase 2 (948781) |  | 7524 | G |  |  |  | W | 1236 | X | W | 345 | F
|  |  | 1770 | X |  |  |  | C | 7524 | G | C | 3605 | F
|  |  | 19016 | [5 empty] | 9294 |  | C | 17387
|  |  | 32260 | [8 empty] | 22142
| Intramural Field Parking Structure |  | 3000 | X |  |  |  | P | 101 | X |  |  |  | 1/01 | Regents | 3/9/01 | 1/17/01 | P, W and C | 35192000
| (946770) |  | 32192 | LB |  |  |  | W | 2899 | X
|  |  | 35192 |  |  |  |  | W | 730 | LB
[8 empty] | C | 31462 | LB
35192
| Thermal Energy Storage System |  | 6089 | X | P | 150 | X | W | 181 | X |  |  |  | 2/01 | Admin. Approval | 2/13/01 | 2/7/01 | W and C | 989000
| (946160) |  |  |  | W | 250 | X | C | 808 | X
[5 empty] | C | 4700 | X |  | 989
5100
| CNSI/Engineering 1 Replacement |  | 1424 |  |  |  |  | P | 1424 |  |  |  |  | 1/01 | Regents | 2/28/01 | 1/18/01 | CISI/State Funds | 1424000
| Building (942660) | [16 empty] | "P" Only
| CNSI Court of Sciences |  | 2995 |  |  |  |  | P | 2995 |  |  |  |  | 1/01 | Regents | 2/28/01 | 1/18/01 | CISI/State Funds | 2995000
| Building (942650) | [16 empty] | "P" Only
| Wooden West Addition (941170) |  | 1208 | R |  |  |  | P | 945 | R |  |  |  | 6/01 | Regents | 7/19/01 | 625/01 | P, W and C | 12685000
|  |  | 11477 | LB |  |  |  | W | 263 | R
|  |  | 12685 |  |  |  |  | W | 851 | LB
[8 empty] | C | 10626 | LB
12685
| Gonda (Goldschmeid) Neuroscience |  | 49979 | G | P | 2508 | G | C | 66 | X |  |  |  | 6/01 | Admin. Approval | 6/21/01 | 6/1/01
| & Genetics Research Center |  | 3326 | X | W | 2056 | G
| (945930) |  | 53305 |  | C | 44971 | G
[5 empty] | C | 3260 | X
[5 empty] | E | 444 | G
53239
| Acosta Athletic Training Center |  | 6000 | N |  |  |  | P | 677 | N |  |  |  | 5/01 | Regents | 6/11/01 | 5/23/01 | P, W and C
| Renovation and Expansion (942260) |  | 7600 | G |  |  |  | W | 809 | N
|  |  | 13600 |  |  |  |  | C | 4514 | N
[8 empty] | C | 7600 | G
13600
| CSB1 Elevator Addition (942560) |  | 662 | X |  |  |  | P | 42 | X |  |  |  |  | Chancellor Approved
[8 empty] | W | 70 | X
[8 empty] | C | 550 | X
662
| CSB1 Second Floor |  | 977 | X |  |  |  | P | 20 | X |  |  |  |  | Chancellor Approved
| Renovation (942550) | [6 empty] | W | 42 | X
[8 empty] | C | 915 | X
977
| HSSRB1 - Site Demolition & |  | 1842 | G |  |  |  | P | 40 | G |  |  |  |  | Chancellor Approved
| Development (946199) | [6 empty] | W | 60 | G
[8 empty] | C | 1742 | G
1842
| Life Sciences Third Floor |  | 1000 | X |  |  |  | P | 30 | X |  |  |  |  | Chancellor Approved
| Renovation (943440) | [6 empty] | W | 129 | X
[8 empty] | C | 841 | X
1000
| Rehab 2nd Floor Cytogenetics |  | 652 | X |  |  |  | P | 29 | X |  |  |  |  | Chancellor Approved
| Lab Renovation (948802) | [6 empty] | W | 45 | X
[8 empty] | C | 578 | X
652
| Rehab Immunogenetics Lab |  | 1515 | X |  |  |  | P | 95 | X |  |  |  |  | Chancellor Approved
| Renovation (944970) | [6 empty] | W | 200 | X
[8 empty] | C | 1200 | X
[8 empty] | E | 20 | X
1515
| SM-UCLA MC AB26-30 Clinical |  | 489 | HR |  |  |  | P | 1 | HR |  |  |  |  | Chancellor Approved
| Lab Life Safety | [6 empty] | W | 70 | HR
| Alterations (948784) | [6 empty] | C | 418 | HR
489
| SM-UCLA MC Emergency |  | 293 | HR |  |  |  | P | 1 | HR |  |  |  |  | Chancellor Approved
| Lighting System Bracing | [6 empty] | W | 25 | HR
| Correction (946068) | [6 empty] | C | 267 | HR
293
| SOM 23-360 Pharmacology |  | 259 | X |  |  |  | P | 2 | X |  |  |  |  | Chancellor Approved
| Renovation (944340) | [6 empty] | W | 8 | X
[8 empty] | C | 245 | X
[8 empty] | E | 4 | X
259
| UCLA Guest House |  | 273 | N |  |  |  | P | 6 | N |  |  |  |  | Chancellor Approved
| Renovation (946430) | [6 empty] | W | 41 | N
[8 empty] | C | 219 | N
[8 empty] | E | 7 | N
273
| Vending Pavilions for Misc- |  | 391 | N |  |  |  | P | 7 | N |  |  |  |  | Chancellor Approved
| ellaneous Locations (946111) | [6 empty] | W | 64 | N
[8 empty] | C | 320 | N
391
| Warren 13-114/14-184 |  | 450 | G |  |  |  | P | 22 | G |  |  |  |  | Chancellor Approved
| Pulmonary Immunology | [6 empty] | W | 44 | G
| Lab (944550) | [6 empty] | C | 384 | G
450
| West Medical Pharmacy |  | 1977 | G |  |  |  | P | 42 | G |  |  |  |  | Chancellor Approved
| Manufacturing | [6 empty] | W | 117 | G
| Renovation (944040) | [6 empty] | C | 1818 | G
1977
| ADA Schoenberg Auditorium |  | 260 | X | P | 7 | X | [7 empty] | Chancellor Approved
| Alterations (948879) |  |  |  | W | 24 | X
[5 empty] | C | 223 | X | C | 6 | X
254
| CHS BL Radiology Intervention |  | 1465 | HR | P | 27 | HR | [7 empty] | Chancellor Approved
| MRI Renovation (948886) |  |  |  | W | 79 | HR
[5 empty] | C | 1000 | HR | C | 359 | HR
1106
| MC A7-229 Pathology Cutting |  | 1225 | HR | P | 20 | HR | [7 empty] | Chancellor Approved
| Suite Alteration (945730) |  |  |  | W | 94 | HR
[5 empty] | C | 872 | HR | C | 239 | HR
986
| PPB 2400 SSC/CASSELL |  | 758 | X | P | 9 | X | [7 empty] | Chancellor Approved
| Computer Lab |  |  |  | W | 37 | X
| Renovation (943470) |  |  |  | C | 503 | X | C | 134 | X
[5 empty] | E | 75 | X
624
| SM-UCLA 500/501 Neonatal |  | 440 | HR | P | 5 | HR | [7 empty] | Chancellor Approved
| ICU (948362) |  |  |  | W | 77 | HR
[5 empty] | C | 339 | HR | C | 19 | HR
421
SOM 63-134, 142, 170
| Neurobiology Renovation (945790) |  | 994 | X | P | 100 | X | [7 empty] | Chancellor Approved
[5 empty] | W | 150 | X | W | 10 | X
[5 empty] | C | 400 | X | C | 264 | X
[8 empty] | E | 70 | X
[6 empty] | 650 |  |  | 344
| SOM 73-167 A&B Lab |  | 1272 | X | P | 30 | X | [7 empty] | Chancellor Approved
| Renovation (944060) |  |  |  | W | 70 | X
[5 empty] | C | 972 | X | C | 72 | X
[5 empty] | E | 128 | X
1200
| SOM 73-323/338 Neurobiology |  | 325 | X | P | 20 | X | [7 empty] | Chancellor Approved
| Wet Lab Renovation (947760) |  |  |  | W | 20 | X
[5 empty] | C | 170 | X | C | 75 | X
[5 empty] | E | 40 | X
250
| SOM B2-B3 Pharmacology |  | 927 | X | P | 65 | X | [7 empty] | Chancellor Approved
| Renovation (944210) |  |  |  | W | 50 | X
[5 empty] | C | 360 | X
[5 empty] | E | 394 | X | E | 58 | X
869
| Warren Hall 13-160 |  | 852 | X | P | 20 | X | [7 empty] | Chancellor Approved
| Renovation (942190) |  |  |  | W | 74 | X
[5 empty] | C | 657 | X | C | 86 | X
[5 empty] | E | 15 | X
766
| Banks Loans or Bonds (LB) |  | 298744 |  |  | 88208 |  |  | 210536 |  |  | 0 |  |  | 0
*Internal Loans (LB*)
| Other (i.e. Campus Funds) (X) |  | 28978 |  |  | 13574 |  |  | 13695 |  |  | 1709 |  |  | 0
| Gifts (G) |  | 306482 |  |  | 94392 |  |  | 195857 |  |  | 16233 |  |  | 0
| Federal (F) |  | 527340 |  |  | 505100 |  |  | 17096 |  |  | 5144 |  |  | 0
| Hospital Reserves (HR) |  | 18812 |  |  | 2513 |  |  | 16299 |  |  | 0 |  |  | 0
| Registration Fees (R) |  | 1208 |  |  | 0 |  |  | 1208 |  |  | 0 |  |  | 0
| Reserves other than University Fees (N) |  | 28492 |  |  | 10775 |  |  | 17717 |  |  | 0 |  |  | 0
| University or Educational Funds (U) | [13 empty] | 0
| TOTAL |  | 1210056 |  |  | 714562 |  |  | 472408 |  |  | 23086 |  |  | 0
| STATE FUNDS | ( | 300219 | ) | ( | 82611 | ) | ( | 185119 | ) | ( | 32489 | ) |  | 0

## Riverside
RIVERSIDE CAMPUS
2000-2001 NON-STATE CAPITAL BUDGET
($ in thousands)
C U R R E N T S T A T U S
| Project | Project Cost |  |  | Prefunded |  |  | 2000-2001 |  |  | Beyond |  |  | Date | Action | Approval Letter | Date | Action | Cost
[11 empty] | 2000-2001 | [6 empty] | Action | Cost
| Undergraduate Student Housing |  | 1978 | X |  |  |  | P | 1015 | LB |  |  |  | 7/00 | Regents | 09/12/00 | 7/19/00 | P, W, C and E | 42798000
| Expansion 2 (956298) |  | 40820 | LB |  |  |  | W | 1820 | LB | [7 empty] | Exernal Funds
|  |  | 42798 |  |  |  |  | C | 37985 | LB
[8 empty] | E | 1978 | X
42798
| Campus Surge (950424) |  | 13000 | LB* |  |  |  | P | 500 | R |  |  |  | 8/00 | Regents | 9/6/00 | 8/22/00 | P, W, C | 15885000
|  |  | 2385 | LB |  |  |  | P | 35 | LB*
|  |  | 500 | R |  |  |  | P | 6 | LB
|  |  | 15885 |  |  |  |  | W | 592 | LB*
[8 empty] | W | 103 | LB
[8 empty] | C | 12373 | LB*
[8 empty] | C | 2276 | LB
15885
| Campus Modular |  | 2328 | X |  |  |  | P | 81 | X |  |  |  |  | Chancellor Approved
| Building (950443) | [6 empty] | W | 93 | X
[8 empty] | C | 2154 | X
2328
| Entomology Greenhouse |  | 100 | G |  |  |  | P | 36 | X |  |  |  |  | Chancellor Approved
| Replacement (950444) |  | 935 | X |  |  |  | W | 41 | X
|  |  | 1035 |  |  |  |  | C | 100 | G
[8 empty] | C | 858 | X
1035
| Plant Transformation |  | 469 | X |  |  |  | P | 48 | F |  |  |  |  | Chancellor Approved
| Facility (958900) |  | 1117 | F |  |  |  | W | 71 | F
|  |  | 1586 |  |  |  |  | C | 998 | F
[8 empty] | C | 469 | X
1586
| Chilled Water Expansion |  | 1878 | X |  |  |  | P | 66 | X |  |  |  |  | Chancellor Approved
| (958901) | [6 empty] | W | 75 | X
[8 empty] | C | 1737 | X
1878
| 12 KV Expansion |  | 710 | X |  |  |  | P | 25 | X |  |  |  |  | Chancellor Approved
| (958902) | [6 empty] | W | 28 | X
[8 empty] | C | 657 | X
710
| Steam Plant Pump |  | 356 | X |  |  |  | P | 12 | X |  |  |  |  | Chancellor Approved
| Modification (958903) | [6 empty] | W | 14 | X
[8 empty] | C | 330 | X
356
| Banks Loans or Bonds (LB) |  | 43205 |  |  | 0 |  |  | 43205 |  |  | 0 |  |  | 0
| *Internal Loans (LB*) |  | 13000 | [5 empty] | 13000 | [5 empty] | 0
| Other (i.e. Campus Funds) (X) |  | 8654 |  |  | 0 |  |  | 8654 |  |  | 0 |  |  | 0
| Gifts (G) |  | 100 |  |  | 0 |  |  | 100 |  |  | 0 |  |  | 0
| Federal (F) |  | 1117 |  |  | 0 |  |  | 1117 |  |  | 0 |  |  | 0
| Hospital Reserves (HR) |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
| Registration Fees (R) |  | 500 |  |  | 0 |  |  | 500 |  |  | 0 |  |  | 0
| Reserves other than University Fees (N) |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
| University or Educational Funds (U) | [13 empty] | 0
| TOTAL |  | 66576 |  |  | 0 |  |  | 66576 |  |  | 0 |  |  | 0
| STATE FUNDS | ( | 0 | ) | ( | 0 | ) | ( | 0 | ) | ( | 0 | ) |  | 0

## San Diego
SAN DIEGO CAMPUS
2000-2001 NON-STATE CAPITAL BUDGET
($ in thousands)
C U R R E N T S T A T U S
| Project | Project Cost |  |  | Prefunded |  |  | 2000-2001 |  |  | Beyond |  |  | Date | Action | Approval Letter | Date | Action | Cost
[11 empty] | 2000-2001 | [6 empty] | Action | Cost
| UCSD Cancer Center Facility |  | 67879 | G |  |  |  | P | 3136 | G |  |  |  | 2000-07-01 | Regents | 10/06/00 | 7/19/00 | P, W, C | 87109000
| ('965750) |  | 19230 | LB |  |  |  | P | 784 | LB | [7 empty] | External and Gifts Funds
|  |  | 87109 |  |  |  |  | W | 3833 | G
[8 empty] | W | 958 | LB
[8 empty] | C | 60910 | G
[8 empty] | C | 17488 | LB
87109
| La Jolla Playhouse Development |  | 14736 | G |  |  |  | P | 600 | G |  |  |  | 11/00 | Regents | 1/18/01 | 11/27/00 | P, W, C and E | 14736000
| and Education Center (962840) | [6 empty] | W | 800 | G
[8 empty] | C | 12836 | G
[8 empty] | E | 500 | G
14736
| Cal-(IT)2 Facility (962980) |  | 3644 |  |  |  |  | P | 3644 |  |  |  |  | 1/01 | Regents | 2/28/01 | 1/18/01 | CISI/State Funds | 3644000
"P" Only
|  |  | 20000 | LB |  |  |  | W | 3966 |  |  |  |  | 3/01 | Regents |  | 3/15/01 | W,C and E
|  |  | 16000 | G |  |  |  | C | 44890
|  |  | 62856 |  |  |  |  | C | 20000 | LB
|  |  | 102500 |  |  |  |  | E | 14000
[8 empty] | E | 16000 | G
102500
| Eleanor Roosevelt College |  | 95804 | LB | P | 3428 | LB | P | 877 | LB |  |  |  | 3/01 | Regents | 4/18/01 | 3/15/01 | P, W and C | 22697000
| Housing and Dining Facilities |  | 7316 | N | P | 85 | LB | P | 144 | X
| (966320) |  | 2900 | X | W | 4189 | LB | W | 1073 | LB
|  |  | 106020 |  | W | 104 | LB | W | 176 | X
[5 empty] | C | 66804 | LB | C | 15592 | LB
[5 empty] | C | 1704 | LB | C | 307 | N
[5 empty] | C | 1755 | N | C | 2580 | X
[5 empty] | E | 1755 | LB | E | 1948 | N
[5 empty] | E | 193 | LB |  | 22697
[5 empty] | E | 3306 | N
83323
| UCSD Hillcrest Building Systems |  | 16494 | ( )* |  |  |  | P | 1090 | ( )* |  |  |  | 4/01 | Regents | 6/29/01 | 4/27/01 | P, W and C | 16494000
| Improvements (966231) | [6 empty] | W | 760 | ( )* | [7 empty] | *Infrastructure Funds
[8 empty] | C | 14644 | ( )*
16494
| UCSD Hillcrest Department |  | 6006 | ( )* |  |  |  | P | 407 | ( )* |  |  |  | 4/01 | Regents | 6/29/01 | 4/27/01 | P, W and C | 6006000
| Improvements (965820) | [6 empty] | W | 282 | ( )* | [7 empty] | *Infrastructure Funds
[8 empty] | C | 5317 | ( )*
6006
| UCSD Hillcrest Emergency |  | 2500 | ( )* |  |  |  | C | 2500 | ( )* |  |  |  | 5/01 | Regents | 7/23/01 | 5/23/01 | "C" Only | 2500000
| Department Improvements | [16 empty] | *Infrastructure Funds
(965520)
| Basic Science Building Laboratory |  | 500 | X |  |  |  | P | 17 | X |  |  |  |  | Chancellor
| Renovation (965830) | [6 empty] | W | 23 | X |  |  |  |  | Approved
[8 empty] | C | 460 | X
500
| East Campus Neighborhood Parking |  | 840 | N |  |  |  | P | 32 | N |  |  |  |  | Chancellor
| Lots (966598) | [6 empty] | W | 48 | N |  |  |  |  | Approved
[8 empty] | C | 760 | N
840
| IGPP-2 HVAC Renovation and |  | 740 | F |  |  |  | P | 10 | F |  |  |  |  | Chancellor
| Upgrade (962155) | [6 empty] | W | 44 | F |  |  |  |  | Approved
[8 empty] | C | 686 | F
740
| Ludwig institute for Center |  | 318 | X |  |  |  | P | 17 | X |  |  |  |  | Chancellor
| Research-CMME/Renovation of | [6 empty] | W | 45 | X |  |  |  |  | Approved
| Suite 3080 (965790) | [6 empty] | C | 256 | X
318
| Medical Center Drive South |  | 1840 | G |  |  |  | P | 82 | G |  |  |  |  | Chancellor
| Road Realignment (966597) |  | 460 | HR |  |  |  | P | 21 | HR |  |  |  |  | Approved
|  |  | 2300 |  |  |  |  | W | 102 | G
[8 empty] | W | 25 | HR
[8 empty] | C | 1656 | G
[8 empty] | C | 414 | HR
2300
| Torrey Pines Center South Suites 295, |  | 619 | X |  |  |  | P | 45 | X |  |  |  |  | Chancellor
| 310 and 340 Renovations (963030) | [6 empty] | W | 121 | X |  |  |  |  | Approved
[8 empty] | C | 404 | X
[8 empty] | E | 49 | X
619
| UCSDMC Hillcrest: Ambulatory Care |  | 328 | HR |  |  |  | P | 34 | HR |  |  |  |  | Chancellor
| Center/Owen Clinic Exhaust System | [6 empty] | W | 55 | HR |  |  |  |  | Approved
| Upgrade (966214) | [6 empty] | C | 239 | HR
328
| UCSDMC Hillcrest: Dickinson Street Sewer |  | 836 | HR |  |  |  | P | 0 | [5 empty] | Chancellor
| Improvements (966234) | [6 empty] | W | 0 | [5 empty] | Approved
[8 empty] | C | 836 | HR
836
| UCSDMC Hillcrest: Main Tower Column |  | 355 | HR |  |  |  | P | 16 | HR |  |  |  |  | Chancellor
| Fiber Wrap (965780) | [6 empty] | W | 63 | HR |  |  |  |  | Approved
[8 empty] | C | 276 | HR
355
| UCSDMC Hillcrest: 12 KV Main |  | 1291 | HR |  |  |  | P | 25 | HR |  |  |  |  | Chancellor
| Switchgear Replacement (966220) | [6 empty] | W | 100 | HR |  |  |  |  | Approved
[8 empty] | C | 1166 | HR
1291
| UCSDMC Thornton: Infusion Center |  | 290 | HR |  |  |  | P | 35 | HR |  |  |  |  | Chancellor
| Tenant Improvement (965810) | [6 empty] | W | 35 | HR |  |  |  |  | Approved
[8 empty] | C | 220 | HR
290
| University Center Building 700 |  | 277 | X |  |  |  | P | 5 | X |  |  |  |  | Chancellor
| Renovation (963000) | [6 empty] | W | 15 | X |  |  |  |  | Approved
[8 empty] | C | 257 | X
277
| Vaughan Hall and Ritter Hall |  | 868 | X |  |  |  | P | 0 | X |  |  |  |  | Chancellor
| Demolition and Basement Shell (962990) | [6 empty] | W | 20 | X |  |  |  |  | Approved
[8 empty] | C | 848 | X
868
| Warren Field Restrooms/Storage |  | 396 | X |  |  |  | P | 20 | X |  |  |  |  | Chancellor
| (963010) | [6 empty] | W | 20 | X |  |  |  |  | Approved
[8 empty] | C | 356 | X
396
| Regents Road Parking Lot (966594) |  | 3288 | N | P | 50 | N | [7 empty] | Chancellor
|  |  | 571 | X | W | 200 | N | [7 empty] | Approved
|  |  | 3859 |  | C | 2964 | N | C | 74 | N
[5 empty] | C | 503 | X | C | 68 | X
[6 empty] | 3717 |  |  | 142
| SOM Biomedical Information Center |  | 401 | X | P | 15 | X | [7 empty] | Chancellor
| (965760) |  | 3 | G | W | 18 | X | C | 16 | X |  |  |  |  | Approved
|  |  | 404 |  | C | 352 | X | C | 3 | G
[6 empty] | 385 |  |  | 19
| UCSDMC Hillcrest: Kitchen Sewer Line |  | 2490 | HR | P | 16 | HR | [7 empty] | Chancellor
| Replacement (966207) |  |  |  | W | 110 | HR | [7 empty] | Approved
[5 empty] | C | 2049 | HR | C | 315 | HR
[6 empty] | 2175 |  |  | 315
| UCSDMC Hillcrest Water System Upgrade |  | 4289 | HR | P | 258 | HR | [7 empty] | Chancellor
| (966185) |  |  |  | W | 136 | HR | [7 empty] | Approved
[5 empty] | C | 2002 | HR | C | 1893 | HR
[6 empty] | 2396 |  |  | 1893
| Banks Loans or Bonds (LB) |  | 135034 |  |  | 78262 |  |  | 56772 |  |  | 0 |  |  | 0
*Internal Loans (LB*)
| Other (i.e. Campus Funds) (X) |  | 6850 |  |  | 888 |  |  | 5962 |  |  | 0 |  |  | 0
| Gifts (G) |  | 100458 | [5 empty] | 100458 |  |  | 0 |  |  | 0
| Federal (F) |  | 740 |  |  | 0 |  |  | 740 |  |  | 0 |  |  | 0
| Hospital Reserves (HR) |  | 10339 |  |  | 4571 |  |  | 5768 |  |  | 0 |  |  | 0
| Registration Fees (R) |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
| Reserves other than University Fees (N) |  | 11444 |  |  | 8275 |  |  | 3169
University or Educational Funds (U)
| TOTAL |  | 264865 |  |  | 91996 |  |  | 172869 |  |  | 0 |  |  | 0
| STATE FUNDS | ( | 91500 | ) | ( | 0 | ) | ( | 91500 | ) | ( | 0 | ) |  | 0
This project will provide for the demolition and realignment of an existing road (near the Health Sciences Drive intersection) and demolition of existing utilities (storm drain, water, electrical, gas, sewer) to accommodate the future Cancer Center Building and other future development on the East Campus. The road alignment includes sidewalks, a landscaped median, and new utilities (storm drain, telephone, electrical, gas, and water). In addition, Campus Point Drive will be re-configured as a cul-de-sac, including utilities (storm drain, telephone, electrical, gas, water, sewer), terminating near the Shiley Eye Center and serving as a drop-off and turnaround point for transportation.
This project will provide air conditioning to 29 selected rooms in IGPP-2, also known as the Revelle Laboratory at SIO. The scope of work includes the extension of chilled water lines from existing chillers in adjacent buildings, including pumps; the upgrade of electrical service; and, the installation of 28 chilled water fan coil units with associated piping and controls.
This project will provide for the renovation of approximately 1,900 asf in Suite 3080 of the Center for Molecular Medicine East Building, which is used by the Ludwig Institute for Cancer Research. The scope of work includes the remodeling of existing space to incorporate a new lobby, computer room, and clerical, work/storage and office space.
This project will provide for the upgrading of the mechanical system at the Owen Clinic, which is located on the 3rd floor of the Ambulatory Care Center Building in Hillcrest. The system will be based on negative pressure ventilation with HEPA filtration and 100% outside exhaust and will bring the system into code compliance.
This project will provide carbon fiber wrapping of columns for a portion of the Main Tower at UCSDMC Hillcrest, specifically the east and west sides of the sixth through eleventh floors. This work will achieve a SPC-2 seismic rating for the facility. In addition, a column on the first floor of the building in the Radiology Department will be upgraded.
This project will provide a new 12 KV main switchgear facility near the Central Plant service yard, replacing a 28 year old 12KV substation. The scope of work includes expanding an existing concrete pad to house the switchgear equipment; enclosing the site with chain-link fencing; and, installing landscaping to serve as a visual buffer. Electrical power will be provided via an underground connection to an existing SDG&E service connection.
This project will provide administrative offices for both the Animal Care Program and Sixth College Provost in the former University and State Employees (USE) Credit Union Building, which is approximately 4,693 asf and renamed University Center Building 700. The scope of work includes the addition of new partitions to maximize the number of interior offices; the upgrade of lighting and telecommunications; and, the extension of the existing ventilation system.
This project will provide for the demolition of Vaughan Hall and the east and south wings of Ritter Hall (approximately 36,300 asf), except for the basement level of the Ritter east wing (approximately 3,500 asf) which will be retained and modified for use as an underground utility space and funded through a separate project. In addition, the remaining portion of Ritter Hall requires repairs to the south facade and adjoining areas of the building due to the demolition. Deferred Maintenance funds ($150,000) were used to fund a portion of this project.
The project will provide a building to support the new Warren Recreation Field. The building, approximately 1,990 asf, will include a men's and women's restroom, locker and training areas, and storage/utility space. The scope of work includes utility extensions to the building and site improvements of landscaping, concrete walks, and additional fencing.
This project will provide for the renovation of three suites in Torrey Pines Center South to accommodate the space needs of administrative units. The scope of work includes extensive demolition of interior space and construction of tenant improvements, totaling approximately 5,192 asf.
Original approval in 1998-99 for $3,634k. Augmentation in 1999-00; revised project cost of $3,717k. Augmentation in 2000-01; revised project cost of $3,858k. Augmentation was due to an expanded scope of work required by the City of San Diego and for the development of the Science Research Park Project.
Original approval in 1999-00 for $385k. Augmentation in 2000-01; revised project cost of $404k. Augmentation was required to cover expenses for changes to sprinklers and other miscellaneous items.
Original approval in 1999-00 for $2,175k. Augmentation in 2000-01; revised project cost of $2,490k. Augmentation was required to cover expenses in connection with infection control and asbestos abatement and to include additional flooring.
Original approval in 1997-98 for $2,396k. Augmentation in 2000-01; revised project cost of $4,289k. Augmentation was required to fund additional costs of renting temporary equipment for the duration of the project, satisfy required OSHPD modifications, fund additional fees, and mitigate unknown site conditions.
This project will provide for the remodeling of approximately 1,900 asf on the first floor of Thornton Hospital to accommodate the requirements of the existing Infusion Center which serves patients requiring intravenous treatment. The function of this space will change from office/administration to clinical functions including therapeutic intervention and diagnostic medical procedures for outpatients.
This project will provide for the renovation of the Basic Science Building lobby (approximately 2,400 asf). The scope of work includes replacement of existing lighting which is inadequate and costly to maintain; installation of new storefront doors and pedestal card readers; restoration of wall finishes or replacement with new wall panels; and, installation of new glass display cases and a building directory.
This project will provide for improvements of the sewer line that crosses Dickinson Street at the Hillcrest Medical Center. This sewer line is the only sewer from the hospital which connects to the City of San Diego main sewer line. A recent study found that the sewer line is broken in two places and that sections of the pipe are misaligned. The scope of work includes tunneling under all of the utilities at an alignment that will avoid the congested utility area and minimize contact with any essential utility.
This project will provide for the construction of two parking lots on the east side of campus. The first lot consisting of 236 parking spaces will be located to the north of the Shiley Eye Center. The second lot consisting of 104 parking spaces will be located west of Thornton Hospital. The scope of work includes lighting and landscaping for both lots.

## San Francisco
SAN FRANCISCO CAMPUS
2000-2001 NON-STATE CAPITAL BUDGET
($ in thousands)
C U R R E N T S T A T U S
| Project | Project Cost |  |  | Prefunded |  |  | 2000-2001 |  |  | Beyond |  |  | Date | Action | Approval Letter | Date | Action | Cost
[11 empty] | 2000-2001 | [6 empty] | Action | Cost
| Mission Bay Building 24C |  | 4700 |  |  |  |  | P | 4700 |  |  |  |  | 1/01 | Regents | 2/28/01 | 1/18/01 | CISI/State Funds | 4700000
| (923200) | [16 empty] | "P" Only
| Mission Bay Phase 1 Landscaping |  | 7128 | G |  |  |  | P | 431 | G |  |  |  | 4/01 | Admin. Approval | 5/15/01 | 4/10/01 |  | 7128000
| (923045) | [6 empty] | W | 413 | G
[8 empty] | C | 6159 | G
[8 empty] | E | 125 | G
7128
| UCSF Emergency Department |  | 5000 | ( )* |  |  |  | P | 450 | ( )* |  |  |  | 6/01 | President's Authority | 6/29/01 | 6/1/01 | P,W and C | 9287000
| Expansion (910140) |  | 4287 | HR |  |  |  | W | 450 | ( )* |  |  |  |  | *Infrastructure Funds
|  |  | 9287 |  |  |  |  | C | 4100 | ( )*
[8 empty] | C | 4287 | HR
9287
| SB 1953 Moffitt 2002 |  | 2659 | ( ) |  |  |  | P | 25 | HR |  |  |  | 6/01 | President's Authority | 6/29/01 | 6/1/01 | P,W and C | 2745000
| (910110) |  | 86 | HR |  |  |  | W | 61 | HR
|  |  | 2745 |  |  |  |  | W | 214 | ( )
[8 empty] | C | 2445 | ( )
2745
| MC A Elevator Upgrades |  | 1100 | HR |  |  |  | P | 59 | HR |  |  |  |  | Chancellor Approved
| 910020 | [6 empty] | W | 117 | HR
[8 empty] | C | 924 | HR
1100
| S/M-MC A-6 Urology Office And Clinic Renovation |  | 900 | X |  |  |  | P | 89 | X |  |  |  |  | Chancellor Approved
|  |  | 945 | HR |  |  |  | W | 108 | X
| 910030 |  | 1845 |  |  |  |  | C | 615 | X
[8 empty] | C | 945 | HR
[8 empty] | E | 88 | X
1845
| MC M-7 Pediatrics Day Hospital |  | 3891 | HR |  |  |  | P | 183 | HR |  |  |  |  | Chancellor Approved
| 910040 | [6 empty] | W | 400 | HR
[8 empty] | C | 3308 | HR
3891
| MC L Elevators Upgrade |  | 1143 | HR |  |  |  | P | 63 | HR |  |  |  |  | Chancellor Approved
| 910050 | [6 empty] | W | 100 | HR
[8 empty] | C | 500 | HR | C | 480 | HR
[9 empty] | 663 |  |  | 480
| MC L-3 MR Interventional Room Renovatiion (Turnkey) |  | 1466 | HR |  |  |  | P | 31 | HR |  |  |  |  | Chancellor Approved
[8 empty] | W | 65 | HR
| 910060 | [6 empty] | C | 1370 | HR
1466
| MC MZ R-2 Pathology/Cytology Remodel |  | 660 | HR |  |  |  | P | 33 | HR |  |  |  |  | Chancellor Approved
[8 empty] | W | 59 | HR
| 910070 | [6 empty] | C | 568 | HR
660
| MC MtZ A Elevators Upgrade |  | 1500 | HR |  |  |  | P | 90 | HR |  |  |  |  | Chancellor Approved
| 910090 | [6 empty] | W | 100 | HR | W | 50 | HR
[8 empty] | C | 460 | HR | C | 800 | HR
[9 empty] | 650 |  |  | 850
| MC SB 1953 Mt. Zion 2002 Buildings A, B, D & R |  | 4000 | HR |  |  |  | P | 25 | HR |  |  |  |  | Chancellor Approved
[8 empty] | W | 300 | HR
| 910130 | [6 empty] | C | 3675 | HR
4000
| S/M SFGH 100-3 Clinical Research Lab Renovation |  | 1000 | F |  |  |  | P | 141 | X |  |  |  |  | Chancellor Approved
|  |  | 1298 | X |  |  |  | W | 194 | X
| 921720 |  | 2298 |  |  |  |  | C | 1000 | F
[8 empty] | C | 963 | X
2298
| S/M HSW-14 Urology Lab Rnovation |  | 479 | X |  |  |  | P | 26 | X |  |  |  |  | Chancellor Approved
[8 empty] | W | 37 | X
| 922000 | [6 empty] | C | 416 | X
479
| S/P HSE-11 Biopharmaceutical Sciences Lab and Office Renovation |  | 1678 | X |  |  |  | P | 72 | X |  |  |  |  | Chancellor Approved
[8 empty] | W | 165 | X
[8 empty] | C | 1401 | X
| 922630 | [6 empty] | E | 40 | X
1678
| S/M LPPI-1 Department of Psychiatry Lab Ventilation Improvements |  | 106 | X |  |  |  | P | 27 | X |  |  |  |  | Chancellor Approved
|  |  | 427 | G |  |  |  | W | 43 | X
|  |  | 533 |  |  |  |  | C | 427 | G
| 922670 | [6 empty] | C | 36 | X
533
| S/M HSW-14 Pediatrics Lab Renovation |  | 263 | X |  |  |  | P | 14 | X |  |  |  |  | Chancellor Approved
[8 empty] | W | 21 | X
| 922680 | [6 empty] | C | 228 | X
263
| S/D D-3 Clinic C Modernization |  | 893 | X |  |  |  | P | 21 | X |  |  |  |  | Chancellor Approved
| 922770 | [6 empty] | W | 42 | X
[8 empty] | C | 665 | X
[8 empty] | E | 165 | X
893
| S/M M-5 Pathology Chairmain's Suite Renovation |  | 577 | X |  |  |  | P | 32 | X |  |  |  |  | Chancellor Approved
[8 empty] | W | 62 | X
| 922810 | [6 empty] | C | 455 | X
[8 empty] | E | 28 | X
577
| S/M S-5 Pathology Lab Renovation |  | 698 | X |  |  |  | P | 37 | X |  |  |  |  | Chancellor Approved
[8 empty] | W | 53 | X
| 922830 | [6 empty] | C | 608 | X
698
| A Elevators Construction |  | 967 | X |  |  |  | P | 105 | X |  |  |  |  | Chancellor Approved
| 922970 |  | 967 | HR |  |  |  | W | 152 | X
|  |  | 1934 |  |  |  |  | C | 710 | X
[8 empty] | C | 967 | HR
1934
| MB Phase 1 Green |  | 4113 | G |  |  |  | P | 459 | G |  |  |  |  | Chancellor Approved
| 923040 | [6 empty] | W | 522 | G
[8 empty] | C | 3057 | G
[8 empty] | E | 75 | G
4113
| MB Phase 1 Surface Parking and Site Lighting |  | 3351 | X |  |  |  | P | 27 | X |  |  |  |  | Chancellor Approved
[8 empty] | W | 42 | X
| 923060 | [6 empty] | C | 3282 | X
3351
| MB Phase 1 Infrastructure--Surcharge 4th St. West |  | 4112 | X |  |  |  | P | 144 | X |  |  |  |  | Chancellor Approved
[8 empty] | W | 268 | X
| 923070 | [6 empty] | C | 3700 | X
4112
| MB Phase 1 Infrastructure--Demolition and Remediation |  | 4652 | X |  |  |  | P | 160 | X |  |  |  |  | Chancellor Approved
[8 empty] | W | 296 | X
| 923075 | [6 empty] | C | 4196 | X
4652
| MB Phase 1 Infrastructure--Surcharge 4th St. East |  | 4732 | X |  |  |  | P | 165 | X |  |  |  |  | Chancellor Approved
[8 empty] | W | 307 | X
| 923076 | [6 empty] | C | 4260 | X
4732
| MB Phase 1 Infrastructure--Utilities Plant and Design |  | 3040 | X |  |  |  | P | 106 | X |  |  |  |  | Chancellor Approved
[8 empty] | W | 199 | X
| 923080 | [6 empty] | C | 2735 | X
3040
| MB Phase 1 Infrastructure--Streets and Utilities Construction |  | 3763 | X |  |  |  | P | 132 | X |  |  |  |  | Chancellor Approved
[8 empty] | W | 244 | X
| 923090 | [6 empty] | C | 3387 | X
3763
| S/M HSE-6 Neurology Electron Microscope Room Remodel |  | 282 | X |  |  |  | P | 26 | X |  |  |  |  | Chancellor Approved
[8 empty] | W | 39 | X
| 940000 | [6 empty] | C | 217 | X
282
| LPPI Sprinker System Upgrade |  | 607 | X |  |  |  | P | 23 | X |  |  |  |  | Chancellor Approved
[8 empty] | W | 21 | X
[8 empty] | C | 563 | X
607
| S/P S-11 Pharmaceutical Chemistry Lab Renovation |  | 1088 | X |  |  |  | P | 66 | X |  |  |  |  | Chancellor Approved
|  |  | 100 | G |  |  |  | W | 96 | X
|  |  | 1188 |  |  |  |  | C | 926 | X
[8 empty] | C | 100 | G
1188
| S/M S-8 HHMI Lab renovation |  | 649 | X |  |  |  | P | 42 | X |  |  |  |  | Chancellor Approved
[8 empty] | W | 66 | X
[8 empty] | C | 541 | X
649
| S/M S-8 Physiology Lab Renovation |  | 461 | X |  |  |  | P | 33 | X |  |  |  |  | Chancellor Approved
[8 empty] | W | 52 | X
[8 empty] | C | 376 | X
461
| Banks Loans or Bonds (LB) |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
*Internal Loans (LB*)
| Other (i.e. Campus Funds) (X) |  | 34596 | [5 empty] | 34596 |  |  | 0 |  |  | 0
| Gifts (G) |  | 11768 | [5 empty] | 11768 |  |  | 0 |  |  | 0
| Federal (F) |  | 1000 | [5 empty] | 1000 |  |  | 0 |  |  | 0
| Hospital Reserves (HR) |  | 15758 |  |  | 0 |  |  | 14428 |  |  | 1330 |  |  | 0
| Registration Fees (R) |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
| Reserves other than University Fees (N) |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
| University or Educational Funds (U) | [13 empty] | 0
| TOTAL |  | 63122 |  |  | 0 |  |  | 61792 |  |  | 1330 |  |  | 0
| STATE FUNDS | ( | 12359 | ) | ( | 0 | ) | ( | 12359 | ) | ( | 0 | ) |  | 0

## Santa Barbara
SANTA BARBARA CAMPUS
2000-2001 NON-STATE CAPITAL BUDGET
($ in thousands)
C U R R E N T S T A T U S
| Project | Project Cost |  |  | Prefunded |  |  | 2000-2001 |  |  | Beyond |  |  | Date | Action | Approval Letter | Date | Action | Cost
[11 empty] | 2000-2001 | [6 empty] | Action | Cost
| San Rafael Housing Addition |  | 3000 | N | P | 1941 | N | W | 1103 | LB |  |  |  | 7/00 | Regents | 11/15/00 | 7/19/00 | P,W,C and E | 57860000
| Program (986255) |  | 54860 | LB | W | 1059 | N | C | 9806 | LB | [7 empty] | External Finance &
|  |  | 57860 |  | W | 878 | LB |  | 10909 | [8 empty] | Reserves Funds
[5 empty] | C | 40558 | LB
[5 empty] | E | 2515 | LB
46951
|  |  | 3000 | N |  |  |  | C | 7298 | LB |  |  |  | 3/01 | Regents | 4/18/01 | 3/15/01 | C | 7298000
|  |  | 62158 | LB
65158
| Recreation Center Expansion |  | 14950 | LB |  |  |  | P | 688 | LB |  |  |  | 9/00 | Regents | 8/25/00 | 9/5/00 | P,W,C and E | 16945000
| (981400) |  | 1995 | N |  |  |  | W | 739 | LB
|  |  | 16945 |  |  |  |  | C | 13523 | LB
[8 empty] | C | 1254 | N
[8 empty] | E | 741 | N
16945
| Broida Hall Building Renewal |  | 11418 | ( ) | P | 449 | ( ) |  | 340 | X |  |  |  |  | Admin. Approval | 10/7/00
| (988621) |  | 340 | X | W | 712 | ( ) |  | 1600 | LB
|  |  | 1600 | LB | C | 10257 | ( ) |  | 1940
|  |  | 13358 |  |  | 11418
| Broida Hall Seismic Correction |  | 4548 | ( ) | P | 147 | X |  | 413 | ( ) |  |  |  |  | Admin. Approval | 10/7/00
| (988779) |  | 374 | X | W | 227 | X |  | 1866 | LB*
|  |  | 1866 | LB* | C | 4135 | ( ) |  | 2279
|  |  | 6788 |  |  | 4509
| Intercollegiate Athletics Building |  | 13717 | LB |  |  |  | P | 719 | LB |  |  |  | 1/01 | Regents | 2/21/01 | 1/31/01 | P, W, C and E | 15017000
| (981300) |  | 1300 | N |  |  |  | W | 699 | LB
|  |  | 15017 |  |  |  |  | C | 12299 | LB
[8 empty] | C | 664 | N
[8 empty] | E | 636 | N
15017
| CNSI Building (981270) |  | 1971 |  |  |  |  | P | 1971 |  |  |  |  | 1/01 | Regents | 3/9/01 | 1/18/01 | CISI/State Funds | 3051000
|  |  | 80 | G |  |  |  | P | 80 | G | [7 empty] | "P" Only
|  |  | 1000 | N |  |  |  | P | 1000 | N
|  |  | 3051 | [5 empty] | 3051
| Engineering II--First Floor MOCVD |  | 932 | X |  |  |  | P | 59 | X |  |  |  |  | Chancellor Approved
| Laboratory Renovations | [6 empty] | W | 79 | X
| 981260 | [6 empty] | C | 794 | X
932
| DeLaGuerra Patio Expansion |  | 300 | N |  |  |  | P | 11 | N |  |  |  |  | Chancellor Approved
| 986295 | [6 empty] | W | 23 | N
[8 empty] | C | 266 | N
300
| Student Health Services Lobby |  | 374 | R |  |  |  | P | 16 | R |  |  |  |  | Chancellor Approved
| Renovation | [6 empty] | W | 21 | R
| 981290 | [6 empty] | C | 337 | R
374
| Building 570 Laboratory |  | 589 | X |  |  |  | P | 33 | X |  |  |  |  | Chancellor Approved
| Conversion | [6 empty] | W | 46 | X
[8 empty] | C | 485 | X
[8 empty] | E | 25 | X
589
| Relocation of Biology Shops and |  | 699 | X |  |  |  | P | 45 | X |  |  |  |  | Chancellor Approved
| Storeroom to Bldg. 569 | [6 empty] | W | 49 | X
| 981310 | [6 empty] | C | 605 | X
[8 empty] | E | 0 | X
[9 empty] | 699 | X
| Banks Loans or Bonds (LB) |  | 92425 |  |  | 43951 |  |  | 48474 |  |  | 0 |  |  | 0
| *Internal Loans (LB*) |  | 1866 | [5 empty] | 1866 | [5 empty] | 0
| Other (i.e. Campus Funds) (X) |  | 2934 |  |  | 374 |  |  | 2560 |  |  | 0 |  |  | 0
| Gifts (G) |  | 80 |  |  | 0 |  |  | 80 |  |  | 0 |  |  | 0
| Federal (F) |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
| Hospital Reserves (HR) |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
| Registration Fees (R) |  | 374 |  |  | 0 |  |  | 374 |  |  | 0 |  |  | 0
| Reserves other than University Fees (N) |  | 7595 |  |  | 3000 |  |  | 4595 |  |  | 0 |  |  | 0
| University or Educational Funds (U) | [13 empty] | 0
| TOTAL |  | 105274 |  |  | 47325 |  |  | 57949 |  |  | 0 |  |  | 0
| STATE FUNDS | ( | 17937 | ) | ( | 15553 | ) | ( | 2384 | ) | ( | 0 | ) |  | 0

## Santa Cruz
SANTA CRUZ CAMPUS
2000-2001 NON-STATE CAPITAL BUDGET
($ in thousands)
C U R R E N T S T A T U S
| Project | Project Cost |  |  | Prefunded |  |  | 2000-2001 |  |  | Beyond |  |  | Date | Action | Approval Letter | Date | Action | Cost
[11 empty] | 2000-2001 | [6 empty] | Action | Cost
| Colleges Nine and Ten |  | 73503 | LB | P | 2448 | LB | C | 6323 | LB |  |  |  | 11/00 | Regents | 12/6/00 | 11/8/00 | P,W,C and E | 82945000
| Residence Halls (976292) |  | 9042 | N | P | 164 | N | C | 3500 | N
|  |  | 400 | G | W | 2600 | LB |  | 9823
|  |  | 82945 |  | W | 184 | N
[5 empty] | C | 62132 | LB
[5 empty] | C | 3233 | N
[5 empty] | C | 400 | G
[5 empty] | E | 1961 | N
73122
| Infill Apartments (976400) |  | 2221 | N |  |  |  | P | 2221 | N |  |  |  | 1/01 | Regents | 2/14/01 | 1/17/01 | P Only | 2221000
|  |  | 54062 | LB |  |  |  | P | 2221 | LB |  |  |  | 3/01 | Regents | 4/18/01 | 3/15/01 | W, C and E
|  |  | 2100 | N |  |  |  | W | 2625 | LB
|  |  | 56162 |  |  |  |  | C | 49216 | LB
[8 empty] | E | 2100 | N
56162
| Engineering Building Addition A |  | 192 | ( ) |  |  |  | P | 192 | ( ) |  |  |  | 1/01 | Regents | 2/28/01 | 1/18/01 | CISI/State Funds | 192000
| (971110) | [16 empty] | "P" Only
| Physical Sciences Building |  | 500 | ( ) |  |  |  | P | 500 | ( ) |  |  |  | 1/01 | Regents | 3/9/01 | 1/18/01 | CISI/State Funds | 500000
| Upgrade (971100) | [16 empty] | "P" Only
| Bioinformatics Equipment |  | 1000 | ( ) |  |  |  | E | 1000 | ( ) |  |  |  | 4/01 | Presidents Authority | 6/29/01 | 4/27/01 | "E" Only | 1000000
| (971101) | [16 empty] | CISI/State Funds
| Center For Ocean Health |  | 2000 | LB* |  | 1800 | LB* |  | 200 | LB* |  |  |  | 1/01 | Internal Loan | 2/5/01
| Physical Sciences Building |  | 47682 | ( ) | P | 1232 | U | C | 264 | G |  |  |  |  | Chancellor Approved
| (970770) |  | 1232 | U | P | 1232 | G
|  |  | 8600 | LB* | W | 2053 | ( ) | C | 2600 | LB* |  |  |  | 8/00 | Internal Loan | 8/2/00
|  |  | 2264 | G | C | 43629 | ( ) | C | 1000 | LB* |  |  |  | 6/01 | Internal Loan | 6/1/01
|  |  | 59778 |  | C | 3000 | LB* |  | 3864
[5 empty] | C | 768 | G
[5 empty] | E | 2000 | ( )
[5 empty] | E | 2000 | LB*
55914
| Baskin Engineering |  | 326 | X |  |  |  | P | 20 | X |  |  |  |  | Chancellor Approved
| Room 213 Renovations (977080) | [6 empty] | W | 20 | X
[8 empty] | C | 278 | X
[8 empty] | E | 8 | X
326
| Bi-Directional Bus Project |  | 499 | F |  |  |  | P | 55 | X |  |  |  |  | Chancellor Approved
| (976500) |  | 102 | X |  |  |  | W | 10 | X
|  |  | 601 |  |  |  |  | C | 499 | F
[8 empty] | C | 37 | X
601
| Monterey Bay Education, Science, and | [6 empty] | P | 137 | G |  |  |  |  | Chancellor Approved
| Technology Center (MBEST) |  | 714 | G |  |  |  | P | 1 | X
| Infrastructure improvement (970992) |  | 7 | X |  |  |  | P | 63 | LB
|  |  | 264 | LB |  |  |  | C | 577 | G
|  |  | 985 |  |  |  |  | C | 6 | X
[8 empty] | C | 201 | LB
985
| Central Garage TAPS Office Addition |  | 55 | X |  |  |  | P | 19 | X |  |  |  |  | Chancellor Approved
| (973300) |  | 370 | LB |  |  |  | W | 17 | X
|  |  | 425 |  |  |  |  | C | 19 | X
[9 empty] | 370 | LB
425
| Banks Loans or Bonds (LB) |  | 128199 |  |  | 67180 |  |  | 61019 |  |  | 0 |  |  | 0
| *Internal Loans (LB*) |  | 10600 |  |  | 6800 |  |  | 3800 | [5 empty] | 0
| Other (i.e. Campus Funds) (X) |  | 490 |  |  | 0 |  |  | 490 |  |  | 0 |  |  | 0
| Gifts (G) |  | 3378 |  |  | 2400 |  |  | 978 |  |  | 0 |  |  | 0
| Federal (F) |  | 499 |  |  | 0 |  |  | 499 |  |  | 0 |  |  | 0
| Hospital Reserves (HR) |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
| Registration Fees (R) |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
| Reserves other than University Fees (N) |  | 11142 |  |  | 5542 |  |  | 5600 |  |  | 0 |  |  | 0
| University or Educational Funds (U) |  | 1232 |  |  | 1232 | [8 empty] | 0
| TOTAL |  | 155540 |  |  | 83154 |  |  | 72386 |  |  | 0 |  |  | 0
| STATE FUNDS | ( | 49374 | ) | ( | 47682 | ) | ( | 1692 | ) | ( | 0 | ) |  | 0

## OP
OFFICE OF THE PRESIDENT
2000-2001 NON-STATE CAPITAL BUDGET
($ in thousands)
C U R R E N T S T A T U S
| Project | Project Cost |  |  | Prefunded |  |  | 2000-2001 |  |  | Beyond |  |  | Date | Action | Approval Letter | Date | Action | Cost
[11 empty] | 2000-2001 | [6 empty] | Action | Cost
A. | UC Washington DC Center |  | 22286 | LB | P | 1000 | LB | W | 330 | X |  |  |  | 9/00 | President's Auth. | 3/13/01 | 2/27/01 | W, C and E | 3031000
| (908530) |  | 6031 | X | W | 1547 | LB | C | 1819 | X
|  |  | 2001 | LB* | C | 18615 | LB | E | 882 | X
|  |  | 30318 |  | C | 3000 | X |  | 3031
[5 empty] | C | 2001 | LB*
[5 empty] | E | 1124 | LB
27287
| Banks Loans or Bonds (LB) |  | 22286 |  |  | 22286 | [5 empty] | 0 |  |  | 0
| *Internal Loans (LB*) |  | 2001 |  |  | 2001 | [8 empty] | 0
| Other (i.e. Campus Funds) (X) |  | 6031 |  |  | 3000 |  |  | 3031 |  |  | 0 |  |  | 0
| Gifts (G) |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
| Federal (F) |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
| Hospital Reserves (HR) |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
| Registration Fees (R) |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
| Reserves other than University Fees (N) |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
| University or Educational Funds (U) | [13 empty] | 0
| TOTAL |  | 30318 |  |  | 27287 |  |  | 3031 |  |  | 0 |  |  | 0
| STATE FUNDS | ( | 0 | ) | ( | 0 | ) | ( | 0 | ) | ( | 0 | ) |  | 0

## DANR
DIVISION OF
AGRICULTURE AND NATURAL RESOURCES
2000-2001 NON-STATE CAPITAL BUDGET
($ in thousands)
C U R R E N T S T A T U S
| Project | Project Cost |  |  | Prefunded |  |  | 2000-2001 |  |  | Beyond |  |  | Date | Action | Approval Letter | Date | Action | Cost
[11 empty] | 2000-2001 | [6 empty] | Action | Cost
A.
| Banks Loans or Bonds (LB) |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
*Internal Loans (LB*)
| Other (i.e. Campus Funds) (X) |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
| Gifts (G) |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
| Federal (F) |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
| Hospital Reserves (HR) |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
| Registration Fees (R) |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
| Reserves other than University |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
| Fees (N) | [13 empty] | 0
| University or Educational Funds (U) | [13 empty] | 0
| TOTAL |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
| STATE FUNDS | ( | 0 | ) | ( | 0 | ) | ( | 0 | ) | ( | 0 | ) |  | 0