## Berkeley
BERKELEY CAMPUS
1982-83 NON-STATE CAPITAL BUDGET
($000)
[5 empty] | C U R R E N T S T A T U S | [11 empty] | PRIOR ACTION/COMMENTS
|  |  | Project | [8 empty] | Beyond |  |  |  | Approval
| Project |  | Cost |  |  | Prefunded |  |  | 1982-83 |  |  | 1982-83 |  | Action |  | Letter | Date | Action | Cost
A. | CAC Deficiencies, High-Rise Fire |  | DEFERRED |  |  | --- |  |  | --- |  |  | --- |  | 10/82 | Deferred | --- | 10/80 | 1981-84 CIP | 542
| and Life Safety (912030) | [13 empty] | to 1984-85 |  | 10/81 | 1982-85 CIP | 735
B. | Donner Laboratory Alterations |  | 420 | U | P | 19 | U | C | 379 | U |  | --- |  | 10/81 | Admin | 11/11/81 | 1/80 | 1980-83 CIP | 330
| (911260) |  |  |  | W | 22 | U | [9 empty] | 10/80 | 1981-84 CIP | 330
41
C. | Central Control System (912100) |  | DELETED |  |  | --- |  |  | --- |  |  | --- |  | 9/83 | Deleted | 11/6/80 | 9/80 | 1980-83 CIP | 1075
[15 empty] | by Campus |  | 10/80 | 1981-84 CIP | 1075
[17 empty] | 10/81 | 1982-85 CIP | 1075
D. | Hill Area Dewatering and |  | 945 | U | PWC | 485 | U | C | 230 | U | C | 230 | U | 10/81 | Future funding |  | 2/79 | 1979-82 CIP | 945
| Stabilization (911030) | [13 empty] | not scheduled or |  |  | (listed as 2 projects)
[15 empty] | approved pending |  | 1/80 | 1980-83 CIP | 945
[15 empty] | definition of |  |  | (listed as 2 projects)
[15 empty] | project scope |  | 10/80 | 1981-84 CIP | 945
(listed as 2 projects)
E. | Dwight-Derby Housing and |  | DELETED |  |  | --- |  |  | --- |  |  | --- |  | 10/82 | Deleted--replaced |  | 10/81 | 1982-85 CIP | 20067
| Parking Complex (911720) | [13 empty] | by projects "O", "P" &
"R" in 1982-83
F. | Stern Hall - West Annex (912010) |  | DEFERRED |  |  | --- |  |  | --- |  |  | --- |  | 10/82 | Deferred | --- | 10/81 | 1982-85 CIP | 1750
G. | CAC Deficiencies (Handicapped) |  | 300 | U | PW | 35 | U | C | 265 | U |  | --- |  | 10/82 | Admin | 12/7/82 | 9/80 | 1980-83 CIP | 250
| Site Modifications, Step 2 | [15 empty] | 10/80 | 1981-84 CIP | 250
| (912080) | [15 empty] | 10/81 | 1982-85 CIP | 250
H. | CAC Deficiencies, Bowles Hall, |  | DELETED |  |  | --- |  |  | --- |  |  | --- |  | 10/82 | Deleted | --- | 1/80 | 1980-83 CIP | 1025
| Step 2 (911600) | [13 empty] | by campus |  | 10/80 | 1981-84 CIP | 1025
[17 empty] | 10/81 | 1982-85 CIP | 400
I. | 2223 Fulton Street Remodeling |  | DEFERRED |  |  | --- |  |  | --- |  |  | --- |  | 10/82 | Deferred to | --- | 10/81 | 1982-85 CIP | 615
| and Ventilation Improvements | [13 empty] | 1983-84
(912300)
J. | Bodega Marine Laboratory |  | DELETED |  |  | --- |  |  | --- |  |  | --- |  | 9/83 | Deleted | 11/3/82 | 10/80 | 1981-84 CIP | 755
| Housing Addition (911740) | [13 empty] | by Campus |  | 10/81 | 1982-85 CIP | 755
[17 empty] | 10/82 | 1982-85 CIP | 1170
K. | Biological Sciences - |  | DEFERRED |  |  | --- |  |  | --- |  |  | --- |  | 10/82 | Deferred to | --- | 10/81 | 1982-85 CIP | 31788
| Biochemistry Annex (912270) | [13 empty] | 1983-84
L. | Cory Hall Fifth Floor Addition and |  | 8500 | G |  | --- |  | P | 180 | G | C | 6900 | G | 9/83 | Regents | 11/10/83 | 7/82 | 1982-85 CIP | 7253
| Alterations for Computer-Aided | [6 empty] | W | 420 | G | E | 1000 | G
| Design (912407) | [7 empty] | 600 |  |  | 7900
M. | Silver Laboratory Addition |  | 281 | X | PWC | 215 | X | C | 66 | X |  | --- |  | 9/82 | Admin | 9/13/82 | 10/81 | 1981-84 CIP | 150
(912340)
N. | CAC Deficiencies, Asbestos |  | 300 | N | PWC | 260 | U | C | 300 | N |  | --- |  | 10/82 | Admin | 11/11/81 | 10/81 | 1981-84 CIP | 592
| Hazards, Step 2 (913230) |  | 260 | U
560
O. | Dwight-Derby Alts., Phase II |  | 8888 | LB |  | --- |  | PWCE | 8888 | LB |  | --- |  | 10/82 | Regents | 11/2/82 | 10/81 | Replaces project "E" in
| (911720) | [16 empty] | 1982-83
P. | Dwight-Derby Alts., Recreation |  | 523 | LB |  | --- |  | PWCE | 523 | LB |  | --- |  | 10/82 | Admin | 11/2/82 | 10/81 | Replaces project "E" in
| (911720) | [16 empty] | 1982-83
Q. | Latimer Hall, 6th and 7th Floor |  | 362 | U | PWCE | 362 | U | CE | 160 | X |  | --- |  | 1/82 | Admin | 3/17/82
| Alts. (912370) |  | 327 | X | PWCE | 167 | X
|  |  | 689 |  |  | 529
R. | Dwight-Derby Alts., Phase III |  | 9614 | LB |  | --- |  | PWCE | 9614 | LB |  | --- |  | 1/83 | Regents | 1/26/83 | 10/81 | Replaces project "E" in
| (911720) | [16 empty] | 1982-83
S. | Intramural Sports Facility and |  | 13900 | LB | PWC | 1900 | N | E | 750 | LB | C | 900 | LB | 6/84 | Regents | 6/19/84 | 7/79 | 1979-82 CIP
| Related Parking (910800) |  | 1900 | N | PWC | 4100 | R | [10 empty] | (Step 1-Planning
|  |  | 4100 | R | C | 12250 | LB | [10 empty] | purposes only)
|  |  | 19900 |  |  | 18250 | [10 empty] | 7/80 | 1979-82 & | 7000
1980-83 CIP (Step 1)
[17 empty] | 10/80 | 1980-83 CIP | 12000
(Step 2)
T. | College of Chemistry, Unit III | ( | 13182 | ) |  | --- |  | P | 30 | X | P | 518 | G | 9/92 | Admin | 9/29/92 | 10/82 | 1983-86 CIP | 22199
| (912390) |  | 14288 | G | [6 empty] | W | 2221 | G |  |  |  | 10/83 | 1984-87 CIP | 30100
|  |  | 10440 | LB | [6 empty] | ( C | 13182 | ) |  |  |  | 5/89 | 1983-86 &
|  |  | 30 | X | [6 empty] | C | 10549 | G |  |  |  |  | 1988-91 CIP | 32846
|  |  | 37940 | [7 empty] | C | 8235 | LB |  |  |  | 10/91 | 1992-95 CIP | 37940
[11 empty] | E | 2205 | LB
[11 empty] | E | 1000 | G
37910
| Gifts (G) |  | 22788 | G |  | --- |  |  | 600 | G |  | 22188 | G
| Bank Loans or Bonds (LB) |  | 43365 | LB |  | 12250 | LB |  | 19775 | LB |  | 11340 | LB
Reserves other than University
| Registration Fees (N) |  | 2200 | N |  | 1900 | N |  | 300 | N |  | ---
| Registration Fees (R) |  | 4100 | R |  | 4100 | R |  | --- |  |  | ---
| Regents' Appropriations (U) |  | 2287 | U |  | 1183 | U |  | 874 | U |  | 230 | U
| Other (X) |  | 638 | X |  | 382 | X |  | 256 | X |  | ---
| TOTAL |  | 75378 |  |  | 19815 |  |  | 21805 |  |  | 33758
| STATE FUNDS | ( | 13182 | ) | ( | --- | ) | ( | --- | ) | ( | 13182 | )

## Davis
DAVIS CAMPUS
1982-83 NON-STATE CAPITAL BUDGET
($000)
[6 empty] | C U R R E N T S T A T U S | [7 empty] | PRIOR ACTION/COMMENTS
|  | Project | [6 empty] | Beyond |  |  |  | Approval
| Project | Cost |  | Prefunded |  | 1982-83 |  |  | 1982-83 |  | Action |  | Letter | Date | Action | Cost
A. | Surface Parking, 1982-83 | DELETED |  | --- |  | --- |  |  | --- |  | 10/82 | Deleted | --- | 10/81 | 1982-85 CIP | 200
by campus
B. | CAC Deficiencies, Non-State | DEFERRED |  | --- |  | --- |  |  | --- |  | 10/82 | Deferred | --- | 10/81 | 1982-85 CIP | 734
| Funded, Step 2 (Handicapped) | [10 empty] | to 1984-85
(930680)
C. | UCDMC Sacramento - | 1000 | U | --- | PW | 250 | U | C | 750 | U | 10/82 | Regents | 12/17/82 | 10/81 | 1982-85 CIP | 24337
| North/South Wing Reconstruction | 10943 | HR |  | PW | 1166 | HR | C | 9277 | HR
| and Remodeling (934430) | 1000 | N |  | C | 500 | HR | C | 1000 | N
|  | 12943 |  |  |  | 1916 |  |  | 11027
D. | Hospital and Clinics Reserve | 1000 | HR | --- | PWC | 1000 | HR |  | --- |  | 11/81 | Regents' | N/A
| Funded Improvements, Under | [10 empty] | Budget
$150,000, 1982-83
E. | Hospital and Clinics Reserve | 1000 | HR | --- | E | 1000 | HR |  | --- |  | 11/81 | Regents' | N/A
| Funded New Equipment, 1982-83 | [10 empty] | Budget
F. | UCDMC Sacramento, Energy | DEFERRED |  | --- |  | --- |  |  | --- |  | 10/82 | Deferred | --- | 10/81 | 1982-85 CIP | 620
| Conservation (934570) | [10 empty] | to 1984-85
G. | UCDMC Sacramento, | DEFERRED |  | --- |  | --- |  |  | --- |  | 10/82 | Deferred | --- | 10/81 | 1982-85 CIP | 500
| Labor/Delivery Suite Remodel | [10 empty] | to 1983-84
(934550)
H. | UCDMCS, Pneumatic Trash and | DEFERRED |  | --- |  | --- |  |  | --- |  | 10/82 | Deferred | --- | 10/81 | 1982-85 CIP | 550
| Linen Chute Installation (934580) | [10 empty] | by campus
I. | UCDMCS, Seismic Deficient | DEFERRED |  | --- |  | --- |  |  | --- |  | 10/82 | Deferred | --- | 10/81 | 1982-85 CIP | 4336
| Buildings Renovations | [10 empty] | by campus
J. | UCDMC Sacramento, Hospital | 5125 | HR | --- | E | 2000 | HR | E | 3125 | HR | 9/83 | Admin | 1/19/83 | 10/82 | 1983-86 CIP | 3500
| Information System Equipment | [12 empty] | 10/83 | 1983-86 CIP | 4325
(934382)
K. | UCDMC Sacramento, Pediatrics | 648 | HR | --- | PWC | 648 | HR |  | --- |  | 1/83 | Admin | 1/19/83
Unit Renovation (934510)
L. | UCDMC Sacramento, East 5 | 241 | HR | --- | P | 10 | HR | C | 215 | HR | 9/83 | Admin | 1/19/83 | 10/82 | 1982-85 CIP | 170
| Physical Medicine and |  |  |  | W | 16 | HR
| Rehabilitations and Neurosciences |  |  |  |  | 26
Remodel (934381)
M. | Seed and Plant Materials Service | 120 | G | --- |  | --- |  | P | 15 | G | 9/84 | Admin | 9/19/84 | 10/82 | 1982-85 CIP | 765
| and Research Facility (930750) | 500 | LB |  |  |  |  | W | 35 | G
|  | 620 | [5 empty] | C | 70 | G
[8 empty] | C | 500 | LB
620
| Gifts (G) | 120 | G | --- |  | --- |  |  | 120 | G
| Hospital Reserves (HR) | 18957 | HR | --- |  | 6340 | HR |  | 12617 | HR
| Bank Loans or Bonds (LB) | 500 | LB | --- |  | --- |  |  | 500 | LB
Reserves other than University
| Registration Fee (N) | 1000 | N | --- |  | --- |  |  | 1000 | N
| Regents' Appropriations (U) | 1000 | U | --- |  | 250 | U |  | 750 | U
| TOTAL | 21577 |  | --- |  | 6590 |  |  | 14987

## Irvine
IRVINE CAMPUS
1982-83 NON-STATE CAPITAL BUDGET
($000)
[9 empty] | C U R R E N T S T A T U S | [7 empty] | PRIOR ACTION/COMMENTS
|  |  | Project | [8 empty] | Beyond |  |  |  | Approval
| Project |  | Cost |  |  | Prefunded |  |  | 1982-83 |  |  | 1982-83 |  | Action |  | Letter | Date | Action | Cost
A. | Student Services 2 (992040) |  | 1525 | LB | P | 45 | LB | C | 1425 | LB |  | --- |  | 11/81 | Regents' | N/A
|  |  | 100 | R | C | 55 | LB | E | 100 | R |  |  |  |  | Budget
|  |  | 1625 |  |  | 100 |  |  | 1525
B. | UCIMC Library Module (994301) |  | 275 | G | PW | 110 | G | ( E | 79 | H ) |  | --- |  | 11/81 | Regents' | N/A | 10/79 | 1980-83 CIP | 2454
|  | ( | 770 | H ) | ( W | 25 | H ) | E | 253 | X |  |  |  |  | Budget |  | 10/80 | 1981-84 CIP | 2639
|  |  | 231 | R | ( C | 666 | H ) |  | 332
|  |  | 1395 | X | C | 165 | G
|  |  | 2671 |  | C | 231 | R
[5 empty] | C | 1142 | X
2339
C. | Hospital and Clinics |  | 1500 | HR |  | --- |  | PWC | 1500 | HR |  | --- |  | 11/81 | Regents' | N/A | 10/81 | 1982-85 CIP | 720
| Reserve-Funded Improvements | [13 empty] | Budget
Under $150,000, 1982-83
D. | Physical Sciences Research |  | DELETED |  |  | --- |  |  | --- |  |  | --- |  | 3/82 | Deleted: | ---
| Facility, Phase 2 | [13 empty] | Replaced by
"G" in 1982-83
E. | Biological Sciences Research |  | 7864 | G |  | --- |  |  | --- |  | P | 193 | G | 11/81 | Regents' | N/A | PHASE 2 ONLY:
| Facility, Phase 2 and 3(991665 & | [9 empty] | W | 235 | G |  | Budget |  | 9/80 | 1980-83 CIP | 1920
| 991667) | [9 empty] | C | 6818 | G |  |  |  | 10/80 | 1981-84 CIP | 1730
[11 empty] | E | 618 | G |  |  |  | 10/81 | 1982-85 CIP | 2085
7864
F. | Marine Biophysics Facility |  | 2178 | G | P | 60 | G | C | 1994 | G |  | --- |  | 11/81 | Regents' | N/A | 9/80 | 1981-84 CIP | 2178
| (992020) |  |  |  | W | 74 | G | E | 50 | G |  |  |  |  | Budget
[6 empty] | 134 |  |  | 2044
G. | Physical Sciences Research |  | 800 | X | P | 24 | X | WC | 776 | X |  | --- |  | 3/82 | Admin | 3/25/82 | 10/81 | 1982-85 CIP | 462
Facility, Phase 2 (991635)
H. | Transportation Improvements |  | 2000 | LB | P | 130 | LB | WC | 1070 | LB | C | 800 | LB | 6/84 | Admin | 6/19/84 | 10/81 | 1982-85 CIP | 2000
| Program (996588) | [15 empty] | 3/82 | 1983-86 CIP | 2000
I. | University Extension Facility |  | 1280 | N |  | --- |  | P | 30 | N | C | 205 | N | 5/84 | Admin | 5/14/84 | 7/82 | 1982-85 CIP | 1075
| (991690) | [6 empty] | W | 37 | N
[8 empty] | C | 1008 | N
1075
J. | UCIMC Energy Conservation |  | 220 | F |  | --- |  | PWC | 220 | F |  | --- |  | 6/82 | Admin | 7/6/82
| (998804) |  | 127 | HR |  |  |  | PC | 127 | HR
|  |  | 347 | [5 empty] | 347
K. | Professional Programs Facility |  | 2500 | LB |  | --- |  | P | 64 | U | P | 108 | U | 6/88 | Admin | 6/15/88 | 10/82 | 1982-85 CIP | 6310
| (991145) (Formerly: Graduate |  | 1500 | U | [6 empty] | W | 207 | U |  |  |  | 10/82 | 1983-86 CIP | 6310
| School of Management) |  | 2050 | X | [6 empty] | C | 1121 | U |  |  |  | 11/85 | 1985-88 CIP | 6050
|  |  | 6050 | [7 empty] | C | 2050 | X
[11 empty] | C | 1860 | LB
[11 empty] | E | 640 | LB
5986
L. | Organic Chemistry Laboratory | ( | 15 | ) | ( PW | 15 | ) | C | 208 | U |  | --- |  | 10/82 | Admin | 12/7/82
| Conversion (992010) |  | 208 | U
223
M. | Materiel Management, Phase 5 |  | DELETED |  |  | --- |  |  | --- |  |  | --- |  | 9/83 | Deleted | --- | 10/82 | Addend. to 1982-85 | 778
| (Building 20-A) (995040) | [13 empty] | by campus |  |  | CIP
N. | Dietary Renovations, Phase 2 |  | DELETED |  |  | --- |  |  | --- |  |  | --- |  | 9/83 | Deleted | --- | 10/82 | 1982-85 CIP | 751
| (995081) | [13 empty] | by campus
O. | Donald Bren Events Center |  | 1617 | G |  | --- |  | P | 86 | G | P | 171 | G | 7/86 | Regents | 8/1/86 | 10/82 | 1983-86 CIP | 6855
| (997239) (Formerly: Campus |  | 13383 | LB | [6 empty] | W | 307 | G |  |  |  | 3/84 | 1983-86 CIP and
| Events Center) |  | 15000 | [7 empty] | C | 1883 | LB |  |  |  |  | 1984-87 CIP | 11497
[11 empty] | C | 10977 | LB
[11 empty] | E | 1053 | G
[11 empty] | E | 523 | LB
14914
P. | Biomedical Laser Research Facility |  | 50 | U |  | --- |  | P | 50 | U |  | --- |  | 10/82 | Admin | 12/7/82
| (991720) |  | 4950 | G |  |  |  | PWCE | 4950 | G
|  |  | 5000 | [5 empty] | 5000
Q. | Alumni House (991695) |  | 435 | G |  | --- |  | P | 10 | G | C | 85 | G | 5/84 | Admin | 5/14/84 | 10/82 | 1982-85 CIP | 350
[8 empty] | W | 13 | G
[8 empty] | C | 327 | G
350
R. | ICS - Engineering Research |  | 1130 | U |  | --- |  | P | 54 | X | C | 701 | X | 9/84 | Admin | 11/6/84 | 1/83 | 1982-85 CIP | 1145
| Facility (991740) |  | 820 | X |  |  |  | W | 65 | X | [6 empty] | 9/83 | 1983-86 CIP | 1600
|  |  | 1950 |  |  |  |  | C | 1130 | U
1249
S. | Faculty Research Facility, |  | 280 | G |  | --- |  | PWC | 280 | G |  | --- |  | 3/83 | Admin | 4/18/83
| Developmental Biology Center |  | 50 | X |  |  |  | C | 50 | X
| Addition (991750) |  | 330 | [5 empty] | 330
| Federal (F) |  | 220 | F |  | --- |  |  | 220 | F |  | ---
| Gifts (G) |  | 17599 | G |  | 409 | G |  | 7710 | G |  | 9480 | G
| Hospital Reserves (HR) |  | 1627 | HR |  | --- |  |  | 1627 | HR |  | ---
| Bank Loans or Bonds (LB) |  | 19408 | LB |  | 230 | LB |  | 2495 | LB |  | 16683 | LB
Reserves other than University
| Registration Fees (N) |  | 1280 | N |  | --- |  |  | 1075 | N |  | 205 | N
| Registration Fees (R) |  | 331 | R |  | 231 | R |  | 100 | R |  | ---
| Regents' Appropriations (U) |  | 2888 | U |  | --- |  |  | 1452 | U |  | 1436 | U
| Other (X) |  | 5115 | X |  | 1166 | X |  | 1198 | X |  | 2751 | X
| TOTAL |  | 48468 |  |  | 2036 |  |  | 15877 |  |  | 30555
| State Funds | ( | 15 | ) | ( | 15 | ) | ( | --- | ) | ( | --- | )
| Health Science Bond Funds (H) | ( | 770 | H ) | ( | 691 | H ) | ( | 79 | H ) | ( | --- | )
| TOTAL | ( | 785 | ) | ( | 706 | ) | ( | 79 | ) | ( | --- | )

## Los Angeles
LOS ANGELES CAMPUS
1982-83 NON-STATE CAPITAL BUDGET
($000)
[8 empty] | C U R R E N T S T A T U S | [7 empty] | PRIOR ACTION/COMMENTS
|  | Project | [8 empty] | Beyond |  |  |  | Approval
| Project | Cost |  |  | Prefunded |  |  | 1982-83 |  |  | 1982-83 |  | Action |  | Letter | Date | Action | Cost
A. | Memorial Activities Center "B" | 3010 | G/N | P | 84 | G/N | C | 1807 | G/N |  | --- |  | 4/81 | Admin | 4/16/81 |  |  |  | 0
| Alterations (940830) |  |  | W | 110 | G/N
|  |  |  | C | 1009 | G/N
1203
B. | CAC Def. (Cal/OSHA) Non-State | DELETED |  |  | --- |  |  | --- |  |  | --- |  | 9/83 | Deleted | 12/27/77 | 10/77 | 1978-81 CIP | 1256
| (948815) | [12 empty] | by campus |  | 1/80 | 1980-83 CIP | 1256
[16 empty] | 10/80 | 1981-84 CIP | 1256
[16 empty] | 10/81 | 1982-85 CIP | 1256
[16 empty] | 10/82 | 1983-86 CIP | 1256
C. | Royce Hall Auditorium Code | 500 | F | P | 425 | N | C | 2 | G |  | --- |  | 11/82 | Regents | 12/7/82 | 1/80 | 1979-82 & | 27300
| Corrections and Renovation | 500 | G | W | 498 | G | C | 1200 | U | [7 empty] | 1980-83 CIP
| (940910) | 4830 | LB | C | 108 | N | C | 1800 | LR | [6 empty] | 10/81 | 1981-84 CIP | 10000
|  | 1800 | LR | CE | 1000 | U | C | 500 | F | [6 empty] | 3/82 | 1981-84 & | 12000
|  | 3095 | N |  | 2031 |  | C | 4830 | LB | [7 empty] | 1982-85 CIP
|  | 2200 | U |  |  |  | C | 2562 | N
|  | 12925 | [5 empty] | 10894
D. | Medical Receiving Expansion | DELETED |  |  | --- |  |  | --- |  |  | --- |  | 10/82 | Deleted | --- | 10/80 | 1981-84 CIP | 269
| (944780) | [12 empty] | by campus |  | 10/81 | 1982-85 CIP | 292
E. | Hospital & Clinics | 502 | HR |  | --- |  | PWC | 502 | HR |  | --- |  | 10/81 | Regents' | N/A
| Reserve-Funded Improvements | [12 empty] | Budget
Under $150,000, 1982-83
F. | Hospital & Clinics | 537 | HR |  | --- |  | E | 537 | HR |  | --- |  | 10/81 | Regents' | N/A
| Reserve-Funded New | [12 empty] | Budget
Equipment, 1982-83
G. | Site Development, Westwood | 1853 | N | PW | 80 | N | C | 1773 | N |  | --- |  | 10/82 | Admin | 3/22/83 | 10/80 | 1981-84 CIP | 1906
| Central Plaza, Phase II (946050) | [14 empty] | 10/81 | 1982-85 CIP | 2377
H. | Sunset Canyon Recreation Food | DELETED |  |  | --- |  |  | --- |  |  | --- |  | 10/82 | Deleted | --- | 10/81 | 1982-85 CIP | 200
Facility (940490)
I. | Renovation of Baseball Facility | 980 | X |  | --- |  | P | 90 | X | C | 855 | X | 9/83 | Admin | N/A | 10/80 | 1981-84 CIP | 1054
| (Sawtelle Field), Phase 2 | [5 empty] | W | 35 | X | [6 empty] | 10/81 | 1982-85 CIP | 1300
| (940520) | [6 empty] | 125 | [7 empty] | 10/82 | 1983-86 CIP | 1029
J. | HSC Correct Safety Deficiencies | DELETED |  |  | --- |  |  | --- |  |  | --- |  | 6/82 | Deleted -- | --- | 10/81 | 1982-85 CIP | 658
| Phase IIIA - Jules Stein Eye | [12 empty] | Replaced by "AA"
| Institute (944492) | [12 empty] | in 1982-83
K. | Married Student Housing - | DELETED |  |  | --- |  |  | --- |  |  | --- |  | 9/83 | Deleted | --- | 10/81 | 1982-85 CIP | 1000
| Safety Deficiencies Corrections | [12 empty] | by campus
(946280)
L. | Perinatal Care Unit, Phase III | DELETED |  |  | --- |  |  | --- |  |  | --- |  | 10/82 | Deleted | --- | 10/81 | 1982-85 CIP | 1128
(944462)
M. | Outpatient Pharmacy Relocation | DELETED |  |  | --- |  |  | --- |  |  | --- |  | 5/82 | Deleted | 4/30/82 | 10/81 | 1982-85 CIP | 280
| (944680) | [12 empty] | by Amdmt Action;
funding resched.
in 1981-82
N. | Emergency Medicine Center | 3134 | HR |  | --- |  | P | 17 | HR | PWC | 3117 | HR | 10/82 | Regents' | N/A | 10/79 | 1980-83 CIP | 546
| (944470) | [12 empty] | Budget |  | 9/80 | 1980-83 CIP | 625
[16 empty] | 10/80 | 1981-84 CIP | 685
[16 empty] | 10/81 | 1982-85 CIP | 785
O. | Remodel Radiology Core Area | DELETED |  |  | --- |  |  | --- |  |  | --- |  | 10/82 | Deleted | --- | 10/78 | 1979-82 CIP | 500
| (944530) | [14 empty] | 10/79 | 1980-83 CIP | 500
[16 empty] | 10/80 | 1981-84 CIP | 500
[16 empty] | 10/81 | 1982-85 CIP | 500
P. | Residence Halls Energy | DELETED |  |  | --- |  |  | --- |  |  | --- |  | 9/83 | Deleted | --- | 10/81 | 1982-85 CIP | 225
| Conservation (946300) | [12 empty] | by campus
Q. | Marion Davies First Floor | DELETED |  |  | --- |  |  | --- |  |  | --- |  | 9/83 | Deleted | --- | 10/81 | 1982-85 CIP | 170
| Alterations, Hospital and Clinics | [12 empty] | by campus |  | 10/82 | 1982-85 CIP | 600
Pediatrics, Phase 1 (944540)
R. | University Guesthouse Expansion | 3200 | LB | P | 71 | LB | PWC | 2956 | LB | E | 173 | LB | 5/83 | Admin | 5/3/83 | 10/81 | 1981-84 CIP | 1400
| (946310) | [14 empty] | 1/82 | 1981-84 CIP | 2387
[16 empty] | 9/82 | 1982-85 CIP | 2999
S. | Clinical Faculty Office (944770) | 19567 | LB |  | --- |  |  | --- |  | P | 577 | LB | 3/86 | Regents | N/A | 10/81 | 1982-85 CIP | 26000
| (Developer financed component | [8 empty] | W | 710 | LB |  |  |  | 10/82 | 1983-86 CIP | 28000
| of: Lot 1 Mixed-Use Medical | [8 empty] | C | 18280 | LB |  |  |  | 10/83 | 1984-87 CIP | 40000
| Facilities Complex) | [9 empty] | 19567
T. | Four-East Medical Intensive | DELETED |  |  | --- |  |  | --- |  |  | --- |  | 9/83 | Deleted | --- | 10/81 | 1982-85 CIP | 500
| Care Unit | [12 empty] | by campus
U. | Outpatient Surgical Center | DELETED |  |  | --- |  |  | --- |  |  | --- |  | 9/83 | Deleted | --- | 10/81 | 1982-85 CIP | 600
| (944650) | [12 empty] | by campus |  | 10/82 | 1983-86 CIP | 1500
V. | Remodel Fourth and Fifth Floor | DELETED |  |  | --- |  |  | --- |  |  | --- |  | 10/82 | Deleted | ---
| OPD Wings (944850) | [12 empty] | Replaced by two
projects: see
Project II for
4th Floor project;
5th Floor project
is in 1983-86 CIP.
W. | Student Health Service Released | DELETED |  |  | --- |  |  | --- |  |  | --- |  | 10/82 | Deleted | --- | 10/81 | 1982-85 CIP | 5000
| Space for Hospital (944970) | [12 empty] | by campus
X. | Conversion of Hospital Laundry | DELETED |  |  | --- |  |  | --- |  |  | --- |  | 10/82 | Deleted | --- | 10/78 | 1979-82 CIP | 400
| Boilers (944380) | [12 empty] | by campus |  | 10/79 | 1980-83 CIP | 293
[16 empty] | 10/80 | 1981-84 CIP | 293
[16 empty] | 10/81 | 1982-85 CIP | 293
Y. | Hospital Elevator Addition | DELETED |  |  | --- |  |  | --- |  |  | --- |  | 9/83 | Deleted | --- | 10/81 | 1982-85 CIP | 800
| (944930) | [12 empty] | by campus
Z. | HSC - A&B Floor Alterations for | DELETED |  |  | --- |  |  | --- |  |  | --- |  | 10/82 | Deleted | --- | 10/81 | 1982-85 CIP | 4000
| Radiology and Radiation | [12 empty] | by campus
Oncology (944720)
AA. | Health Sciences Center - Correct | 300 | HR | PW | 124 | U | C | 300 | HR |  | --- |  | 6/82 | Admin | 7/6/82 | 10/81 | 1982-85 CIP | 658
| Safety Deficiencies Phase IIIA | 231 | U |  |  |  | C | 107 | U
| (944492) | 531 | [5 empty] | 407
BB. | Northeast Campus Student | 3100 | LB | P | 234 | N/X | WCE | 3100 | LB |  | --- |  | 7/82 | Admin | 7/26/82 | 10/80 | 1981-84 CIP | 2600
| Facility (940630) | 250 | N/X |  |  |  | WCE | 16 | N/X
|  | 3350 | [5 empty] | 3116
CC. | Fast Neutron Therapy Research | 6375 | F | PWCE | 5965 | F | C | 410 | F |  | --- |  | 7/82 | Regents | 9/2/82 | 9/79 | 1979-82 CIP | 5965
| Facility, Veterans Administration | 1400 | G |  |  |  | C | 1400 | G | [6 empty] | 10/81 | 1982-85 CIP | 7615
| Wadsworth Medical Center | 545 | N |  |  |  | C | 545 | N
| (944910) | 8320 | [5 empty] | 2355
DD. | Purchase of Property for | 1630 | X |  | --- |  | A | 1630 | X |  | --- |  | 7/82 | Regents | N/A
Bookbindery and Storage Facility
EE. | Mark Taper Center for Health | 1250 | G | PWC | 786 | G | C | 464 | G |  | --- |  | 10/82 | Admin | 8/3/81
Enhancement (944960)
FF. | University Extension Conference | 220 | N |  | --- |  | PWC | 220 | N |  | --- |  | 10/82 | Regents' | N/A
| Room Alterations (940980) | [12 empty] | Budget
GG. | Lake Arrowhead Conference | 2000 | G/N |  | --- |  | PWC | 2000 | G/N |  |  |  | 10/81 | Regents' | N/A
| Center Alterations (946350) | [12 empty] | Budget
HH. | Lindblade Warehouse Alterations | 225 | N |  | --- |  | PWC | 225 | N |  | --- |  | 10/82 | Regents' | N/A
| for Book Bindery (940990) | [12 empty] | Budget
II. | Fourth Floor Medical Clinic | DELETED |  |  | --- |  |  | --- |  |  | --- |  | 9/83 | Deleted | --- | 10/82 | 1982-85 CIP | 1439
| Alterations, Hospital and Clinics | [12 empty] | by campus
(944850)
JJ. | Medical Center Administration | 18250 | HR | P | 25 | HR | P | 185 | HR | WCE | 18040 | HR | 10/82 | Regents' | N/A | 10/82 | 1982-85 CIP | 18250
| Office Building (Formerly: | [12 empty] | Budget
Administration Office Building)
(944760)
KK. | Convert Multiple Patient Rooms to | DELETED |  |  | --- |  |  | --- |  |  | --- |  | 9/83 | Deleted | --- | 10/82 | 1982-85 CIP | 250
| Single Rooms, Eighth Floor | [12 empty] | by campus
(945100)
LL. | Tennis Center Complex (940840) | 1374 | G | PW | 410 | G | C | 964 | G |  | --- |  | 10/82 | Regents' | N/A | 1/80 | 1979-82 & | 1000
|  | 6315 | LB |  |  |  | C | 6315 | LB |  |  |  |  | Budget Addendum |  |  | 1980-83 CIP
|  | 126 | R |  |  |  | C | 126 | R | [7 empty] | (part of Recreation
|  | 7815 | [5 empty] | 7405 | [8 empty] | & Sports Center
Project)
[16 empty] | 7/80 | 1980-83 CIP | 2500
(part of Recreation
& Sports Center
Project)
[16 empty] | 7/81 | 1980-83 CIP | 4100
(part of Recreation
& Sports Center
Project)
MM. | Resonance Imaging Clinical | 175 | G | P | 25 | G | W | 50 | X | C | 150 | G | 8/83 | Admin | 8/11/83 | 2/83 | 1982-85 CIP | 350
| Research Facility (945140) | 271 | X | [6 empty] | C | 221 | X
|  | 446 | [8 empty] | 371
| Federal (F) | 6875 | F |  | 5965 | F |  | 910 | F |  | ---
| Gifts (G) | 4699 | G |  | 1719 | G |  | 2830 | G |  | 150 | G
| Hospital Reserves (HR) | 22723 | HR |  | 25 | HR |  | 1541 | HR |  | 21157 | HR
| Bank Loans or Bonds (LB) | 37012 | LB |  | 71 | LB |  | 17201 | LB |  | 19740 | LB
| Regents' Loan (LR) | 1800 | LR |  | --- |  |  | 1800 | LR |  | ---
Reserves other than University
| Registration Fee (N) | 5938 | N |  | 613 | N |  | 5325 | N |  | ---
| Registration Fees (R) | 126 | R |  | --- |  |  | 126 | R
| Regents' Appropriations (U) | 2431 | U |  | 1124 | U |  | 1307 | U |  | ---
| Other (X) | 2881 | X |  | --- |  |  | 1805 | X |  | 1076 | X
| Gifts/Reserves (G/N) | 5010 | G/N |  | 1203 | G/N |  | 1807 | G/N |  | 2000 | G/N
| Reserves/Other (N/X) | 250 | N/X |  | 234 | N/X |  | 16 | N/X |  | ---
| TOTAL | 89745 |  |  | 10954 |  |  | 34668 |  |  | 44123

## Riverside
RIVERSIDE CAMPUS
1982-83 NON-STATE CAPITAL BUDGET
($000)
[6 empty] | C U R R E N T S T A T U S | [7 empty] | PRIOR ACTION/COMMENTS
|  | Project | [6 empty] | Beyond |  |  |  | Approval
| Project | Cost |  | Prefunded |  | 1982-83 |  |  | 1982-83 |  | Action |  | Letter | Date | Action | Cost
A. | Centrifugal Chillers (950340) | 715 | U | --- | PW | 55 | U | C | 660 | U | 10/82 | Admin | 12/7/82
| Regents' Appropriations (U) | 715 | U | --- |  | 55 | U |  | 660 | U
| TOTAL | 715 |  | --- |  | 55 |  |  | 660

## San Diego
SAN DIEGO CAMPUS
1982-83 NON-STATE CAPITAL BUDGET
($000)
[8 empty] | C U R R E N T S T A T U S | [7 empty] | PRIOR ACTION/COMMENTS
|  | Project | [8 empty] | Beyond |  |  |  | Approval
| Project | Cost |  |  | Prefunded |  |  | 1982-83 |  |  | 1982-83 |  | Action |  | Letter | Date | Action | Cost
A. | SI0-Physical Oceanography and | 4750 | LB | P | 90 | LB | C | 4056 | LB |  | --- |  | 5/82 | Regents | 2/15/84 | 9/81 | 1981-84 CIP | 4752
| Space Science Building (960710) |  |  | W | 154 | LB | [9 empty] | 10/81 | 1982-85 CIP | 4750
|  |  |  | C | 450 | LB
694
B. | UCMC, San Diego - University | 2000 | HR |  | --- |  | P | 6 | HR | P | 54 | HR | 11/84 | Regents' | N/A | 10/81 | 1982-85 CIP | 2000
| Hospital Equipment Tie-Down | [5 empty] | W | 10 | HR | W | 90 | HR |  | Budget
| (964780) | [5 empty] | C | 184 | HR | C | 1656 | HR
[8 empty] | 200 |  |  | 1800
C. | UCMC, San Diego - Mission | DELETED |  |  | --- |  |  | --- |  |  | --- |  | 11/82 | Deleted | --- | 10/80 | 1981-84 CIP | 320
| Valley Access Road (966037) | [12 empty] | by campus |  | 10/81 | 1982-85 CIP | 350
D. | University Theatre Addition | 620 | G |  | --- |  | P | 9 | G |  | --- |  | 11/81 | Regents' | N/A
| (960770) | [5 empty] | W | 33 | G |  |  |  |  | Budget
[7 empty] | C | 578 | G
620
E. | Hospital and Clinics Reserve | 533 | HR |  | --- |  | PWC | 533 | HR |  | --- |  | 11/82 | Regents' | N/A | 10/81 | 1982-85 CIP | 389
| Funded Improvements Under | [12 empty] | Budget
$150,000, 1982-83
F. | Hospital and Clinics Reserve | 400 | HR |  | --- |  | E | 400 | HR |  | --- |  | 11/82 | Regents' | N/A | 10/81 | 1982-85 CIP | 300
| Funded New Equipment, 1982-83 | [12 empty] | Budget
G. | Administrative/Warren College | DELETED |  |  | --- |  |  | --- |  |  | --- |  | 10/82 | Deleted | --- | 10/81 | 1982-85 CIP | 126
| Parking (966539) | [12 empty] | by campus
H. | Student Center Multi-Facility | DELETED |  |  | --- |  |  | --- |  |  | --- |  | 10/82 | Deleted | --- | 10/81 | 1982-85 CIP | 3750
by campus
I. | Recombinant DNA Facility | DELETED |  |  | --- |  |  | --- |  |  | --- |  | 10/82 | Deleted | --- | 10/81 | 1982-85 CIP | 4000
by campus
J. | Athymic Mice Research Facility | DELETED |  |  | --- |  |  | --- |  |  | --- |  | Deleted |  | --- | 10/81 | 1982-85 CIP | 1459
Addition
K. | Central Services (Corporation | DELETED |  |  | --- |  |  | --- |  |  | --- |  | Deleted |  | --- | 10/81 | 1982-85 CIP | 63
Yard) Facility Parking (966539)
L. | UCMC, San Diego - South Access | DELETED |  |  | --- |  |  | --- |  |  | --- |  | Deleted |  | --- | 10/81 | 1982-85 CIP | 1024
Road (Including Land ) (966042)
M. | General Campus Classroom | 1400 | X |  | --- |  | P | 40 | X |  | --- |  | 5/82 | Admin | 6/1/82
| Building (961120) | [5 empty] | W | 110 | X
[7 empty] | C | 1250 | X
1400
N. | NO PROJECT
O. | UCMC San Diego Parking Facility | 9000 | LB | P | 150 | LB | PWC | 8850 | LB |  | --- |  | 7/82 | Admin | 7/30/82 | 10/80 | 1981-84 CIP | 5400
(966540)
P. | Internal Medicine Group Expansion | 415 | X |  | --- |  | P | 10 | X |  | --- |  | 11/82 | Regents' | N/A
| (964810) | [5 empty] | W | 30 | X |  |  |  |  | Budget
[7 empty] | C | 375 | X
415
Q. | UCMC, San Diego - Replace | 1220 | HR |  | --- |  | P | 42 | HR | C | 1125 | HR | 11/82 | Regents' | N/A
| Emergency Power System | [5 empty] | W | 53 | HR |  |  |  |  | Budget
| (964800) | [6 empty] | 95
R. | UCMC, San Diego - Construction | 250 | HR |  | --- |  | P | 25 | HR | C | 200 | HR | 3/84 | Admin | 3/20/84 | 10/82 | 1982-85 CIP | 500
| for Linear Accelerator (1983-84 | [5 empty] | W | 25 | HR | [6 empty] | 10/82 | 1983-86 CIP | 250
| Title: Install Linear Accelerator) | [6 empty] | 50
(964820)
S. | Career Planning and Placement | 1162 | R |  | --- |  | P | 35 | R | C | 1020 | R | 3/83 | Regents | 7/6/83
| Center (961140) | [5 empty] | W | 40 | R | E | 67 | R
[8 empty] | 75 |  |  | 1087
T. | College Apartments (966410) | 13000 | LB |  | --- |  | PW | 150 | LB | C | 12150 | LB | 9/84 | Admin | 12/27/84 | 10/82 | 1983-86 CIP | 13542
|  | 1500 | N | [6 empty] | C | 1500 | N |  |  |  | 3/83 | 1983-86 CIP | 13000
|  | 14500 | [7 empty] | E | 700 | LB |  |  |  | 9/83 | 1983-86 CIP | 14200
14350
U. | Instruction and Research | 191 | X |  | --- |  | PW | 23 | X |  | --- |  | 6/83 | Admin | 7/5/83
| Expansion Space Facility (961160) | [5 empty] | C | 168 | X
191
V. | UCSD Extension/General Campus | 146 | N |  | --- |  | P | 12 | N | W | 20 | N | 5/84 | Admin | 5/14/84 | 2/84 | 1982-85 & 1983-86 CIP | 485
| Modular Building (961240) | 451 | X | [6 empty] | C | 114 | N
|  | 597 | [7 empty] | C | 451 | X
585
| Gifts (G) | 620 | G |  | --- |  |  | 620 | G |  | ---
| Hospital Reserves (HR) | 4403 | HR |  | --- |  |  | 1278 | HR |  | 3125 | HR
| Bank Loans or Bonds (LB) | 26750 | LB |  | 844 | LB |  | 12906 | LB |  | 13000
Reserves other than University
| Registration Fee (N) | 1646 | N |  | --- |  |  | 12 | N |  | 1634 | N
| Registration Fees (R) | 1162 | R |  | --- |  |  | 75 | R |  | 1087 | R
| Other (X) | 2457 | X |  | --- |  |  | 2006 | X |  | 451 | X
| TOTAL | 37038 |  |  | 844 |  |  | 16897 |  |  | 19297

## San Francisco
SAN FRANCISCO CAMPUS
1982-83 NON-STATE CAPITAL BUDGET
($000)
[9 empty] | C U R R E N T S T A T U S | [7 empty] | PRIOR ACTION/COMMENTS
|  |  | Project | [8 empty] | Beyond |  |  |  | Approval
| Project |  | Cost |  |  | Prefunded |  |  | 1982-83 |  |  | 1982-83 |  | Action |  | Letter | Date | Action | Cost
A. | CAC Deficiencies High Rise Fire |  | 290 | N |  | --- |  | PW | 40 | N | C | 250 | N | 11/82 | Admin | 11/5/82 | 10/80 | 1981-84 CIP | 517
| Protection (Millberry |  | 362 | U |  |  |  | PW | 27 | U | C | 335 | U |  |  |  | 10/81 | 1982-85 CIP | 605
| Union/Garage) (920120) |  | 652 | [5 empty] | 67 |  |  | 585
B. | Hospital and Clinics Reserve |  | 1000 | HR |  | --- |  | PWC | 1000 | HR |  | --- |  | 11/82 | Regents' | N/A | 10/81 | 1982-85 CIP | 800
| Funded Improvements Under | [13 empty] | Budget
$150,000, 1982-83
C. | Hospital and Clinics Reserve |  | 700 | HR |  | --- |  | E | 700 | HR |  | --- |  | 11/82 | Regents' | N/A
| Funded New Equipment, 1982-83 | [13 empty] | Budget
D. | Moffitt Hospital Modernization, | ( | 4120 | ) | ( PWC | 4120 | ) | A/C | 7000 | HR |  | --- |  | 7/82 | Regents | --- | Multiple prior actions --
| Phases I and II and Interior | ( | 28424 | H) | ( PWC | 28424 | H) | [9 empty] | See project files.
| Comple- tion of 15th Floor for | ( | 632 | Ed) | ( PWC | 632 | Ed)
| Obstetric Unit and Nursery |  | 3683 | X | PWC | 4208 | HR
|  |  | 11208 | HR | PWC | 13270 | G
|  |  | 13270 | G | PWC | 11813 | N
|  |  | 11813 | N | PWC | 3683 | X
|  |  | 73150 |  |  | 66150
E. | HSIR - East, Fifth Floor Alterations |  | 488 | N | P | 30 | N | W | 24 | N |  | --- |  | 10/82 | Admin | 10/8/82
| for Immunogenetics and | [6 empty] | C | 434 | N
| Transplantation Laboratory | [7 empty] | 458
(924810)
F. | SFGH Building 1 - First Floor |  | DEFERRED |  |  | --- |  |  | --- |  |  | --- |  | Deferred |  | --- | 10/81 | 1981-84 CIP | 525
| Alterations for Applied | [12 empty] | by campus
Neurobiology Laboratory (924770)
G. | UC Hospital - Molecular Genetics |  | 2980 | G |  | --- |  | P | 120 | G |  | --- |  | 10/82 | Regents | 7/26/83
| and Immunology Research | [6 empty] | W | 220 | G
| Laboratory (924830) | [6 empty] | C | 2640 | G
2980
H. | Clinical Sciences Building - |  | 237 | X |  | --- |  | P | 17 | X |  | --- |  | 1/83 | Admin | 1/31/83
| Alterations for Mass Spectrometry |  | 100 | F |  |  |  | W | 21 | X
| Research Facility (924850) |  | 337 |  |  |  |  | C | 199 | X
[8 empty] | C | 100 | F
337
I. | Westside Parking Lot (920170) |  | 764 | N |  | --- |  | P | 50 | N |  | --- |  | 5/83 | Admin | 5/26/83
|  |  | 800 | LB |  |  |  | W | 79 | N
|  |  | 1564 |  |  |  |  | C | 635 | N
[8 empty] | C | 800 | LB
1564
J. | School of Medicine, Vision |  | 708 | F |  | --- |  |  | --- |  | P | 374 | X | 7/84 | Regents | 7/24/84 | 3/83 | 1983-86 CIP | 7780
| Research Laboratory Building |  | 9178 | G | [6 empty] | W | 601 | G
| (924840) |  | 374 | X | [6 empty] | C | 708 | F
|  |  | 10260 | [7 empty] | C | 8577 | G
10260
(LETTERS K - O NOT USED)
P. | Laboratory for Cell Analysis, CED, |  | 350 | N |  | --- |  | P | 25 | U | W | 40 | N | 7/82 | Admin | 7/8/82
| School of Medicine (924820) |  | 375 | U |  |  |  | W | 40 | U | C | 210 | N
|  |  | 725 |  |  |  |  | C | 210 | U |  | 250
[8 empty] | E | 100 | U
[8 empty] | E | 100 | N
475
| Federal (F) |  | 808 | F |  | --- |  |  | 100 | F |  | 708 | F
| Gifts (G) |  | 25428 | G |  | 13270 | G |  | 2980 | G |  | 9178 | G
| Hospital Reserves (HR) |  | 12908 | HR |  | 4208 | HR |  | 8700 | HR
| Bank Loans or Bonds (LB) |  | 800 | LB |  | --- |  |  | 800 | LB |  | ---
Reserves other than University
| Registration Fee (N) |  | 13705 | N |  | 11843 | N |  | 1362 | N |  | 500 | N
| Regents' Appropriations (U) |  | 737 | U |  | --- |  |  | 402 | U |  | 335 | U
| Other (X) |  | 4294 | X |  | 3683 | X |  | 237 | X |  | 374 | X
| TOTAL |  | 58680 |  |  | 33004 |  |  | 14581 |  |  | 11095
| State Funds | ( | 4120 | ) | ( | 4120 | ) | ( | --- | ) | ( | --- | )
| Health Sciences Bonds (H) | ( | 28424 | H ) | ( | 28424 | H ) | ( | --- | ) | ( | --- | )
| Educational Fund (Ed) | ( | 632 | Ed ) | ( | 632 | Ed ) | ( | --- | ) | ( | --- | )
| TOTAL | ( | 33176 | ) | ( | 33176 | ) | ( | --- | ) | ( | --- | )
Note on J83: Formula failed to convert
Note on J84: Formula failed to convert
Note on J85: Formula failed to convert
Note on J86: Formula failed to convert
Note on J90: Formula failed to convert

## Santa Barbara
SANTA BARBARA CAMPUS
1982-83 NON-STATE CAPITAL BUDGET
($000)
[8 empty] | C U R R E N T S T A T U S | [5 empty] | PRIOR ACTION/COMMENTS
|  | Project | [7 empty] | Beyond |  |  | Approval
| Project | Cost |  |  | Prefunded |  |  | 1982-83 |  | 1982-83 | Action |  | Letter | Date | Action | Cost
A. | Student Services Building (980380) | 1575 | R | P | 47 | R | C | 1370 | R | --- | 1/83 | Admin | 1/31/83 | 10/80 | 1981-84 CIP | 2000
|  | 50 | N | W | 58 | R | C | 50 | N |  |  |  |  | 10/81 | 1982-85 CIP | 1300
|  | 1625 |  |  | 105 |  | E | 100 | R |  |  |  |  | 2/82 | 1982-85 CIP | 1300
1520
B. | CAC Deficiencies Residence Halls | DEFERRED |  |  | --- |  |  | --- |  | --- | 10/82 | Deferred | --- | 10/80 | 1981-84 CIP | 308
| and Dining Commons | [10 empty] | by campus |  | 10/81 | 1982-85 CIP | 379
(Handicapped) Step 2 (986256)
C. | CAC Deficiencies Residence Halls | DEFERRED |  |  | --- |  |  | --- |  | --- | 10/82 | Deferred | --- | 10/80 | 1981-84 CIP | 196
| and Dining Commons | [10 empty] | by campus |  | 10/81 | 1982-85 CIP | 432
(Handicapped) Step 3 (986257)
D. | Swimming Pool and Support Facilities | 3000 | G |  | --- |  | PWCE | 3000 | G | --- | 11/82 | Regents' | N/A
| (980440) | [10 empty] | Budget
E. | Art Museum (980420) | 5300 | G |  | --- |  | P | 135 | G | --- | 10/82 | Regents | 4/4/83
[7 empty] | W | 165 | G
[7 empty] | C | 4700 | G
[7 empty] | E | 300 | G
5300
F. | Interim Facility - Ocean Engineering | 294 | X |  | --- |  | P | 13 | X | --- | 3/83 | Admin | 3/25/83 | 10/82 | 1982-85 CIP | 330
| Laboratory (980500) | [5 empty] | W | 15 | X
[7 empty] | C | 266 | X
294
G. | Alterations to Stadium for Studio | 322 | X |  | --- |  | P | 12 | X | --- | 7/83 | Admin | 7/5/83
| Art (980510) | [5 empty] | W | 15 | X
[7 empty] | C | 295 | X
322
| Gifts (G) | 8300 | G |  | --- |  |  | 8300 | G | ---
Reserves other than University
| Registration Fee (N) | 50 | N |  | --- |  |  | 50 | N | ---
| Registration Fees (R) | 1575 | R |  | 105 | R |  | 1470 | R | ---
| Other (X) | 616 | X |  | --- |  |  | 616 | X | ---
| TOTAL | 10541 |  |  | 105 |  |  | 10436 |  | ---

## Santa Cruz
SANTA CRUZ CAMPUS
1982-83 NON-STATE CAPITAL BUDGET
($000)
[6 empty] | C U R R E N T S T A T U S | [7 empty] | PRIOR ACTION/COMMENTS
|  | Project | [6 empty] | Beyond |  |  |  | Approval
| Project | Cost |  | Prefunded |  | 1982-83 |  |  | 1982-83 |  | Action |  | Letter | Date | Action | Cost
A. | Science Library Addition (970390) | 3800 | G | --- | PWCE | 3800 | G |  | --- |  | 11/82 | Regents' | N/A
Budget
B. | Swimming Pool (970410) | 499 | G | --- | P | 10 | R |  | --- |  | 10/82 | Admin | 6/9/83
|  | 321 | R |  | P | 15 | G
|  | 820 |  |  | W | 15 | R
[5 empty] | W | 20 | G
[5 empty] | C | 296 | R
[5 empty] | C | 434 | G
[5 empty] | E | 30 | G
820
C. | Long Marine Laboratory Education | 6135 | G | --- | P | 14 | G | P | 200 | G | 11/84 | Regents' | N/A | 10/82 | 1982-85 CIP | 5725
| and Marine Bio-Research Facility |  |  |  | W | 16 | G | W | 263 | G |  | Budget
| (970440) |  |  |  | C | 339 | G | C | 4899 | G
[5 empty] | E | 17 | G | E | 387 | G
[6 empty] | 386 |  |  | 5749
D. | Visual Arts Facility, Phase 1 (970430) | 620 | G | --- | P | 50 | X | C | 620 | G | 3/84 | Admin | 3/2/84 | 10/82 | 1982-85 CIP | 1,570
|  | 1166 | U |  | W | 75 | U | C | 825 | U
|  | 220 | X |  |  | 125 |  | C | 266 | U
|  | 2006 | [5 empty] | C | 170 | X
1881
| Gifts (G) | 11054 | G | --- |  | 4299 | G |  | 6369 | G
| Registration Fees (R) | 321 | R | --- |  | 321 | R |  | ---
| Regents' Appropriations (U) | 1166 | U | --- |  | 75 | U |  | 1091 | U
| Other (X) | 220 | X | --- |  | 50 | X |  | 170 | X
| TOTAL | 12761 |  | --- |  | 4745 |  |  | 7630

## Summary
1983-84 NON-STATE FUNDED PROJECTS
($ in thousands)
| UCB | UCD | UCI | UCLA | UCR | UCSD | UCSF | UCSB | UCSC | OTHER | TOTAL
Federal (F) | - - - | - - - | - - - | - - - | - - - | - - - | - - - | - - - | - - - | - - - | 0
Gifts (G) | 0 | 0 | 4950 | 225 | - - - | 0 | 0 | - - - | 0 | - - - | 5175
Gifts/Other (G/X) | - - - | - - - | - - - | - - - | - - - | - - - | - - - | - - - | - - - | - - - | - - -
Hospital Reserves (HR) | - - - | 0 | 5000 | 0 | - - - | 0 | 0 | - - - | - - - | - - - | 5000
Bank Loans or Bonds (LB) | 874 | 0 | 0 | 0 | - - - | 0 | - - - | 1470 | - - - | - - - | 2344
Reserves Other Than University
Registration Fees (N) | 0 | 0 | 10 | - - - | - - - | 168 | 0 | - - - | 4745 | - - - | 4923
Funds From Sources Yet To Be
Determined (Q) | - - - | - - - | - - - | - - - | - - - | - - - | - - - | - - - | - - - | - - - | - - -
Registration Fees (R) | - - - | 0 | - - - | - - - | - - - | 0 | - - - | - - - | 0 | - - - | 0
Regents' Appropriations (U) | 0 | 0 | - - - | - - - | 55 | 191 | 0 | - - - | 0 | - - - | 246
Regents' Loans (LR) | - - - | - - - | - - - | - - - | - - - | 0 | - - - | - - - | - - - | - - - | 0
Other (X) | 0 | - - - | - - - | 0 | - - - | 0 | 0 | - - - | 0 | - - - | 0
TOTAL | 874 | 0 | 9960 | 225 | 55 | 359 | 0 | 1470 | 4745 | 0 | 17688