## Berkeley
BERKELEY CAMPUS
1987-88 NON-STATE CAPITAL BUDGET
($000)
C U R R E N T S T A T U S
|  |  | Project | [8 empty] | Beyond |  |  |  | Approval
| Project |  | Cost |  |  | Prefunded |  |  | 1987-88 |  |  | 1987-88 |  | Action |  | Letter | Date | Action | Cost
A. | Computer Science Building |  | 32500 | G |  | - - - |  | P | 1200 | G | P | 200 | G | 2/91 | Admin | 2/13/91 | 7/87 | 1987-90 CIP | 30000
| (912542) | [6 empty] | W | 1800 | G | W | 200 | G
[8 empty] | C | 25500 | G | C | 2500 | G
[8 empty] | E | 1100 | G |  | 2900
29600
B. | Genetics and Plant Biology Bldg. |  | 21004 | G | (P | 754 | ) |  | - - - |  | E | 1380 | G | 11/87 | Regents' | N/A | 11/81 | 1982-85 CIP | 31788
| (912272) |  | 206 | N | P | 766 | G |  |  |  | (E | 1380 | ) |  | Budget |  | 11/82 | 1983-86 CIP | 42630
|  | ( | 20715 | ) | (W | 847 | ) |  |  |  |  | 2760 |  |  |  |  | 11/84 | 1985-88 CIP | 41326
|  |  | 41925 |  | W | 872 | G | [9 empty] | 10/85 | 1986-89 CIP | 41851
[5 empty] | (C | 17734 | ) | [9 empty] | 11/86 | 1987-90 CIP | 41851
[5 empty] | C | 17986 | G
[5 empty] | C | 206 | N
39165
C. | Life Sciences Renovation for |  | 24049 | G | P | 1626 | G |  | - - - |  | (W | 2603 | ) | 1/94 | Regents, | 1994-03-30 | 10/85 | 1986-89 CIP | 62357
| Ecology and Evolutionary Biology |  | 19083 | X | P | 85 | X |  |  |  | W | 94 | G |  | Admin |  | 11/86 | 1987-90 CIP | 62357
| (912274) | ( | 48199 | ) | (P | 938 | ) |  |  |  | W | 69 | X |  |  |  | 11/87 | 1988-91 CIP | 67746
|  |  | 91331 |  |  | 2649 |  |  |  |  | C | 750 | X |  |  |  | 11/88 | 1989-92 CIP | 69547
[11 empty] | (C | 41066 | ) |  |  |  | 11/89 | 1990-93 CIP | 69936
[11 empty] | C | 20533 | G |  |  |  | 10/90 | 1991-94 CIP | 70035
[11 empty] | (E | 3592 | ) |  |  |  | 11/91 | 1992-95 CIP | 70080
[11 empty] | E | 1796 | G |  |  |  | 10/92 | 1993-96 CIP | 73152
[11 empty] | C | 18179 | X
88682
D. | Etcheverry Hall Reactor |  | 625 | U |  | - - - |  | P | 250 | U | C | 1100 | X | 6/90 | Admin | 6/26/90 | 8/87 | 1987-90 CIP | 1750
| Decommissioning and Removal |  | 1725 | X |  |  |  | W | 250 | U
| (912536) |  | 2350 |  |  |  |  | C | 125 | U
[8 empty] | E | 625 | X
1250
E. | Foothill Student Housing, Phase I |  | 49022 | LB |  | - - - |  | A | 1905 | LB | C | 15817 | LB | 9/90 | Regents | 10/31/90 | 9/87 | 1987-90 CIP | 60296
| (912548) |  | 1358 | N |  |  |  | P | 1210 | LB | [6 empty] | 1/88 | 1987-90 CIP | 34563
|  |  | 50380 |  |  |  |  | P | 77 | N | [6 empty] | 3/89 | 1988-91 CIP | 40139
[8 empty] | W | 4040 | LB
[8 empty] | W | 98 | N
[8 empty] | C | 24430 | LB
[8 empty] | C | 1183 | N
[8 empty] | E | 1620 | LB
34563
F. | Shattuck and Channing Student |  | 11700 | LB |  | - - - |  | A | 930 | LB | A | 304 | LB | 6/93 | Regents | 6/14/93 | 9/87 | 1987-90 CIP | 8426
| Housing (912550) (Replaced by: | [6 empty] | P | 259 | LB | P | 521 | LB |  | (Replaced --see "F"
| 2100 Channing Student Housing | [6 empty] | W | 319 | LB | W | 151 | LB |  | in 1992-93)
| #912664) | [6 empty] | C | 6663 | LB | C | 2223 | LB
[8 empty] | E | 255 | LB | E | 75 | LB
[9 empty] | 8426 |  |  | 3274
G. | Northwest Site Development |  | 850 | X | P | 100 | X | W | 106 | X |  | - - - |  | 12/87 | Admin | 12/22/87
| (912546) | [6 empty] | C | 644 | X
750
H. | Campus Energy Management |  | 2388 | LB |  | - - - |  | P | 60 | LB | P | 140 | LB | 12/87 | Admin | 12/11/87
| Control System, Steps 2 & 3 | [6 empty] | W | 60 | LB | W | 140 | LB
| (912530) | [6 empty] | C | 431 | LB | C | 1557 | LB
[9 empty] | 551 |  |  | 1837
I. | Campus Energy Conservation |  | 1594 | LB |  | - - - |  | P | 29 | LB |  | - - - |  | 1/88 | Admin | 1/12/88
| Lighting Efficiency Improvements, | [6 empty] | W | 58 | LB
| Step 3 (912552) | [6 empty] | C | 1507 | LB
1594
J. | Residence Halls, Renovation |  | 17638 | LB |  | - - - |  | P | 785 | LB | C | 2000 | LB | 12/88 | Interim | 12/15/88 | 5/86 | 1985-88 CIP | 6796
| Program, Phase I, Unit III Complex |  | 5035 | N |  |  |  | W | 1211 | LB | C | 3075 | N |  |  |  | 3/88 | 1987-90 CIP | 17639
| (912528) |  | 41 | X |  |  |  | C | 13642 | LB |  | 5075
|  |  | 22714 |  |  |  |  | C | 41 | X
[8 empty] | E | 1960 | N
17639
K. | Dining Commons Renovation for |  | 5796 | LB |  | - - - |  | P | 273 | N |  | - - - |  | 5/88 | Regents | 6/21/88
| Student Services and Food |  | 700 | N |  |  |  | W | 330 | N
| Services (912553) |  | 6496 |  |  |  |  | C | 97 | N
[8 empty] | C | 5544 | LB
[8 empty] | E | 252 | LB
6496
L. | Earth Sciences Building Fourth |  | 775 | X |  | - - - |  | P | 25 | X |  | - - - |  | 5/88 | Admin | 5/20/88
| Floor Alterations for Analytical | [6 empty] | W | 50 | X
| Measurements Facility (912551) | [6 empty] | C | 695 | X
[8 empty] | E | 5 | X
775
M. | Lawrence Hall of Science Additions |  | 8000 | G |  | - - - |  |  | - - - |  | P | 515 | G | 3/94 | Regents | 1994-08-22 | 6/88 | 1987-90 CIP | 5000
| and Alterations, Step (912551) | [9 empty] | W | 1020 | G |  | (Replaced --see "B" in
| (Replaced by: Lawrence Hall of | [9 empty] | C | 6040 | G |  | 1993-94)
| Science #912551) | [9 empty] | E | 425 | G
8000
N. | Biological Sciences Relocations |  | 1900 | U |  | - - - |  | P | 110 | X | C | 950 | U | 1/89 | Regents | 2/24/89 | 9/88 | 1987-90 CIP | 2100
| (912540) |  | 1150 | X |  |  |  | W | 130 | X
|  |  | 3050 |  |  |  |  | C | 910 | X
[8 empty] | C | 950 | U
2100
| Gift Funds (G) |  | 85553 | G |  | 21250 | G |  | 29600 | G |  | 34703 | G
| Bank Loans or Bonds (LB) |  | 88138 | LB |  | - - - |  |  | 65210 | LB |  | 22928 | LB
Reserves other than University
| Registration Fees (N) |  | 7299 | N |  | 206 | N |  | 4018 | N |  | 3075 | N
| Regents' Appropriation (U) |  | 2525 | U |  | - - - |  |  | 1575 | U |  | 950 | U
| Other - Campus Funds (X) |  | 23624 | X |  | 185 | X |  | 3341 | X |  | 20098 | X
| TOTAL |  | 207139 |  |  | 21641 |  |  | 103744 |  |  | 81754
| STATE FUNDS | ( | 68914 | ) | ( | 20273 | ) | ( | - - - | ) | ( | 48641 | )

## Davis
DAVIS CAMPUS
1987-88 NON-STATE CAPITAL BUDGET
($000)
[9 empty] | C U R R E N T S T A T U S | [8 empty] | PRIOR ACTION/COMMENTS
|  |  | Project | [8 empty] | Beyond |  |  |  | Approval
| Project |  | Cost |  |  | Prefunded |  |  | 1987-88 |  |  | 1987-88 |  | Action |  | Letter | Date |  | Action | Cost
A. | Memorial Union Expansion and |  | 7600 | LB |  | --- |  | P | 440 | LB |  | --- |  | 1/91 | Regents | 4/16/91 | 7/87 |  | 1987-90 CIP | 8352
| Remodel (930840) |  | 4493 | N |  |  |  | W | 455 | LB | [6 empty] | 5/88 |  | 1987-90 CIP | 10234
|  |  | 197 | R |  |  |  | C | 6705 | LB | [6 empty] | 3/89 |  | 1988-91 CIP | 11020
|  |  | 12290 |  |  |  |  | C | 3137 | N
[8 empty] | C | 197 | R
[8 empty] | E | 1356 | N
12290
B. | Silo Student Center Expansion |  | 5300 | LB |  | --- |  | P | 207 | LB |  | --- |  | 1/91 | Regents | 4/16/91 | 7/87 |  | 1987-90 CIP | 4917
| and Remodel (930970) |  | 1003 | R |  |  |  | W | 219 | LB | [6 empty] | 3/89 |  | 1988-91 CIP | 7350
|  |  | 1002 | N |  |  |  | C | 4874 | LB
|  |  | 400 | X |  |  |  | C | 1003 | R
|  |  | 7705 |  |  |  |  | C | 752 | N
[8 empty] | C | 400 | X
[8 empty] | E | 250 | N
7705
C. | Public Service Building (930740) |  | DELETED |  |  | --- |  |  | --- |  |  | --- |  | 7/88 | Deleted
by campus
D. | UCDMC Parking Structure 1 |  | 7900 | LB |  | --- |  | P | 352 | LB |  | --- |  | 11/87 | Regents | 12/1/87
| (936552) | [6 empty] | W | 534 | LB
[8 empty] | C | 7014 | LB
7900
E. | Thoreau Hall Replacement (936300) |  | 8564 | LB |  | --- |  | P | 300 | LB |  | --- |  | 3/89 | Regents | 3/21/89 | 1/88 |  | 1987-90 CIP | 7539
[8 empty] | W | 250 | LB | [6 empty] | 9/88 |  | 1988-91 CIP | 7695
[8 empty] | C | 7614 | LB
[8 empty] | E | 400 | LB
8564
F. | Webster/Emerson Dining Common |  | 2581 | LB |  | --- |  | P | 120 | LB | C | 250 | N | 5/90 | Admin | 5/14/90 | 1/88 |  | 1987-90 CIP | 2266
| Remodel (936310) |  | 250 | N |  |  |  | W | 138 | LB | [6 empty] | 3/89 |  | 1988-91 CIP | 2581
|  |  | 2831 |  |  |  |  | C | 2323 | LB
2581
G. | University Extension Classroom |  | 304 | N |  | --- |  | P | 7 | N |  | --- |  | 3/88 | Admin | 3/15/89 | 1/88 |  | 1987-90 CIP | 280
| Building (931150) | [6 empty] | W | 8 | N
[8 empty] | C | 289 | N
304
H. | Art Studio Facility (931160) |  | 576 | X |  | --- |  | P | 17 | X |  | --- |  | 6/88 | Admin | 6/29/88 | 1/88 |  | 1987-90 CIP | 400
[8 empty] | W | 20 | X
[8 empty] | C | 539 | X
576
I. | UCDMC East Wing Third Floor |  | DELETED |  |  | --- |  |  | --- |  |  | --- |  | 9/88 | Deleted
| (Obstetrics/Nursery) Remodel | [13 empty] | by Campus
(934850)
J. | UCDMC East Wing Eighth Floor |  | 1334 | HR |  | --- |  | P | 80 | HR | W | 116 | HR | 7/88 | Admin | 7/11/88
| Remodel (934860) | [9 empty] | C | 1138 | HR
1254
K. | UCDMC Sacramento Emergency |  | 3715 | HR | P | 110 | HR | C | 2162 | HR | C | 495 | HR | 7/89 | Admin | 7/21/89 | 11/83 |  | 1984-87 CIP | 1000
| Department Remodel (934620) | ( | 1442 | ) | W | 128 | HR | [9 empty] | 11/84 |  | 1984-87 CIP | 1840
|  |  | 5157 |  | C | 820 | HR | [9 empty] | 11/84 |  | 1985-88 CIP | 2500
[5 empty] | ( C | 1442 | ) | [9 empty] | 5/86 |  | 1985-88 & 1986-89 CIP | 2500
[6 empty] | 2500 | [10 empty] | 6/88 |  | 1987-90 CIP | 4662
L. | UCDMC Intensive Care Unit |  | 999 | HR |  | --- |  | P | 149 | HR | ( W | 171 | ) | 11/91 | Admin | 11/14/91 | 11/86 |  | 1987-90 CIP | 1856
| Expansion Project (934840) | ( | 2345 | ) | [6 empty] | ( C | 2174 | ) |  |  |  | 11/87 |  | 1988-91 CIP | 2494
|  |  | 3344 | [7 empty] | C | 850 | HR
3195
M. | UCDMC Operating Room |  | 999 | HR |  | --- |  | P | 314 | HR | ( W | 361 | ) | ?/? | Admin | ( Letter | 11/87 |  | 1988-91 CIP | 5216
| Expansion Project (934820) | ( | 4902 | ) | [6 empty] | ( C | 4541 | ) |  |  | Pending )
|  |  | 5901 | [7 empty] | C | 685 | HR
5587
N. | Bodega Marine Laboratory |  | 194 | F |  | --- |  | P | 15 | U | P | 6 | U | 10/90 | Admin | 10/12/90 | 12/88 |  | 1988-91 CIP | 766
| Housing Facilities, Phase I |  | 279 | U | [6 empty] | W | 25 | X
| (936280) |  | 504 | X | [6 empty] | W | 20 | U
|  |  | 977 | [7 empty] | C | 194 | F
[11 empty] | C | 449 | X
[11 empty] | C | 238 | U
[11 empty] | E | 30 | X
962
O. | UCDMC Sacramento, Hospital |  | 5125 | HR | E | 4550 | HR | E | 575 | HR |  | --- |  | 11/84 | Regents' | N/A | 11/82 |  | 1983-86 CIP | 3500
| Information System Equipment | [13 empty] | Budget |  | 11/83 |  | 1984-87 CIP | 4325
(934382)
P. | UCDMC Acquisition of Digital |  | 200 | HR | E | 200 | HR | ( E | 1750 | ) |  | --- |  | 11/86 | Regents' | N/A | 5/86 |  | 1985-88 & 1986-89 CIP | 3200
| Electronic Telephone System | ( | 3000 | ) | ( E | 1250 | ) | [7 empty] | Budget
| (934780) |  | 3200 |  |  | 1450
| Federal Funds (F) |  | 194 | F |  | --- |  |  | --- |  |  | 194 | F
| Hospital Reserves (HR) |  | 12372 | HR |  | 5808 | HR |  | 3280 | HR |  | 3284 | HR
| Bank Loans or Bonds (LB) |  | 31945 | LB |  | --- |  |  | 31945 | LB |  | ---
Reserves other than University
| Registration Fees (N) |  | 6049 | N |  | --- |  |  | 5799 | N |  | 250 | N
| Registration Fees (R) |  | 1200 | R |  | --- |  |  | 1200 | R |  | ---
| Regents' Appropriation (U) |  | 279 | U |  | --- |  |  | 15 | U |  | 264 | U
| Other (X) |  | 1480 | X |  | --- |  |  | 976 | X |  | 504 | X
| TOTAL |  | 53519 |  |  | 5808 |  |  | 43215 |  |  | 4496
| STATE FUNDS | ( | 11689 | ) | ( | 2692 | ) | ( | 1750 | ) | ( | 7247 | )

## Irvine
IRVINE CAMPUS
1987-88 NON-STATE CAPITAL BUDGET
($000)
[9 empty] | C U R R E N T S T A T U S | [7 empty] | PRIOR ACTION/COMMENTS
|  |  | Project | [8 empty] | Beyond |  |  |  | Approval
| Project |  | Cost |  |  | Prefunded |  |  | 1987-88 |  |  | 1987-88 |  | Action |  | Letter | Date | Action | Cost
A. | Parking and Transportation |  | 12150 | LB |  | --- |  | P | 384 | LB |  | --- |  | 11/88 | Regents | 11/29/88 | 7/87 | 1987-90 CIP | 10850
| Improvements Program, Step 3 | [6 empty] | W | 470 | LB
| (996730) | [6 empty] | C | 11296 | LB
12150
B. | UCI Campus Clinical Facility |  | 6164 | N | P | 170 | N | C | 464 | N |  | --- |  | 9/87 | Regents | 10/19/87 | 3/86 | 1985-88 CIP | 4649
| (994075) |  | 420 | G | W | 207 | N | C | 250 | G
|  |  | 6584 |  | C | 4272 | N | E | 1051 | N
[6 empty] | 4649 |  | E | 170 | G
1935
C. | UCIMC Parking Program, Step 1 |  | 6243 | LB |  | --- |  | P | 197 | LB |  | --- |  | 9/87 | Regents | 11/18/87
| (994600) | [6 empty] | W | 241 | LB
[8 empty] | C | 5805 | LB
6243
D. | Graduate Student Apartments |  | 13768 | LB |  | --- |  | P | 434 | LB |  | --- |  | 9/87 | Regents | 11/25/87
| (991575) | [6 empty] | W | 530 | LB
[8 empty] | C | 12754 | LB
[8 empty] | E | 50 | LB
13768
E. | Satellite Food Service Facilities |  | 4001 | LB |  | --- |  | P | 119 | LB |  | --- |  | 10/87 | Admin | 10/7/87
| (991595) | [6 empty] | W | 145 | LB
[8 empty] | C | 3493 | LB
[8 empty] | E | 244 | LB
4001
F. | Campus Child Care Center |  | 1700 | LB |  | --- |  | P | 47 | LB |  | --- |  | 7/88 | Admin | 7/22/88 | 10/87 | 1987-90 CIP | 1500
| (991580) | [6 empty] | W | 57 | LB
[8 empty] | C | 1576 | LB
[8 empty] | E | 20 | LB
1700
G. | Irvine Campus Housing Community |  | 2310 | LB |  | --- |  | P | 60 | LB |  | --- |  | 5/88 | Admin | 5/27/88
| Program Infrastructure | [6 empty] | W | 74 | LB
| Improvements, Phase 4 (996385) | [6 empty] | C | 2176 | LB
2310
H. | Central Housing Office Building |  | 1098 | N | P | 75 | N | C | 202 | N |  | --- |  | 1/88 | Admin | 1/20/88 | 2/86 | 1985-88 CIP | 896
| (996400) |  |  |  | W | 96 | N
[5 empty] | C | 725 | N
896
I. | ICS/Engineering Research Facility |  | 2251 | G | P | 76 | U | C | 253 | G |  | --- |  | 6/88 | Admin | 6/22/88 | 12/86 | 1986-89 CIP | 2348
| Phase 2 (991785) |  | 1000 | U | P | 39 | G | C | 550 | X
|  |  | 1050 | X | W | 89 | U | E | 1150 | G
|  |  | 4301 |  | W | 52 | G |  | 1953
[5 empty] | C | 835 | U
[5 empty] | C | 500 | X
[5 empty] | C | 757 | G
2348
J. | Professional Programs Facility |  | 2500 | LB | P | 64 | U | P | 108 | U |  | --- |  | 6/88 | Admin | 6/15/88 | 10/82 | 1982-85 CIP | 6310
| (Formerly: Graduate School of |  | 1500 | U |  |  |  | W | 207 | U | [6 empty] | 10/82 | 1983-86 CIP | 6310
| Management) (991145) |  | 2050 | X |  |  |  | C | 1121 | U | [6 empty] | 11/85 | 1985-88 CIP | 6050
|  |  | 6050 |  |  |  |  | C | 2050 | X
[8 empty] | C | 1860 | LB
[8 empty] | E | 640 | LB
5986
K. | UCIMC Cancer Center Module |  | 100 | HR | P | 100 | HR | ( C | 9247 | ) | ( E | 1014 | ) | 11/87 | Regents' | N/A | 5/86 | 1985-88 CIP and
| (994470) | ( | 11408 | ) | ( P | 399 | ) | [7 empty] | Budget |  |  | 1986-89 CIP | 11469
|  |  | 11508 |  | ( W | 748 | ) | [9 empty] | 11/86 | 1987-90 CIP | 11469
1247
L. | UCIMC Intensive Care Unit and |  | 410 | HR | P | 14 | HR | ( E | 1687 | ) | C | 378 | HR | 11/88 | Admin | 11/11/88 | 11/84 | 1985-88 CIP | 6003
| Support System Renovation | ( | 6003 | ) | W | 18 | HR | [9 empty] | 11/85 | 1986-89 CIP | 6035
| (994530) |  | 6413 |  | ( PW | 164 | ) | [9 empty] | 11/86 | 1987-90 CIP | 6035
[5 empty] | ( C | 4152 | )
4348
| Gifts (G) |  | 2671 | G |  | 848 | G |  | 1823 | G |  | ---
| Hospital Reserve Funds (HR) |  | 510 | HR |  | 132 | HR |  | --- |  |  | 378 | HR
| Bank Loans or Bonds (LB) |  | 42672 | LB |  | --- |  |  | 42672 | LB |  | ---
Reserves Other Than University
| Registration Fees (N) |  | 7262 | N |  | 5545 | N |  | 1717 | N |  | ---
| Regents' Appropriation (U) |  | 2500 | U |  | 1064 | U |  | 1436 | U
| Other (X) |  | 3100 | X |  | 500 | X |  | 2600 | X |  | ---
|  |  | 0 |  |  | 0 |  |  | 0
| TOTAL |  | 58715 |  |  | 8089 |  |  | 50248 |  |  | 378
| STATE FUNDS | ( | 17411 | ) | ( | 5463 | ) | ( | 10934 | ) | ( | 1014 | )

## Los Angeles
LOS ANGELES CAMPUS
1987-88 NON-STATE CAPITAL BUDGET
($000)
[9 empty] | C U R R E N T S T A T U S | [7 empty] | PRIOR ACTION/COMMENTS
|  |  | Project | [8 empty] | Beyond |  |  |  | Approval
| Project |  | Cost |  |  | Prefunded |  |  | 1987-88 |  |  | 1987-88 |  | Action |  | Letter | Date | Action | Cost
A. | Northwest Housing and Parking, |  | 81486 | LB |  | --- |  | P | 3220 | LB | P | 170 | G | 11/90 | Regents | 11/29/90 | 7/87 | 1987-90 CIP | 62137
| Phase I (946505) |  | 3869 | G |  |  |  | W | 3000 | LB | W | 190 | G |  |  |  | 7/88 | 1987-90 CIP | 62137
|  |  | 440 | X |  |  |  | C | 75266 | LB | C | 3509 | G |  |  |  | 9/88 | 1987-90 &
|  |  | 85795 | [5 empty] | 81486 |  | C | 440 | X |  |  |  |  | 1988-91 CIP | 73300
[12 empty] | 4309 |  |  |  |  | 3/89 | 1988-91 CIP | 77169
B. | UCLA Medical Center, Main |  | 20856 | HR | P | 2280 | HR | C | 8891 | HR | C | 9685 | HR | 9/92 | Admin | 9/29/92 | 9/86 | 1986-89 CIP | 26540
| Operating Room Suite Expansion |  | 40244 | LB | W | 5244 | LB |  |  |  | C | 35000 | LB |  |  |  | 7/87 | 1987-90 CIP | 36600
| (944880) (Formerly: Medical |  | 61100 |  |  | 7524 | [5 empty] | 44685 |  |  |  |  | 9/89 | 1989-92 CIP | 51415
| Center Operating Room #10 | [15 empty] | 3/91 | 1990-93 CIP | 59002
Expansion)
C. | Northwest Recreation, Phase I |  | 5355 | LB |  | --- |  | P | 159 | LB |  | --- |  | 3/89 | Regents | 3/17/89 | 7/87 | 1987-90 CIP | 4956
| (946350) |  | 1379 | N |  |  |  | P | 28 | N | [6 empty] | 3/88 | 1987-90 CIP | 5815
|  |  | 40 | X |  |  |  | P | 18 | X
|  |  | 6774 |  |  |  |  | W | 225 | LB
[8 empty] | W | 22 | X
[8 empty] | C | 1351 | N
[8 empty] | C | 4971 | LB
6774
D. | UCLA Medical Center 7th Floor |  | 3881 | HR | P | 118 | HR | W | 192 | HR | P | 207 | HR | 7/89 | Admin | 8/14/89 | 8/85 | 1985-88 CIP | 8766
| Neurosurgery ICU Alterations | [6 empty] | C | 2536 | HR | W | 226 | HR |  |  |  | 8/87 | 1987-90 CIP | 2802
| (945030) (Formerly: 7th and 8th | [7 empty] | 2728 |  | C | 602 | HR
| Floor Alterations UCLA Medical | [10 empty] | 1035
Center)
E. | Murphy Hall West Wing Third |  | 686 | X |  | --- |  | P | 55 | X |  | --- |  | 8/87 | Admin | 8/4/87
| Floor Alts. (942270) | ( | 150 | ) |  |  |  | W | 70 | X
|  |  | 836 |  |  |  |  | C | 561 | X
[8 empty] | ( E | 150 | )
836
F. | UCLA Medical Center Gift Shop |  | 150 | HR |  | --- |  | P | 68 | G | C | 150 | HR | 9/89 | Admin | 9/13/89 | 8/87 | 1987-90 CIP | 438
| Alteration (945100) |  | 305 | G |  |  |  | W | 104 | G | [6 empty] | 9/89 | 1989-91 CIP | 455
|  |  | 455 |  |  |  |  | C | 133 | G
305
G. | UCLA Medical Center House Staff |  | DELETED |  |  | --- |  |  | --- |  |  | --- |  | Deleted |  | --- | 8/87 | 1987-90 CIP | 472
| Sleep Quarters Alteration | [12 empty] | by campus
(945270)
H. | Ackerman Union A-Level |  | DELETED |  |  | --- |  |  | --- |  |  | --- |  | 4/91 | Deleted -- |  | 9/87 | 1987-90 CIP | 5500
| Alterations, Phase II (940376) | [12 empty] | Replaced by two projects of |  |  | 3/88 | 1988-91 CIP | 17543
increased scope: Ackerman
Union Life Safety
Renovation/Building
Expansion, and Kerckhoff Hall
Life Safety Renovation
I. | International Center, Phase I |  | 2492 | G |  | --- |  | P | 420 | G | P | 74 | G | 6/98 | Admin | 6/23/98 | 5/88 | 1987-90 CIP | 7052
| (renamed the Tom Bradley |  | 8054 | LB |  |  |  | W | 517 | G | P | 82 | LB |  |  |  | 5/94 | 1993-96 CIP | 10200
| International Center for Students |  | 1550 | X |  |  |  | C | 773 | G | W | 72 | G |  |  |  | 11/94 | 1994-97 CIP | 10520
| and Scholars) (942300) |  | 2184 | N |  |  |  | E | 280 | G | W | 104 | X |  |  |  | 11/97 | 1997-00 CIP | 13994
|  |  | 14280 | [5 empty] | 1990 |  | C | 356 | G
[11 empty] | C | 7972 | LB
[11 empty] | C | 1446 | X
[11 empty] | C | 2184 | N
12290
J. | UCLA Medical Center CHS Annex |  | 4647 | HR |  | --- |  | P | 86 | HR | C | 1407 | HR | 10/91 | Admin | 10/22/91 | 11/87 | 1987-90 CIP | 3240
| Building (944870) (Formerly: | [6 empty] | W | 182 | HR | [6 empty] | 9/88 | 1988-91 CIP | 4471
| UCLA Medical Center Hospital | [6 empty] | C | 2972 | HR
| Annex Replacement Building) | [7 empty] | 3240
K. | Anderson Graduate School of |  | 26466 | G |  | --- |  | P | 2670 | G | (W | 1315 | ) | 11/96 | Admin | 12/5/96 | 1/88 | 1987-90 CIP | 67234
| Management (942500) | ( | 27141 | ) | [6 empty] | W | 2951 | G |  |  |  | 11/88 | 1989-91 CIP | 59266
|  |  | 593 | X | [6 empty] | ( C | 25825 | ) |  |  |  | 11/89 | 1990-93 CIP | 65840
|  |  | 27200 | LB | [6 empty] | C | 17939 | G |  |  |  | 3/91 | 1990-93 CIP | 67692
|  |  | 81400 | [7 empty] | C | 593 | X |  |  |  | 6/95 | 1994-97 CIP | 79290
[11 empty] | C | 27200 | LB
[11 empty] | E | 2907 | G
78730
L. | Seismic Renovation of High-Rise |  | 22208 | LB |  | --- |  | P | 500 | LB |  | --- |  | 3/89 | Regents | 3/21/89 | 3/88 | 1987-90 CIP | 15108
| Residence Halls (948703) | [6 empty] | W | 800 | LB
[8 empty] | C | 20908 | LB
22208
M. | Gordon L. and Virginia MacDonald |  | 25924 | G | P | 918 | G | W | 1233 | G |  | --- |  | 3/89 | Regents | 5/10/89 | 7/86 | 1986-89 CIP | 46953
| Medical Research Laboratory |  | 13341 | X | P | 253 | N | W | 339 | N | [6 empty] | 5/88 | 1986-89 &
| Building (944610) |  | 7950 | N | P | 787 | X | W | 1056 | X | [7 empty] | 1987-90 CIP | 45311
|  |  | 47215 |  |  | 1958 |  | C | 23773 | G
[8 empty] | C | 7358 | N
[8 empty] | C | 11498 | X
45257
N. | School of Medicine, Department |  | 259 | X |  | --- |  | P | 13 | X |  | --- |  | 12/88 | Admin | 12/6/88 | 6/88 | 1987-90 CIP | 234
| of Physiology Administrative Area | [6 empty] | W | 14 | X
| Remodel (945310) | [6 empty] | C | 232 | X
259
O. | NO PROJECT
P. | Wight Gallery Air Conditioning |  | 137 | F |  | --- |  | P | 8 | F |  | --- |  | 6/88 | Admin | 6/30/88
| (940730) |  | 305 | X |  |  |  | W | 50 | F
|  | ( | 211 | ) |  |  |  | C | 79 | F
|  |  | 653 |  |  |  |  | C | 305 | X
[8 empty] | ( C | 211 | )
653
Q. | CHS Fourth Floor West Special |  | 565 | HR | P | 15 | HR | P | 14 | HR | W | 47 | HR | 8/90 | Admin | 8/16/90 | 7/88 | 1988-91 CIP | 415
| Procedures Unit Alteration | [6 empty] | W | 53 | HR | C | 436 | HR
| (945170) | [7 empty] | 67 |  |  | 483
R. | West Campus Staging Facility I |  | 4770 | HR |  | --- |  | P | 103 | HR |  | --- |  | 6/89 | Admin | 6/9/89 | 6/87 | 1986-89 CIP | 3699
| (940490) | [6 empty] | W | 128 | HR | [6 empty] | 7/88 | 1986-89 &
[8 empty] | C | 4539 | HR | [7 empty] | 1987-90 CIP | 4770
4770
S. | NO PROJECT
T. | West Campus Staging Facility II |  | 4546 | LB |  | --- |  | P | 75 | LB |  | --- |  | 6/88 | Admin | 6/15/88
| (940494) | [6 empty] | W | 75 | LB
[8 empty] | C | 3696 | LB
[8 empty] | E | 700 | LB
4546
U. | Linguistics Department |  | 1000 | U |  | --- |  | P | 89 | U |  | --- |  | 7/88 | Admin | 7/22/88
| Alterations, Campbell Hall | ( | 85 | ) |  |  |  | W | 114 | U
| (941060) |  | 1085 |  |  |  |  | C | 797 | U
[8 empty] | ( C | 85 | )
1085
V. | School of Medicine Center for |  | 302 | X |  | --- |  | P | 13 | X |  | --- |  | 12/88 | Admin | 5/25/89 | 7/88 | 1987-90 CIP | 214
| Health Sciences First Floor | [6 empty] | W | 20 | X
| Student Affairs Office Alterations | [6 empty] | C | 269 | X
| (944730) | [7 empty] | 302
W. | School of Dentistry Venice |  | 148 | G |  | --- |  | P | 25 | X | W | 8 | X | 5/90 | Admin | 5/24/90 | 7/88 | 1988-91 CIP | 521
| Community Dental Expansion |  | 418 | X |  |  |  | W | 27 | X | C | 358 | X
| (945160) |  | 566 | [5 empty] | 52 |  | C | 148 | G
514
X. | UCLA Medical Center, 7th Floor |  | 2071 | HR |  | --- |  | P | 103 | HR | P | 114 | HR | 1/91 | Admin | 1/10/91 | 7/88 | 1988-91 CIP | 1611
| East Cardiac Intensive Care Unit | [6 empty] | W | 110 | HR | W | 169 | HR |  |  |  | 4/89 | 1989-92 CIP | 1903
| Alterations (944500) | [7 empty] | 213 |  | C | 1575 | HR
1858
Y. | UCLA Medical Center CHS |  | 964 | HR |  | --- |  | P | 31 | HR | W | 23 | HR | 8/90 | Admin | 8/29/90 | 6/88 | 1987-90 CIP | 681
| Non-Invasive Cardiology | [6 empty] | W | 72 | HR | C | 838 | HR |  |  |  | 6/89 | 1988-91 CIP | 894
| Alterations (945190) | [7 empty] | 103 |  |  | 861
Z. | UCLA Medical Center Pediatric |  | 1334 | HR |  | --- |  | P | 10 | HR | P | 72 | HR | 1/89 | Admin | 1/5/89
| Catheterization Laboratory Alt. | [9 empty] | W | 158 | HR
| (945290) | [9 empty] | C | 1094 | HR
1324
AA. | UCLA Medical Center B-Level |  | 28169 | HR |  | --- |  | P | 200 | HR | P | 1532 | HR | 3/91 | Admin | 3/7/91 | 1/89 | 1988-91 CIP | 34434
| Radiological Sciences Alts. | [9 empty] | W | 2715 | HR
| (945180) | [9 empty] | C | 23722 | HR
27969
BB. | UCLA Medical Center Mark Taper |  | 310 | HR |  | --- |  | P | 5 | HR | P | 29 | HR | 11/90 | Admin | 11/29/90 | 3/89 | 1988-91 CIP | 250
| Center for Health Enhancement | [9 empty] | W | 44 | HR |  |  |  | 6/90 | 1989-92 CIP | 250
| Radiological Sciences Site | [9 empty] | C | 232 | HR
| Improvements (945360) | [10 empty] | 305
CC. | Biomedical Cyclotron Nuclear |  | 20 | HR |  | --- |  | P | 20 | HR | P | 112 | X | 4/89 | Admin | 4/18/89
| Medicine and Biophysics Addition |  | 1111 | G | [6 empty] | W | 168 | X
| (945302) |  | 721 | X | [6 empty] | C | 441 | X
|  |  | 1852 | [7 empty] | C | 1111 | G
1832
DD. | UCLA Medical Center B-Level |  | 220 | HR |  | --- |  | P | 9 | HR | C | 185 | HR | 6/89 | Admin | 6/9/89
| Emergency Medicine Alts. | [6 empty] | W | 26 | HR
| (945910) | [7 empty] | 35
EE. | Chemistry and Biological |  | 7500 | G | ( P | 1350 | ) | ( W | 1486 | ) | C | 7500 | G | 9/92 | State | N/A | 11/85 | 1986-89 CIP | 36805
| Sciences Addition (941080) | ( | 40234 | ) | [6 empty] | ( C | 36198 | ) |  | Budget Act |  | 11/86 | 1987-90 CIP | 36075
|  |  | 47734 | [7 empty] | ( E | 1200 | ) |  |  |  | 11/87 | 1988-91 CIP | 36805
[12 empty] | 44898 |  |  |  |  | 11/89 | 1990-93 CIP | 36891
[17 empty] | 10/90 | 1991-94 CIP | 43462
[17 empty] | 11/91 | 1992-95 CIP | 47711
FF. | Off-Campus Surface Parking Lot, |  | 1451 | N | PWC | 1286 | N | PWC | 165 | N |  | --- |  | 7/86 | Admin | 7/7/86
Veteran's Administration Property
(946650)
GG. | Medical Center 1-South |  | 2155 | HR | P | 100 | HR | W | 271 | HR |  | --- |  | 3/87 | Admin | 4/3/87
| Neurosurgery Alterations (945090) | [6 empty] | C | 1784 | HR
2055
HH. | Central Ticket Office Expansion |  | 1825 | X | P | 35 | X | W | 65 | X | W | 307 | X | 4/89 | Admin | 4/18/89 | 7/87 | 1986-89 CIP | 832
| (942020) | [6 empty] | C | 13 | X | C | 1217 | X
[9 empty] | 78 |  | E | 188 | X
1712
II. | Outpatient Care Center (Formerly: |  | 12500 | HR | P | 3001 | LB | C | 12500 | HR |  | --- |  | 5/87 | Regents | 7/9/87 | 3/86 | 1985-88 CIP | 71057
| Center for Health Sciences Mixed |  | 78588 | LB | W | 4502 | LB | [9 empty] | 7/86 | 1985-88 & 1986-89 CIP | 75000
| Use Building) (945070) |  | 91088 |  | C | 71085 | LB
78588
| Federal (F) |  | 137 | F |  | --- |  |  | 137 | F |  | ---
| Gifts (G) |  | 67815 | G |  | 918 | G |  | 29971 | G |  | 36927 | G
| Hospital Reserves (HR) |  | 82612 | HR |  | 2513 | HR |  | 34837 | HR |  | 45262 | HR
| Bank Loans or Bonds (LB) |  | 267681 | LB |  | 83832 | LB |  | 113595 | LB |  | 70254 | LB
Reserves Other Than University
| Registration Fees (N) |  | 12964 | N |  | 1539 | N |  | 9241 | N |  | 2184 | N
| Regents' Appropriation (U) |  | 1000 | U |  | --- |  |  | 1000 | U |  | ---
| Other (X) |  | 20480 | X |  | 822 | X |  | 14276 | X |  | 5382 | X
| TOTAL |  | 452689 |  |  | 89624 |  |  | 203057 |  |  | 160009
| STATE FUNDS | ( | 67821 | ) | ( | 1350 | ) | ( | 1932 | ) | ( | 64538 | )

## Riverside
RIVERSIDE CAMPUS
1987-88 NON-STATE CAPITAL BUDGET
($000)
[6 empty] | C U R R E N T S T A T U S | [5 empty] | PRIOR ACTION/COMMENTS
|  | Project | [5 empty] | Beyond |  |  | Approval
| Project | Cost |  | Prefunded |  | 1987-88 |  | 1987-88 | Action |  | Letter | Date | Action | Cost
A. | Athletic Complex Expansion (950367) | 1200 | X | --- | P | 48 | X | --- | 2/88 | Admin | 2/19/88
[5 empty] | W | 52 | X
[5 empty] | C | 1100 | X
1200
| Other (X) | 1200 | X | --- |  | 1200 | X | ---
| TOTAL | 1200 |  | --- |  | 1200 |  | ---

## San Diego
SAN DIEGO CAMPUS
1987-88 NON-STATE CAPITAL BUDGET
($000)
[9 empty] | C U R R E N T S T A T U S | [7 empty] | PRIOR ACTION/COMMENTS
|  |  | Project | [8 empty] | Beyond |  |  |  | Approval
| Project |  | Cost |  |  | Prefunded |  |  | 1987-88 |  |  | 1987-88 |  | Action |  | Letter | Date | Action | Cost
A. | Matthews Administrative and |  | 499 | G |  | --- |  | P | 24 | G |  | --- |  | 7/87 | Admin | 7/20/87
| Academic Complex 303 | [6 empty] | W | 57 | G
| Remodeling (964900) | [6 empty] | C | 418 | G
499
B. | UCSD Medical Center, Cardiology |  | 819 | HR | P | 25 | HR | C | 753 | HR |  | --- |  | 10/87 | Admin | 10/5/87
| Procedure Room (965010) |  |  |  | W | 41 | HR
66
C. | UCSD Medical Center Emergency |  | 3621 | LB |  | --- |  |  | --- |  | P | 87 | LB | 3/92 | Admin | 3/25/92 | 11/87 | 1987-90 CIP | 2522
| Power Upgrade (EPU) Project | [9 empty] | W | 160 | LB
| (965020) | [9 empty] | C | 3374 | LB
3621
D. | Marine Biology Building Chiller |  | 301 | LB |  | --- |  | P | 5 | LB |  | --- |  | 1/88 | Admin | 1/12/88
| Retrofit/Addition (961730) | [6 empty] | W | 25 | LB
[8 empty] | C | 271 | LB
301
E. | Clinical Sciences Building (965030) |  | 6825 | G |  | --- |  | P | 755 | X | W | 25 | X | 9/92 | Admin | 9/24/92 | 3/88 | 1987-90 CIP | 25165
|  |  | 15165 | LB |  |  |  | W | 245 | X | C | 825 | G
|  |  | 3000 | U |  |  |  | W | 762 | U |  | 850
|  |  | 1025 | X |  |  |  | C | 2238 | U
|  |  | 26015 |  |  |  |  | C | 6000 | G
[8 empty] | C | 15165 | LB
25165
F. | Laboratory Completion Project, |  | 452 | G |  | --- |  | P | 31 | X |  | --- |  | 5/88 | Admin | 5/5/88
| Molecular Biology Research |  | 625 | X |  |  |  | W | 38 | X
| Facility, Unit II (961650) |  | 1077 |  |  |  |  | C | 556 | X
[8 empty] | C | 452 | G
1077
G. | Shiley Eye Center (964990) |  | 2532 | G |  | --- |  | P | 180 | G | P | 25 | HR | 5/92 | Admin | 5/12/92 | 5/88 | 1987-90 CIP | 7059
|  |  | 516 | HR |  |  |  | W | 230 | G | W | 50 | HR
|  |  | 4056 | LB |  |  |  | C | 1390 | G | C | 441 | HR
|  |  | 500 | X |  |  |  | C | 500 | X | C | 732 | G
|  |  | 7604 |  |  |  |  | C | 4056 | LB |  | 1248
6356
H. | Parking and Roadway |  | 4940 | LB | P | 104 | LB | P | 39 | LB |  | --- |  | 5/88 | Admin | 5/27/88 | 5/87 | 1986-89 CIP | 3920
| Improvements (961570, 961660, |  |  |  | W | 138 | LB | W | 40 | LB
| 966551, 966552) |  |  |  | C | 3678 | LB | C | 941 | LB
[6 empty] | 3920 |  |  | 1020
I. | Molecular Biology Research |  | 12468 | X |  |  |  | P | 300 | X | C | 1173 | X | 10/90 | Admin | 10/18/90 | 9/85 | 1985-88 CIP | 11310
| Facility Unit II (961490) | [6 empty] | W | 400 | X | [6 empty] | 1/88 | 1987-90 CIP | 11295
[8 empty] | C | 10595 | X
11295
J. | Third College Science Teaching |  | 13 | N |  | --- |  | P | 80 | U |  | --- |  | 7/87 | Admin | 7/28/87 | 6/86 | 1985-88 CIP | 2600
| Lab Addition (961550) |  | 1000 | U |  |  |  | W | 100 | U
|  |  | 2075 | X |  |  |  | C | 820 | U
|  |  | 3088 |  |  |  |  | C | 2075 | X
[8 empty] | C | 13 | N
3088
K. | Campus Entrance (961630) |  | 491 | LB | P | 12 | LB | C | 166 | LB |  | --- |  | 4/88 | Admin | 4/21/88 | 10/86 | 1986-89 CIP | 325
[5 empty] | W | 18 | LB
[5 empty] | C | 295 | LB
325
L. | Engineering Building Unit 1 |  | 300 | U | P | 300 | U | ( E | 3926 | ) |  | --- |  | 11/86 | Regents' | N/A | 11/85 | 1985-88 CIP | 42126
| (961170) | ( | 45826 | ) | ( P | 395 | ) | [7 empty] | Budget
|  |  | 46126 |  | ( W | 1055 | )
[5 empty] | ( C | 35450 | )
[5 empty] | ( E | 5000 | )
42200
M. | UCSD Medical Center, University |  | 2000 | HR | P | 24 | HR | P | 36 | HR |  | --- |  | 11/84 | Regents' | N/A | 10/81 | 1982-85 CIP | 2000
| Hospital Equipment Tie-Down |  |  |  | W | 40 | HR | W | 60 | HR |  |  |  |  | Budget |  | 10/82 | 1983-86 CIP | 2000
| (964780) |  |  |  | C | 736 | HR | C | 1104 | HR | [6 empty] | 10/83 | 1984-87 CIP | 2000
[6 empty] | 800 |  |  | 1200
N. | UCSD Medical Center |  | 260 | HR | P | 120 | HR | ( E | 200 | ) |  | --- |  | 5/86 | Regents | 6/2/86 | 3/86 | 1985-88, 1986-89 &
| Administrative Multipurpose Facility | ( | 5240 | ) | W | 140 | HR | [10 empty] | 1987-90 CIP | 5500
| (Formerly: UCSD Medical Center |  | 5500 |  | ( C | 5040 | )
| Multipurpose Facility) (964920) |  |  |  |  | 5300
O. | UCSD Medical Center Inpatient |  | 2076 | HR | P | 362 | HR | ( W | 1014 | ) | ( C | 27834 | ) | 2/94 | Admin | 2/2/94 | 5/86 | 1985-88 & 1986-89 CIP | 29450
| Tower Completion and |  | 2622 | LB | ( P | 511 | ) | ( C | 4176 | ) | C | 2622 | LB |  |  |  | 11/87 | 1988-91 CIP | 32301
| Modernization Project (946950) |  | 105 | G | ( W | 182 | ) |  | 5190 |  | C | 1530 | HR |  |  |  | 1/90 | 1989-92 CIP | 34079
|  | ( | 33717 | ) |  | 1055 |  |  |  |  | C | 105 | G |  |  |  | 12/92 | 1992-95 CIP | 36701
|  |  | 38520 | [7 empty] | E | 184 | HR
32275
| Gifts (G) |  | 12930 | G |  | --- |  |  | 8751 | G |  | 837 | G
| Hospital Reserves (HR) |  | 5671 | HR |  | 1488 | HR |  | 1953 | HR |  | 2230 | HR
| Bank Loans or Bonds (LB) |  | 31196 | LB |  | 4245 | LB |  | 20708 | LB |  | 6243 | LB
Reserves other than University
| Registration Fee (N) |  | 13 | N |  | --- |  |  | 13 | N |  | ---
| Regents' Appropriations (U) |  | 4300 | U |  | 300 | U |  | 4000 | U |  | ---
| Other (X) |  | 16693 | X |  | --- |  |  | 15495 | X |  | 2023 | X
| TOTAL |  | 70803 |  |  | 6033 |  |  | 50920 |  |  | 11333
| STATE FUNDS | ( | 84783 | ) | ( | 47633 | ) | ( | 9316 | ) | ( | 27834 | )

## San Francisco
SAN FRANCISCO CAMPUS
1987-88 NON-STATE CAPITAL BUDGET
($000)
[6 empty] | C U R R E N T S T A T U S | [7 empty] | PRIOR ACTION/COMMENTS
|  | Project | [6 empty] | Beyond |  |  |  | Approval
| Project | Cost |  | Prefunded |  | 1987-88 |  |  | 1987-88 |  | Action |  | Letter | Date | Action | Cost
A. | SFGH Bldg. 1 Lung Biology and | 800 | G | --- | P | 50 | X |  | --- |  | 8/87 | Admin | 8/4/87
| Anesthesia Research | 1007 | X |  | W | 145 | X
| Improvements (925300) | 1807 |  |  | C | 812 | X
[5 empty] | C | 800 | G
1807
B. | School of Medicine Laboratory | 759 | X | --- | P | 20 | X |  | --- |  | 12/87 | Admin | 12/14/87
| Improvements for Hearing |  |  |  | W | 50 | X
| Research (927670) |  |  |  | C | 689 | X
759
C. | Pharmacology Laboratory for | 575 | X | --- | P | 20 | X |  | --- |  | 12/87 | Admin | 12/14/87
| Cytoskeletal Research |  |  |  | W | 35 | X
| Improvements (920440) |  |  |  | C | 520 | X
575
D. | Accounting Office Improvements | 1384 | X | --- | P | 40 | X |  | --- |  | 10/87 | Admin | 10/30/87
| (920480) |  |  |  | W | 80 | X
[5 empty] | C | 1264 | X
1384
E. | UCSF Medical Center, Obstetrics | 3940 | HR | --- | P | 110 | HR |  | --- |  | 12/87 | Admin | 12/1/87
| Inpatient Service Relocation |  |  |  | W | 220 | HR
| (920520) |  |  |  | C | 3310 | HR
[5 empty] | E | 300 | HR
3940
F. | Pediatric Intensive Care Unit | 1000 | HR | --- | P | 60 | HR |  | --- |  | 12/87 | Admin | 12/14/87
| Relocation (925740) | 1000 | X |  | W | 120 | HR
|  | 2000 |  |  | C | 820 | HR
[5 empty] | C | 1000 | X
2000
G. | Transgenic Research Animal | 795 | X | --- | P | 25 | X |  | --- |  | 11/87 | Admin | 11/25/87
| Care Facility (925780) |  |  |  | W | 50 | X
[5 empty] | C | 720 | X
795
H. | UCSF Medical Center, | 900 | HR | --- | P | 25 | HR |  | --- |  | 11/87 | Admin | 11/18/87
| Interventional Radiology |  |  |  | W | 55 | HR
| Improvements (925750) |  |  |  | C | 820 | HR
900
I. | UCSF Medical Center, UCH-1 | 400 | HR | --- | P | 12 | HR |  | --- |  | 2/88 | Admin | 2/26/88
| Neurosurgery Outpatient Offices |  |  |  | W | 24 | HR
| (925800) |  |  |  | C | 364 | HR
400
J. | UCSF Medical Center, HCM-8 | 800 | HR | --- | P | 25 | HR |  | --- |  | 4/88 | Admin | 4/12/88
| Neurosurgery Inpatient Service |  |  |  | W | 50 | HR
| Relocation (925830) |  |  |  | C | 725 | HR
800
K. | MSB 4 School of Medicine, | 1482 | X | --- | P | 135 | X |  | --- |  | 6/88 | Admin | 6/3/88
| Microbiology/Immunology |  |  |  | W | 200 | X
| Alterations (925790) |  |  |  | C | 1147 | X
1482
L. | School of Medicine HSIR-16 | 1350 | G | --- | P | 50 | G |  | --- |  | 5/88 | Admin | 5/26/88
| Reproductive Endocrinology | 416 | X |  | W | 100 | G
| Center Improvements (920420) | 1766 |  |  | C | 1200 | G
[5 empty] | C | 416 | X
1766
M. | Millberry Union Recreation and | 1200 | G | --- |  | --- |  | P | 125 | N | 11/88 | Regents | 11/29/88 | 5/88 | 1987-90 CIP | 4720
| Fitness Facility Improvements | 5070 | LB |  |  |  |  | W | 105 | N
| (925680) | 230 | N |  |  |  |  | W | 95 | LB
|  | 6500 | [5 empty] | C | 4975 | LB
[8 empty] | C | 948 | G
[8 empty] | E | 252 | G
6500
N. | LPPI G-5 Ramps/Office | 1600 | X | --- | P | 83 | X |  | --- |  | 6/88 | Admin | 6/23/88
| Reconfiguration (925600) |  |  |  | W | 100 | X
[5 empty] | C | 1417 | X
1600
O. | LPPI 3rd Floor Chairman's Suite | 281 | X | --- | P | 8 | X |  | --- |  | 6/88 | Admin | 6/17/88
| Improvements (920490) |  |  |  | W | 16 | X
[5 empty] | C | 257 | X
281
P. | School of Medicine, CED 2 | 250 | X | --- | P | 15 | X |  | --- |  | 6/88 | Admin | 6/21/88
| Laboratory for Cell Analysis |  |  |  | W | 35 | X
| Improvements (925310) |  |  |  | C | 200 | X
250
Q. | School of Medicine Ambulatory | 268 | X | --- | P | 17 | X |  | --- |  | 6/88 | Admin | 6/23/88
| Care Center C-Level Pediatrics |  |  |  | W | 37 | X
| Alts. (920640) |  |  |  | C | 214 | X
268
R. | School of Medicine/SFGH Harrison | 480 | X | --- | P | 15 | X |  | --- |  | 6/88 | Admin | 6/23/88
| Street Building Third Floor Office |  |  |  | W | 30 | X
| Improvement (920590) |  |  |  | C | 435 | X
480
S. | School of Medicine U-3 Radiation | 762 | X | --- | P | 23 | X |  | --- |  | 6/88 | Admin | 6/23/88
| Oncology Laboratory |  |  |  | W | 46 | X
| Improvements (925710) |  |  |  | C | 693 | X
762
T. | School of Medicine M-12 General | 519 | F | --- | P | 16 | F |  | --- |  | 7/88 | Admin | 7/20/88
| Clinical Research Center Research |  |  |  | W | 31 | F
| Kitchen and Outpatient Facility |  |  |  | C | 472 | F
| Improvements (920580) |  |  |  |  | 519
U. | UCSF Medical Center, M-4 | 350 | HR | --- | P | 10 | HR |  | --- |  | 7/88 | Admin | 7/20/88
| Urology Lithostar Installation |  |  |  | W | 20 | HR
| (925870) |  |  |  | C | 320 | HR
350
V. | UCSF Medical Center, M-L Chilled | 2200 | HR | --- | P | 50 | HR | P | 15 | HR | 11/88 | Admin | 11/14/88
| Water System Addition (920610) | [6 empty] | W | 130 | HR
[8 empty] | C | 2005 | HR
2150
| Federal Funds (F) | 519 | F | --- |  | 519 | F |  | ---
| Gift Funds (G) | 3350 | G | --- |  | 2150 | G |  | 1200 | G
| Hospital Reserves (HR) | 9590 | HR | --- |  | 7440 | HR |  | 2150 | HR
| Bank Loan or Bonds (LB) | 5070 | LB | --- |  | --- |  |  | 5070 | LB
Reserves other than University
| Registration Fees (N) | 230 | N | --- |  | --- |  |  | 230 | N
| Other (X) | 11059 | X | --- |  | 11059 | X |  | ---
|  | 29818 |  | --- |  | 21168 |  |  | 8650

## Santa Barbara
SANTA BARBARA CAMPUS
1987-88 NON-STATE CAPITAL BUDGET
($000)
[6 empty] | C U R R E N T S T A T U S | [5 empty] | PRIOR ACTION/COMMENTS
|  | Project | [5 empty] | Beyond |  |  | Approval
| Project | Cost |  | Prefunded |  | 1987-88 |  | 1987-88 | Action |  | Letter | Date | Action | Cost
A. | Microelectronics Clean Room | 867 | G | --- | P | 50 | G | --- | 3/88 | Admin | 3/15/88 | 11/87 | 1987-90 CIP | 927
| Facility (980780) | 175 | X |  | W | 60 | G
|  | 1042 |  |  | C | 757 | G
[5 empty] | C | 175 | X
1042
B. | NO PROJECT
C. | Residence Halls Renovations | 3200 | LB | --- | P | 110 | LB | --- | 6/88 | Admin | 6/23/88 | 1/88 | 1987-90 CIP | 3200
| Program, Phase III, San Nicolas Hall | 509 | N |  | W | 130 | LB
| (980800) | 3709 |  |  | C | 2335 | LB
[5 empty] | C | 509 | N
[5 empty] | E | 625 | LB
3709
| Gifts (G) | 867 | G | --- |  | 867 | G | ---
| Bank Loans or Bonds (LB) | 3200 | LB | --- |  | 3200 | LB | ---
| Reserves other than University | 509 | N | --- |  | 509 | N | ---
Registration Fees (N)
| Regents' Appropriation (U) | --- |  | --- |  | --- |  | ---
| Other (X) | 175 | X | --- |  | 175 | X | ---
| TOTAL | 4751 |  | --- |  | 4751 |  | ---

## Santa Cruz
SANTA CRUZ CAMPUS
1987-88 NON-STATE CAPITAL BUDGET
($000)
[8 empty] | C U R R E N T S T A T U S | [7 empty] | PRIOR ACTION/COMMENTS
|  | Project | [8 empty] | Beyond |  |  |  | Approval
| Project | Cost |  |  | Prefunded |  |  | 1987-88 |  |  | 1987-88 |  | Action |  | Letter | Date | Action | Cost
A. | Applied Sciences Parking Lot | 233 | N |  | --- |  | P | 7 | N |  | --- |  | 10/87 | Admin | 10/30/87
| Expansion (976540) | [5 empty] | W | 8 | N
[7 empty] | C | 218 | N
233
B. | Academic Office and Laboratory | 986 | U |  | --- |  | P | 48 | U |  | --- |  | 1/88 | Admin | 1/25/88
| Expansion (970860) | [5 empty] | W | 58 | U
[7 empty] | C | 834 | U
[7 empty] | E | 46 | U
986
C. | College Eight Housing, Phase 1 | 16064 | LB | P | 530 | LB | P | 10 | X | C | 184 | N | 7/89 | Admin | 7/26/89 | 9/86 | 1986-89 CIP | 15161
| (976280) | 384 | N | W | 500 | LB | W | 30 | X | [6 empty] | 9/87 | 1986-89 CIP | 16388
|  | 1024 | X | C | 13789 | LB | C | 460 | X | [6 empty] | 6/88 | 1986-89 & 1987-90 CIP | 16888
|  | 17472 |  | C | 200 | N | C | 400 | LB | [6 empty] | 12/88 | 1988-91 CIP | 17288
|  |  |  | C | 524 | X |  | 900
|  |  |  | E | 845 | LB
16388
D. | Fume Hood VAV System Applied | 330 | X |  | --- |  | P | 26 | X |  | --- |  | 7/88 | Admin | 7/14/88
| Sciences (Energy Conservation | [5 empty] | W | 34 | X
| Demonstration Project) (976024) | [5 empty] | C | 270 | X
330
| Bank Loans or Bonds (LB) | 16064 | LB |  | 15664 | LB |  | 400 | LB |  | ---
Reserves other than University
| Registration Fees (N) | 617 | N |  | 200 | N |  | 233 | N |  | 184 | N
| Regents Appropriation (U) | 986 | U |  | --- |  |  | 986 | U |  | ---
| Other (X) | 1354 | X |  | 524 | X |  | 830 | X |  | ---
| TOTAL | 19021 |  |  | 16388 |  |  | 2449 |  |  | 184

## ANR
OFFICE OF THE PRESIDENT
AGRICULTURE AND NATURAL RESOURCES
1987-88 NON-STATE CAPITAL BUDGET
($000)
[6 empty] | C U R R E N T S T A T U S | [5 empty] | PRIOR ACTION/COMMENTS
|  | Project | [5 empty] | Beyond |  |  | Approval
| Project | Cost |  | Prefunded |  | 1987-88 |  | 1987-88 | Action |  | Letter | Date | Action | Cost
A. | Cooperative Extension Office, | 141 | G | --- | P | 61 | X | --- | 6/88 | Admin | 6/6/88
| Imperial Valley (930700) | 230 | LR |  | W | 50 | X
|  | 179 | U |  | C | 79 | X
|  | 190 | X |  | C | 179 | U
|  | 740 |  |  | C | 141 | G
[5 empty] | C | 230 | LR
740
| Gifts (G) | 141 | G | --- |  | 141 | G | ---
| Regents' Loans (LR) | 230 | LR | --- |  | 230 | LR | ---
| Regents' Appropriations (U) | 179 | U | --- |  | 179 | U | ---
| Other (X) | 190 | X | --- |  | 190 | X | ---
| TOTAL | 740 |  | --- |  | 740 |  | ---

## LBL
LAWRENCE BERKELEY LABORATORY
1987-88 NON-STATE CAPITAL BUDGET
($000)
[6 empty] | C U R R E N T S T A T U S | [5 empty] | PRIOR ACTION/COMMENTS
|  | Project | [5 empty] | Beyond |  |  | Approval
| Project | Cost |  | Prefunded |  | 1987-88 |  | 1987-88 | Action |  | Letter | Date | Action | Cost
A. | Advanced Light Source | 2640 | F | --- | P | 90 | F | --- | 12/87 | Admin | 12/3/87
| Improvements, Building 6 |  |  |  | W | 110 | F
[5 empty] | C | 2440 | F
2640
| Federal Funds (F) | 2640 | F | --- |  | 2640 | F | ---
| TOTAL | 2640 |  | --- |  | 2640 |  | ---

## UCOP
OFFICE OF THE PRESIDENT
1987-88 NON-STATE CAPITAL BUDGET
($000)
[6 empty] | C U R R E N T S T A T U S | [5 empty] | PRIOR ACTION/COMMENTS
|  | Project | [5 empty] | Beyond |  |  | Approval
| Project | Cost |  | Prefunded |  | 1987-88 |  | 1987-88 | Action |  | Letter | Date | Action | Cost
A. | UC Press Building Renovations, | 304 | X | --- | P | 15 | X | --- | 7/88 | Admin | 7/5/88
| Phase 2 (912588) |  |  |  | W | 25 | X
[5 empty] | C | 254 | X
[5 empty] | C | 10 | X
304
| Other (X) | 304 | X | --- |  | 304 | X | ---
| TOTAL | 304 |  | --- |  | 304 |  | ---

## Summary
1987-88 NON-STATE FUNDED PROJECTS
($ in thousands)
| UCB | UCD | UCI | UCLA | UCR | UCSD | UCSF | UCSB | UCSC | OTHER | TOTAL
Federal (F) | - - - | - - - | - - - | 137 | - - - | - - - | 519 | 867 | - - - | 2640 | 4163
Gifts (G) | 29600 | - - - | 1823 | 29971 | - - - | 8751 | 2150 | - - - | - - - | 141 | 72436
Hospital Reserves (HR) | - - - | 3280 | - - - | 34837 | - - - | 1953 | 7440 | - - - | - - - | - - - | 47510
Bank Loans or Bonds (LB) | 65210 | 31945 | 42672 | 113595 | - - - | 20708 | - - - | 3200 | 400 | - - - | 277730
Reserves Other Than University
Registration Fees (N) | 4018 | 5799 | 1717 | 9241 | - - - | 13 | - - - | 509 | 233 | - - - | 21530
Funds From Sources Yet To Be
Determined (Q) | - - - | - - - | - - - | - - - | - - - | - - - | - - - | - - - | - - - | - - -
Registration Fees (R) | - - - | 1200 | - - - | - - - | - - - | - - - | - - - | - - - | - - - | - - - | 1200
Regents' Appropriations (U) | 1575 | 15 | 1436 | 1000 | - - - | 4000 | - - - | - - - | 986 | 179 | 9191
Regents' Loans (LR) | - - - | - - - | - - - | - - - | - - - | - - - | - - - | - - - | - - - | 230 | 230
Other (X) | 3341 | 976 | 2600 | 14276 | 1200 | 15495 | 11059 | 175 | 830 | 494 | 50446
TOTAL | 103744 | 43215 | 50248 | 203057 | 1200 | 50920 | 21168 | 4751 | 2449 | 3684 | 484436