## Berkeley
BERKELEY CAMPUS
1989-90 NON-STATE CAPITAL BUDGET
(000)
C U R R E N T S T A T U S
|  |  | Project | [8 empty] | Beyond |  |  |  | Approval
| Project |  | Cost |  |  | Prefunded |  |  | 1989-90 |  |  | 1989-90 |  | Action |  | Letter | Date | Action | Cost
A. | Etcheverry Hall Reactor |  | 625 | U | P | 250 | U | C | 1100 | X |  | - - - |  | 6/90 | Admin | 6/26/90 | 8/87 | 1987-90 CIP | 1750
| Decommissioning & Removal |  | 1725 | X | W | 250 | U
| (912536) |  | 2350 |  | C | 125 | U
[5 empty] | C | 625 | X
1250
B | Seismic Safety Corrections, |  | 6157 | LB |  | - - - |  | P | 262 | LB | C | 80 | LB | 6/93 | Admin | 6/23/93 | 5/90 | 1987-90 CIP | 8200
| University Hall (912585) | [6 empty] | W | 489 | LB
[8 empty] | C | 5326 | LB
6077
C | Intercollegiate Athletics Facilities |  | 4260 | G |  | - - - |  | P | 100 | G |  | - - - |  | 10/90 | Admin | 10/31/90
| Step 2 (912560) | [6 empty] | W | 200 | G
[8 empty] | C | 3800 | G
[8 empty] | E | 160 | G
4260
D. | UC Berkeley University House |  | 998 | LB |  | - - - |  | P | 55 | LB | P | 4 | LB | 5/92 | Admin | 5/12/92 | 10/90 | 1989-92 CIP | 850
| Seismic Safety Corrections | [6 empty] | W | 75 | LB | W | 54 | LB
| (912627) | [6 empty] | C | 720 | LB | C | 90 | LB
[9 empty] | 850 |  |  | 148
E. | Life Sciences Building Renovation | ( | 48199 | ) | (P | 938 | ) | (C | 34976 | ) | (C | 6090 | ) | 1/94 | Regents' | 3/30/94 | 10/85 | 1986-89 CIP | 62357
| for Ecology and Evolutionary |  | 24049 | G | P | 1626 | G | C | 17488 | G | C | 3045 | G |  | Admin |  | 11/86 | 1987-90 CIP | 62357
| Biology (912274) |  | 19083 | X | P | 85 | X |  | 52464 |  | (E | 3592 | ) |  |  |  | 11/87 | 1988-91 CIP | 67746
|  |  | 91331 |  | (W | 2603 | ) |  |  |  | E | 1796 | G |  |  |  | 11/88 | 1989-92 CIP | 69547
[5 empty] | W | 94 | G |  |  |  | C | 18179 | X |  |  |  | 11/89 | 1990-93 CIP | 69936
[5 empty] | W | 69 | X |  |  |  |  | 32702 |  |  |  |  | 10/90 | 1991-94 CIP | 70035
[5 empty] | C | 750 | X | [9 empty] | 11/91 | 1992-95 CIP | 70080
[6 empty] | 6165 | [10 empty] | 10/92 | 1993-96 CIP | 73152
| Gifts Funds (G) |  | 28309 | G |  | 1720 | G |  | 21748 | G |  | 4841 | G
| Bank Loans or Bonds (LB) |  | 7155 | LB |  | - - - |  |  | 6927 | LB |  | 228 | LB
| Regents Appropriations (U) |  | 625 | U |  | 625 | U |  | - - - |  |  | - - -
| Other - Campus Funds (X) |  | 20808 | X |  | 1529 | X |  | 1100 | X |  | 18179 | X
| TOTAL |  | 56897 |  |  | 3874 |  |  | 29775 |  |  | 23248
| STATE FUNDS | ( | 48199 | ) | ( | 938 | ) | ( | 34976 | ) | ( | 9682 | )

## Davis
DAVIS CAMPUS
1989-90 NON-STATE CAPITAL BUDGET
($000)
[7 empty] | C U R R E N T S T A T U S | [8 empty] | PRIOR ACTION/COMMENTS
|  | Project | [8 empty] | Beyond |  |  |  | Approval
| Project | Cost |  |  | Prefunded |  |  | 1989-90 |  |  | 1989-90 |  | Action |  | Letter | Date | Action | Cost
A. | Lawrence Livermore Laboratory | 300 | R |  | --- |  | P | 5 | R |  | --- |  | 7/89 | Admin | 7/11/89
| Student Center (931410) | [5 empty] | W | 30 | R
[7 empty] | C | 265 | R
300
B. | Crocker Nuclear Laboratory Air | 317 | X |  | --- |  | P | 17 | X |  | --- |  | 7/89 | Admin | 7/19/89
| Quality Annex (931280) | [5 empty] | W | 23 | X
[7 empty] | C | 277 | X
317
C. | Alumni and Visitors Center | 3797 | G |  | --- |  | P | 226 | X |  | --- |  | 5/90 | Admin | 5/14/90
| (930960) | 1000 | X |  |  |  | W | 218 | X
|  | 4797 |  |  |  |  | C | 556 | X
[7 empty] | C | 3524 | G
[7 empty] | E | 273 | G
4797
D. | Engineering Modular Office | 950 | X |  | --- |  | P | 15 | X |  | --- |  | 3/90 | Admin | 3/8/90 | 11/89 | 1989-92 CIP | 800
| Complex (931460) | [5 empty] | W | 22 | X
[7 empty] | C | 913 | X
950
E. | Modular Office Complex (931480) | 241 | X |  | --- |  | P | 4 | X |  | --- |  | 11/90 | Admin | 11/29/90 | 11/89 | 1989-92 CIP | 225
[7 empty] | W | 8 | X
[7 empty] | C | 229 | X
241
F. | Academic Surge Building (930740) | 11235 | LB |  | --- |  | P | 493 | X |  | --- |  | 3/90 | Regents | 5/8/90
|  | 3765 | X |  |  |  | W | 512 | X
|  | 15000 |  |  |  |  | C | 2760 | X
[7 empty] | C | 11235 | LB
15000
G. | Mrak Hall Alterations (931470) | 2422 | X |  | --- |  | P | 133 | X |  | --- |  | 5/90 | Admin | 5/14/90
[7 empty] | W | 157 | X
[7 empty] | C | 2132 | X
2422
H. | California Primate Research Center | 677 | F |  | --- |  | P | 20 | F |  | --- |  | 8/90 | Admin | 8/6/90
| Modular Animal Building (935060) | [5 empty] | W | 52 | F
[7 empty] | C | 605 | F
677
I. | Veterinary Medical Clinical | 237 | N |  | --- |  | P | 20 | N |  | --- |  | 11/90 | Admin | 11/8/90 | 7/89 | 1989-92 CIP | 237
| Teaching Facility Modular Office | 103 | G |  |  |  | W | 35 | N
| Building (934940) | 340 |  |  |  |  | C | 182 | N
[7 empty] | C | 103 | G
340
J. | Sproul Hall Seismic Upgrade | 4900 | LB |  | --- |  | P | 200 | LB | C | 650 | X | 1/93 | Admin | 1/7/93 | 7/90 | 1989-92 CIP | 4900
| (938706) | 650 | X |  |  |  | W | 335 | LB
|  | 5550 |  |  |  |  | C | 4365 | LB
4900
K. | Seismic Upgrade--Segundo | 440 | N |  | --- |  | P | 14 | N |  | --- |  | 4/91 | Admin | 4/11/91
| Residence Halls (938705) | [5 empty] | W | 17 | N
[7 empty] | C | 409 | N
440
L. | Struve Residence Hall Seismic | 568 | N |  | --- |  | P | 35 | N |  | --- |  | 4/91 | Admin | 4/11/91
| Upgrade (938707) | [5 empty] | W | 40 | N
[7 empty] | C | 493 | N
568
M. | UCDMC Cancer Center Building | 100 | G | P | 474 | LB | C | 1463 | HR |  | --- |  | 9/89 | Admin | 9/13/89 | 3/87 | 1986-89 CIP | 9909
| (934830) | 11748 | LB | W | 728 | LB | [9 empty] | 7/88 | 1987-91 CIP | 11848
|  | 1463 | HR | C | 100 | G
|  | 13311 |  | C | 9528 | LB
|  |  |  | E | 1018 | LB
11848
N. | NO PROJECT
O. | School of Medicine Research Building | 8771 | LB | P | 430 | LB | C | 7271 | LB |  | --- |  | 9/90 | Admin | 9/18/90 | 7/88 | 1988-91 CIP | 7404
| (934800) |  |  | W | 620 | LB | E | 450 | LB
[5 empty] | 1050 |  |  | 7721
P. | Bookstore Warehouse Addition | 500 | LB |  | --- |  | P | 20 | LB |  | --- |  | 7/89 | Admin | 7/21/89
| (931260) | 100 | X |  |  |  | W | 39 | LB
|  | 600 |  |  |  |  | C | 441 | LB
[7 empty] | E | 100 | X
600
Q. | UCDMC Sacramento Ambulatory | 4196 | HR | P | 145 | HR | C | 605 | HR |  | --- |  | 9/89 | Admin | 9/8/89 | 10/86 | 1986-89 CIP | 3591
| Care Support Unit (934740) |  |  | W | 323 | HR
|  |  |  | C | 2732 | HR
|  |  |  | E | 391 | HR
3591
| Federal Funds (F) | 677 | F |  | --- |  |  | 677 | F |  | ---
| Gift Funds (G) | 4000 | G |  | 100 | G |  | 3900 | G |  | ---
| Hospital Reserve Funds (HR) | 5659 | HR |  | 3591 | HR |  | 2068 | HR |  | ---
| Bank Loans or Bonds (LB) | 37154 | LB |  | 12798 | LB |  | 24356 | LB |  | ---
Reserves other than University
| Registration Fees (N) | 1245 | N |  | --- |  |  | 1245 | N |  | ---
University Registration Fee
| Reserves (R) | 300 | R |  | --- |  |  | 300 | R |  | ---
| Other (X) | 9445 | X |  | --- |  |  | 8795 | X |  | 650 | X
| TOTAL | 58480 |  |  | 16489 |  |  | 41341 |  |  | 650

## Irvine
IRVINE CAMPUS
1989-90 NON-STATE CAPITAL BUDGET
($000)
[6 empty] | C U R R E N T S T A T U S | [7 empty] | PRIOR ACTION/COMMENTS
|  | Project | [6 empty] | Beyond |  |  |  | Approval
| Project | Cost |  | Prefunded |  | 1989-90 |  |  | 1989-90 |  | Action |  | Letter | Date | Action | Cost
A. | Group Housing and Parking | 24850 | LB | --- | P | 786 | LB |  | --- |  | 11/89 | Regents | 8/28/90
| (996355) |  |  |  | W | 961 | LB
[5 empty] | C | 23103 | LB
24850
B. | Parking and Transportation | 12251 | LB | --- | P | 332 | LB | P | 62 | LB | 1/91 | Regents | 5/23/91 | 6/90 | 1989-92 CIP | 10500
| Improvements, Step 4 |  |  |  | W | 406 | LB | W | 74 | LB
| (996540) |  |  |  | C | 9762 | LB | C | 1615 | LB
[6 empty] | 10500 |  |  | 1751
C. | University House Infrastructure | 1000 | X | --- | P | 40 | X |  | --- |  | 10/90 | Admin | 10/31/90
| (996090) |  |  |  | W | 60 | X
[5 empty] | C | 900 | X
1000
D. | Seismic Hazard Mitigation Program | 820 | LB | --- | P | 25 | LB |  | --- |  | 1/90 | Regents | 7/13/90
| (998710) |  |  |  | W | 41 | LB
[5 empty] | C | 754 | LB
820
E. | UCI Medical Center, Neurosciences | 660 | HR | --- | P | 43 | HR | C | 344 | HR | 4/91 | Admin | 4/23/91
| Intensive Care Unit (994410) |  |  |  | W | 198 | HR | C | 75 | HR
[6 empty] | 241 |  |  | 419
| Hospital Reserve Funds (HR) | 660 | HR | --- |  | 241 | HR |  | 419 | HR
| Bank Loans or Bonds (LB) | 37921 | LB | --- |  | 36170 | LB |  | 1751 | LB
| Other (X) | 1000 | X | --- |  | 1000 | X |  | ---
| TOTAL | 39581 |  | --- |  | 37411 |  |  | 2170

## Los Angeles
LOS ANGELES CAMPUS
1989-90 NON-STATE CAPITAL BUDGET
($000)
[9 empty] | C U R R E N T S T A T U S | [7 empty] | PRIOR ACTION/COMMENTS
|  |  | Project | [8 empty] | Beyond |  |  |  | Approval
| Project |  | Cost |  |  | Prefunded |  |  | 1989-90 |  |  | 1989-90 |  | Action |  | Letter | Date | Action | Cost
A. | UCLA Medical Center, 7th Floor |  | 3881 | HR | P | 118 | HR | P | 207 | HR |  | --- |  | 7/89 | Admin | 8/14/89 | 11/85 | 1985-88 CIP | 8766
| Neurosurgery Intensive Care Unit |  |  |  | W | 192 | HR | W | 226 | HR | [6 empty] | 8/87 | 1987-90 CIP | 2802
| Alterations (Formerly: 7th and 8th |  |  |  | C | 2536 | HR | C | 602 | HR
| Floor Alterations UCLA Medical |  |  |  |  | 2846 |  |  | 1035
Center) (945030)
B. | UCLA Medical Center, Gift Shop |  | 510 | HR | P | 68 | HR | C | 150 | HR |  | 55 | HR | 11/90 | Admin | 11/9/90 | 8/87 | 1987-90 CIP | 438
| Alterations (945100) |  |  |  | W | 104 | HR | [9 empty] | 9/89 | 1989-91 CIP | 455
[5 empty] | C | 133 | HR
305
C. | UCLA Medical Center, Main |  | 26100 | HR | P | 2280 | HR | C | 35000 | LB | C | 9685 | HR | 9/92 | Admin | 9/29/92 | 9/86 | 1986-89 CIP | 26540
| Operating Room Suite Expansion |  | 35000 | LB | W | 5244 | HR | [9 empty] | 7/87 | 1987-90 CIP | 36600
| (Formerly: Medical Center |  | 61100 |  | C | 8891 | HR | [9 empty] | 9/89 | 1989-92 CIP | 51415
| Operating Room #10 Expansion) |  |  |  |  | 16415 | [10 empty] | 3/91 | 1990-93 CIP | 59002
(944880)
D. | Earth and Space Sciences |  | 676 | X |  | --- |  | P | 28 | X |  | --- |  | 10/89 | Admin | 10/19/89
| Laboratory Alteration (943020) | [6 empty] | W | 33 | X
[8 empty] | C | 615 | X
676
E. | Reed Neurological Research |  | 2504 | X | S | 50 | X | P | 103 | X | C | 80 | G | 8/90 | Admin | 8/29/90 | 11/89 | 1989-92 CIP | 2504
| Center B-Level Neurology |  | 80 | G |  |  |  | W | 152 | X
| Laboratory Alterations (945280) |  | 2584 |  |  |  |  | C | 2199 | X
2454
F. | Westwood Plaza/LeConte Avenue |  | 30 | N |  | --- |  | S | 30 | N |  | --- |  | 4/91 | Admin | 4/4/91
| Entrance (946092) |  | 800 | X |  |  |  | S | 50 | X
|  |  | 2270 | LB |  |  |  | P | 180 | X
|  |  | 3100 |  |  |  |  | W | 180 | X
[8 empty] | C | 2270 | LB
[8 empty] | C | 390 | X
3100
G. | Health Sciences Bldg. 6th Floor |  | 1406 | X |  | --- |  | P | 108 | X | C | 61 | X | 5/92 | Admin | 5/12/92 | 11/89 | 1989-92 CIP | 1236
| Anatomy & Cell Biology Laboratory | [6 empty] | W | 152 | X | [6 empty] | 11/90 | 1990-93 CIP | 1345
| Alterations (945420) | [6 empty] | C | 1085 | X
1345
H. | Patient Family Guest House |  | 88 | HR | P | 88 | HR | P | 294 | LB |  | --- |  | 11/89 | Regents | 2/7/90
| (945260) |  | 13342 | LB |  |  |  | W | 509 | LB
|  |  | 13430 |  |  |  |  | C | 11839 | LB
[8 empty] | E | 700 | LB
13342
I. | North Campus Interim Staging |  | 2220 | LB |  | --- |  | P | 80 | LB |  | --- |  | 6/91 | Admin | 6/13/91 | 9/90 | 1989-92 CIP | 587
| Facility Site Work (946056) | [6 empty] | W | 146 | LB | [6 empty] | Original project deleted (see "H" in
[8 empty] | C | 1463 | LB | [6 empty] | 1988-89) and replaced by this project.
[8 empty] | E | 531 | LB
2220
J. | UCLA Medical Center HSB Medical |  | 1851 | HR | P | 25 | HR | P | 197 | HR |  | --- |  | 6/90 | Admin | 6/12/90
| Gas System Alterations (946218) | [6 empty] | W | 254 | HR
[8 empty] | C | 1375 | HR
1826
K. | East Melnitz Building (942490) |  | 355 | X |  | --- |  | P | 195 | X | C | 175 | LB | 9/92 | Admin | 9/24/92 | 5/90 | 1989-92 CIP | 4025
|  |  | 3845 | LB |  |  |  | W | 160 | X
|  |  | 4200 |  |  |  |  | C | 3155 | LB
[8 empty] | E | 515 | LB
4025
L. | Science and Technology Research |  | 45000 | LB |  | --- |  |  | --- |  | P | 2913 | LB | 9/95 | Admin | 9/21/95 | 3/90 | 1989-92 CIP | 55775
| Building (942030) | [9 empty] | W | 2321 | LB |  |  |  | 5/93 | 1992-95 CIP | 47794
[11 empty] | C | 34766 | LB
[11 empty] | E | 5000 | LB
45000
M. | UCLA Medical Center 2nd Floor |  | 595 | HR |  | --- |  | P | 51 | HR | W | 10 | HR | 8/90 | Admin | 8/28/90
| Fertility Center (945620) | [6 empty] | W | 59 | HR | C | 475 | HR
[9 empty] | 110 |  |  | 485
N. | UCLA Medical Center A-Level |  | 1026 | HR |  | --- |  | P | 104 | HR | C | 789 | HR | 9/90 | Admin | 9/18/90
| Respiratory Therapy Alterations | [6 empty] | W | 133 | HR
| (945600) | [7 empty] | 237
O. | UCLA Medical Center Health |  | 4600 | HR |  | --- |  | P | 183 | HR | W | 235 | HR | 4/91 | Admin | 4/4/91
| Science Building, 4th Floor | [6 empty] | W | 114 | HR | C | 4068 | HR
| Medical/Surgical Intensive Care | [7 empty] | 297 |  |  | 4303
Unit Alterations (945610)
P. | Northwest Housing and Parking, |  | 81486 | LB | P | 3220 | LB | P | 170 | G |  | --- |  | 11/90 | Regents | 11/29/90 | 7/88 | 1987-90 CIP | 62137
| Phase 1 (946505) |  | 3869 | G | W | 3000 | LB | W | 190 | G | [6 empty] | 9/88 | 1987-90 & 1988-91 CIP | 73300
|  |  | 440 | X | C | 75266 | LB | C | 3509 | G | [6 empty] | 3/89 | 1988-91 CIP | 77169
|  |  | 85795 |  |  | 81486 |  | C | 440 | X
4309
Q. | UCLA Medical Center, CHS |  | 2071 | HR | P | 217 | HR | C | 168 | HR |  | --- |  | 1/91 | Admin | 1/10/91 | 7/88 | 1987-90 CIP | 1611
| Non-Invasive Cardiology |  |  |  | W | 279 | HR | [9 empty] | 4/89 | 1989-92 CIP | 1903
| Alterations (944500) |  |  |  | C | 1407 | HR
1903
R. | UCLA Medical Center Pediatric |  | 1334 | HR | P | 82 | HR | W | 11 | HR |  | --- |  | 1/89 | Admin | 1/5/89
| Catheterization Laboratory |  |  |  | W | 147 | HR | C | 1094 | HR
| Alterations (945290) |  |  |  |  | 229 |  |  | 1105
S. | UCLA Medical Center Mark Taper |  | 310 | HR | P | 34 | HR | C | 55 | HR |  | --- |  | 11/90 | Admin | 11/29/90 | 3/89 | 1986-89 CIP | 250
| Center for Health Enhancement |  |  |  | W | 44 | HR | [9 empty] | 6/90 | 1989-92 CIP | 290
| Radiological Science Site |  |  |  | C | 177 | HR
| Improvements (945360) |  |  |  |  | 255
T. | CHS Fourth Floor West Special |  | 565 | HR | P | 29 | HR | W | 18 | HR |  | --- |  | 8/90 | Admin | 8/16/90 | 7/88 | 1987-90 CIP | 415
| Procedures (945170) |  |  |  | W | 82 | HR | C | 132 | HR
[5 empty] | C | 304 | HR |  | 150
415
U. | School of Dentistry Venice |  | 148 | G | P | 25 | X | W | 8 | X |  | --- |  | 5/90 | Admin | 5/24/90 | 7/88 | 1988-91 CIP | 521
| Community Dental Expansion |  | 418 | X | W | 27 | X | C | 358 | X
| (945160) |  | 566 |  |  | 52 |  | C | 148 | G
514
V. | Anderson Graduate School of |  | 26466 | G | P | 2670 | G | ( W | 1315 | ) | ( C | 25826 | ) | 11/96 | Admin | pending | 1/88 | 1987-90 CIP | 67234
| Management (942500) | ( | 27141 | ) |  |  |  | W | 2950 | G | C | 17939 | G |  | (Finance Action) |  | 11/88 | 1989-92 CIP | 59266
|  |  | 593 | X |  |  |  |  | 4266 |  | C | 593 | X |  |  |  | 11/89 | 1990-93 CIP | 65840
|  |  | 27200 | LB | [6 empty] | C | 27200 | LB |  |  |  | 3/91 | 1990-93 CIP | 67692
|  |  | 81400 | [7 empty] | E | 2907 | G |  |  |  | 6/95 | 1994-97 CIP | 79290
74465
W. | Powell Library Seismic Renovation | ( | 35228 | ) | S | 271 | U | ( P | 1542 | ) | ( W | 1951 | ) | 9/92 | State | N/A | 11/87 | 1988-91 CIP | 29030
| (942510) |  | 271 | U | [6 empty] | ( C | 31735 | ) |  | Budget Act |  | 11/88 | 1989-92 CIP | 34547
|  |  | 35499 | [8 empty] | 33686 |  |  |  |  | 11/89 | 1990-93 CIP | 35692
[17 empty] | 10/90 | 1991-94 CIP | 36007
| Federal Funds (F) |  | --- |  |  | --- |  |  | ---
| Gift Funds (G) |  | 44649 | G |  | 2670 | G |  | 6968 | G |  | 35011 | G
| Hospital Reserves (HR) |  | 42931 | HR |  | 22481 | HR |  | 5133 | HR |  | 15317 | HR
| Bank Loans or Bonds (LB) |  | 210363 | LB |  | 81486 | LB |  | 56502 | LB |  | 72375 | LB
Reserves Other Than University
| Registration Fees (N) |  | 30 | N |  | --- |  |  | 30 | N |  | ---
| Other (X) |  | 6599 | X |  | 102 | X |  | 6436 | X |  | 61 | X
| Regents' Appropriations (U) |  | 271 | U |  | 271 | U |  | - - - |  |  | - - -
| TOTAL |  | 304843 |  |  | 107010 |  |  | 75069 |  |  | 122764
| STATE FUNDS | ( | 62368 | ) | ( | --- | ) | ( | 2857 | ) | ( | 59511 | )

## Riverside
RIVERSIDE CAMPUS
1989-90 NON-STATE CAPITAL BUDGET
($000)
[9 empty] | C U R R E N T S T A T U S | [7 empty] | PRIOR ACTION/COMMENTS
|  |  | Project | [8 empty] | Beyond |  |  |  | Approval
| Project |  | Cost |  |  | Prefunded |  |  | 1989-90 |  |  | 1989-90 |  | Action |  | Letter | Date | Action | Cost
A. | Bell Tower Seismic Upgrade |  | 1243 | LB |  | --- |  | P | 34 | LB |  | --- |  | 7/90 | Admin | 7/13/90
| (958711) | [6 empty] | W | 57 | LB
[8 empty] | C | 1152 | LB
1243
B. | Physics Colonnade Seismic |  | 260 | LB |  | --- |  | P | 8 | LB |  | --- |  | 7/90 | Admin | 7/13/90
| Upgrade (958712) | [6 empty] | W | 13 | LB
[8 empty] | C | 239 | LB
260
C. | Interim Facilities Phase I |  | 2000 | X |  | --- |  | P | 40 | X |  | --- |  | 9/90 | Admin | 9/18/90
| (950382) | [6 empty] | W | 64 | X
[8 empty] | C | 1896 | X
2000
D. | Central Utility Plant Boiler Renewal, |  | 244 | U |  | --- |  | P | 68 | U | P | 25 | U | 10/90 | Regents' | N/A | 11/89 | 1990-93 CIP | 2517
| Phase 2 (950371) | ( | 3268 | ) |  |  |  | W | 111 | U | W | 40 | U |  | Budget
|  |  | 3512 | [5 empty] | 179 |  | ( C | 3268 | )
3333
E. | California Museum of Photography |  | 1930 | G | P | 37 | G | C | 455 | G |  | --- |  | 1/91 | Admin | 1/23/91 | 9/86 | 1986-89 CIP | 1320
| (Formerly: Renovation of Kress |  |  |  | W | 62 | G | [9 empty] | 7/88 | 1988-91 CIP | 1475
| Building for California Museum of |  |  |  | C | 1376 | G
| Photography #958831) (950363) |  |  |  |  | 1475
| Gifts (G) |  | 1930 | G |  | 1475 | G |  | 455 | G |  | ---
| Bank Loans or Bonds (LB) |  | 1503 | LB |  | --- | LB |  | 1503 | LB |  | --- | LB
Reserves other than University
| Registration Fee (N) |  | --- |  |  | --- |  |  | --- |  |  | ---
| Regents' Appropriations (U) |  | 244 | U |  | --- |  |  | 179 | U |  | 65 | U
| Other (X) |  | 2000 | X |  | --- |  |  | 2000 | X |  | ---
| TOTAL |  | 5677 |  |  | 1475 |  |  | 4137 |  |  | 65
| STATE FUNDS | ( | 3268 | ) | ( | --- | ) | ( | --- | ) | ( | 3268 | )

## San Diego
SAN DIEGO CAMPUS
1989-90 NON-STATE CAPITAL BUDGET
($000)
[9 empty] | C U R R E N T S T A T U S | [7 empty] | PRIOR ACTION/COMMENTS
|  |  | Project | [8 empty] | Beyond |  |  |  | Approval
| Project |  | Cost |  |  | Prefunded |  |  | 1989-90 |  |  | 1989-90 |  | Action |  | Letter | Date | Action | Cost
A. | UCSD Medical Center, Outpatient |  | 4118 | LB |  | --- |  | P | 125 | LB | P | 22 | LB | 7/92 | Admin | 7/21/92 | 10/89 | 1989-92 CIP | 3584
| Center Renovations and Cardiac | [6 empty] | W | 324 | LB | W | 281 | LB
| Catheterization Suite (965060) | [6 empty] | C | 3135 | LB | C | 231 | LB
[9 empty] | 3584 |  |  | 534
B. | Central Utility Plant Condensate |  | 725 | X |  | --- |  | P | 25 | X |  | --- |  | 10/89 | Admin | 10/25/89
| and De-aerator System | [6 empty] | W | 35 | X
| Replacement (966064) | [6 empty] | C | 665 | X
725
C. | Campus Services Complex, Phase 1 |  | 4357 | LB |  | --- |  | P | 146 | LB |  | --- |  | 5/90 | Admin | 5/22/90
| (962010) | [6 empty] | W | 188 | LB
[8 empty] | C | 4023 | LB
4357
D. | UCSDMC Coronary Care Unit |  | 2460 | LB |  | --- |  | P | 44 | LB |  | --- |  | 5/90 | Admin | 5/14/90
| Expansion and Renovation | [6 empty] | W | 226 | LB
| (965100) | [6 empty] | C | 2190 | LB
2460
E. | Revelle Electrical Capacity |  | 779 | X |  | --- |  | P | 20 | X |  | --- |  | 4/90 | Admin | 5/7/90
| Improvements (961990) | [6 empty] | W | 45 | X
[8 empty] | C | 714 | X
779
F. | Institute for Geophysics and |  | 1962 | G |  | --- |  | P | 238 | G | C | 960 | X | 12/94 | Admin | 12/21/94 | 3/90 | 1989-92 CIP | 7149
| Planetary Physics Building, Unit 2 |  | 4624 | LB |  |  |  | W | 306 | G | C | 51 | G |  |  |  | 4/90 | 1989-92 CIP | 7356
| (962040) |  | 1208 | X |  |  |  | C | 1367 | G | C | 53 | LB |  |  |  | 9/92 | 1992-95 CIP | 7660
|  |  | 7794 |  |  |  |  | C | 4571 | LB | E | 248 | X |  |  |  | 5/93 | 1992-95 CIP | 7476
[9 empty] | 6482 |  |  | 1312
G. | Molecular Biology Research |  | 29355 | LB |  | --- |  |  | --- |  | P | 979 | X | 5/93 | Interim | 6/16/93 | 3/90 | 1989-92 CIP | 28825
| Facility Unit 3 (962050) |  | 3208 | X | [6 empty] | W | 1259 | X |  |  |  | 3/90 | 1989-92 CIP | 31593
|  |  | 32563 | [7 empty] | C | 970 | X
[11 empty] | C | 27180 | LB
[11 empty] | E | 2175 | LB
32563
H. | UCSDMC Eleventh Operating |  | 1200 | LB |  | --- |  | P | 48 | LB |  | --- |  | 5/93 | Admin | 5/15/93 | 9/90 | 1989-92 CIP | 1200
| Room (965150) | [6 empty] | W | 139 | LB |  |  |  |  | (Revised scope)
[8 empty] | C | 1013 | LB
1200
I. | Early Childhood Education Center |  | 1654 | LB |  | --- |  | P | 48 | LB |  | --- |  | 9/90 | Admin | 9/18/90
| (962020) | [6 empty] | W | 120 | LB
[8 empty] | C | 1471 | LB
[8 empty] | E | 15 | LB
1654
J. | Galbraith Hall Reinforcement |  | 1997 | LB |  | --- |  | P | 66 | LB | W | 25 | LB | 8/93 | Admin | 8/13/93 | 7/90 | 1989-92 CIP | 1440
| (968716) |  | 330 | X |  |  |  | W | 56 | LB | C | 532 | LB |  |  |  | 9/91 | 1991-94 CIP | 1840
|  |  | 2327 |  |  |  |  | C | 1318 | LB | C | 330 | X |  |  |  | 6/92 | 1991-94 CIP | 2250
[9 empty] | 1440 |  |  | 887
K. | UCSD Medical Center Inpatient |  | 2076 | HR | P | 362 | HR | ( C | 1778 | ) | C | 2622 | LB | 2/94 | Admin | 2/2/94 | 5/86 | 1985-88 & 1986-89 CIP | 29450
| Tower Completion and |  | 2622 | LB | ( P | 511 | ) |  |  |  | C | 1530 | HR |  |  |  | 11/87 | 1988-91 CIP | 32301
| Modernization Project (964950) |  | 105 | G | ( W | 1196 | ) |  |  |  | C | 105 | G |  |  |  | 1/90 | 1989-92 CIP | 34079
|  | ( | 33717 | ) | ( C | 30232 | ) |  |  |  | E | 184 | HR |  |  |  | 12/92 | 1992-95 CIP | 36701
|  |  | 38520 |  |  | 32301 | [5 empty] | 4441
L. | Molecular Biology Research |  | 12473 | X | P | 300 | X | C | 1178 | X |  | --- |  | 10/90 | Admin | 10/18/90 | 9/85 | 1985-88 CIP | 11310
| Facility, Unit II (961490) |  |  |  | W | 400 | X | [9 empty] | 1/88 | 1987-90 CIP | 11295
[5 empty] | C | 10595 | X
11295
M. | Parking and Roadway |  | 1356 | LB |  | --- |  | P | 48 | LB | P | 38 | LB | 7/91 | Admin | 7/11/91
| Improvements, Phase 3 (Various) |  | 100 | X |  |  |  | P | 10 | X | W | 109 | LB
|  |  | 1456 |  |  |  |  | W | 110 | LB | C | 907 | LB
[8 empty] | W | 13 | X |  | 1054
[8 empty] | C | 144 | LB
[8 empty] | C | 77 | X
402
| Gifts (G) |  | 2067 | G |  | --- |  |  | 1911 | G |  | 156 | G
| Hospital Reserves (HR) |  | 2076 | HR |  | 362 | HR |  | --- |  |  | 1714 | HR
| Bank Loans or Bonds (LB) |  | 53743 | LB |  | --- |  |  | 26050 | LB |  | 34175 | LB
| Other (X) |  | 18823 | X |  | 11295 | X |  | 2782 | X |  | 4746 | X
|  |  | 0 | [5 empty] | 0
| TOTAL |  | 76709 |  |  | 11657 |  |  | 30743 |  |  | 40791
|  |  | 0 | [5 empty] | 0
| STATE FUNDS | ( | 33717 | ) | ( | 31939 | ) | ( | 1778 | ) | ( | --- | )

## San Francisco
SAN FRANCISCO CAMPUS
1989-90 NON-STATE CAPITAL BUDGET
($000)
[8 empty] | C U R R E N T S T A T U S | [7 empty] | PRIOR ACTION/COMMENTS
|  | Project | [8 empty] | Beyond |  |  |  | Approval
| Project | Cost |  |  | Prefunded |  |  | 1989-90 |  |  | 1989-90 |  | Action |  | Letter | Date | Action | Cost
A. | UCSF Medical Center, M-12 | 2394 | LB |  | --- |  | P | 70 | LB |  | --- |  | 7/89 | Admin | 7/26/89
| Cardiac Catheterization Lab | [5 empty] | W | 145 | LB
| Improvements (920540) | [5 empty] | C | 2179 | LB
2394
B. | UCSF Medical Center, M-15 | 5832 | LB |  | --- |  | P | 200 | LB |  | --- |  | 7/89 | Regents | 7/26/89
| Intensive Care Nursery | [5 empty] | W | 400 | LB
| Improvements (925880) | [5 empty] | C | 5232 | LB
5832
C. | UCSF Medical Center, M-10N | 1424 | LB |  | --- |  | P | 40 | LB |  | --- |  | 11/89 | Admin | 11/29/89
| Cardiac Care Unit Renovations | [5 empty] | W | 80 | LB
| (920780) | [5 empty] | C | 1304 | LB
1424
D. | Campus Library Building | 4550 | G |  | --- |  | P | 160 | G |  | --- |  | 10/89 | Admin | 10/13/89
| Improvements (920840) | [5 empty] | W | 255 | G
[7 empty] | C | 4135 | G
4550
E. | Campus Library Landscaping | 1400 | G |  | --- |  | P | 43 | G |  | --- |  | 10/89 | Admin | 10/13/89
| (920850) | [5 empty] | W | 69 | G
[7 empty] | C | 1288 | G
1400
F. | UCSF School of Medicine, S-10 | 256 | G |  | --- |  | P | 15 | G |  | --- |  | 10/89 | Admin | 10/31/89
| Howard Hughes Medical Institute, | [5 empty] | W | 23 | G
| Structural Biology Lab Alterations | [5 empty] | C | 218 | G
| (925960) | [6 empty] | 256
G. | School of Medicine, S-7 | 308 | X |  | --- |  | P | 18 | X |  | --- |  | 4/90 | Admin | 4/24/90
| Neurology Prion Lab (920800) | [5 empty] | W | 28 | X
[7 empty] | C | 262 | X
308
H. | UCSF School of Dentistry, | 760 | F/N |  | --- |  | P | 30 | F/N |  | --- |  | 11/89 | Admin | 11/15/89
| Stomatology AIDS Research | [5 empty] | W | 67 | F/N
| Center Alterations (920870) | [5 empty] | C | 663 | F/N
760
I. | School of Medicine, | 3594 | G |  | --- |  | P | 211 | G |  | --- |  | 3/90 | Admin | 3/8/90
| Ophthalmology Improvements | [5 empty] | W | 203 | G
| (925690) | [5 empty] | C | 3180 | G
3594
J. | UCSF Medical Center, M-7 N, S, | 3276 | LB |  | --- |  | P | 90 | LB |  | --- |  | 11/89 | Admin | 11/29/89
| E Cardiac Surgery Unit | [5 empty] | W | 200 | LB
| Improvements (920810) | [5 empty] | C | 2986 | LB
3276
K. | UCSF Medical Center, L-G Linear | 700 | HR | P | 25 | HR | C | 625 | HR |  | --- |  | 4/90 | Admin | 4/16/90
| Acceleration Installation (920900) |  |  | W | 50 | HR
75
L. | School of Medicine, S-7 | 354 | X |  | --- |  | P | 21 | X |  | --- |  | 5/90 | Admin | 5/14/90
| Physiology Laboratory | [5 empty] | W | 32 | X
| Improvements (920940) | [5 empty] | C | 301 | X
354
M. | UCSF Medical Center, Mount Zion | DELETED |  |  | --- |  |  | --- |  |  | --- |  | 11/92 | Regents | 2/10/93 | 3/90 | 1989-90 CIP | 42685
| Hospital and Medical Center | [12 empty] | Pulled -- Cancer Center
| Improvements Phase 1 (various) | [12 empty] | component reformulated as:
UCSF/Mt. Zion Outpatient
Cancer Center (see "I" in
1992-93)
N. | School of Medicine, HSE-7 | 1090 | X |  | --- |  | P | 62 | X |  | --- |  | 5/90 | Admin | 5/14/90
| Neurological Surgery Laboratory | [5 empty] | W | 98 | X
| Improvements (920140) | [5 empty] | C | 930 | X
1090
O. | School of Medicine, M-6 | 188 | F |  | --- |  | P | 16 | X |  | --- |  | 5/90 | Admin | 5/14/90
| Pediatrics Clinical Research Center | 80 | X |  |  |  | W | 24 | X
| (PCRC) Laboratory Improvements | 268 |  |  |  |  | C | 40 | X
| (926003) | [5 empty] | C | 188 | F
268
P. | Langley Porter Psychiatric Institute, | 542 | X |  | --- |  | P | 38 | X | P | 21 | X |  | delegated | Chancellor | 6/90 | 1989-92 CIP | 450
| Psychiatry Research Space | [5 empty] | W | 57 | X | W | 4 | X |  | (1993-94)
| Alterations (920930) | [5 empty] | C | 355 | X | C | 67 | X
| (Renamed in 1993-94: S/M Langley | [6 empty] | 450 |  |  | 92
Porter Psychiatric Institute SFGH 20,
Ward 21 Psychiatry Research
Space Alterations)
Q. | School of Medicine, U-5 | 502 | X |  | --- |  | P | 29 | X |  | --- |  | 6/90 | Admin | 6/7/90
| Pediatrics Office Alterations | [5 empty] | W | 51 | X
| (920950) | [5 empty] | C | 422 | X
502
R. | School of Medicine, Mission Center | 400 | X |  | --- |  | P | 21 | X |  | --- |  | 6/90 | Admin | 6/7/90
| (CED)-2 Microbiology Laboratory | [5 empty] | W | 46 | X
| Improvements (925992) | [5 empty] | C | 333 | X
400
S. | School of Medicine, MU-4W | 755 | X |  | --- |  | P | 25 | X |  | --- |  | 9/90 | Admin | 9/18/90
| Epidemiology and Biostatistics | [5 empty] | W | 50 | X
| Department Offices Relocation | [5 empty] | C | 680 | X
| (920200) | [6 empty] | 755
T. | School of Medicine, S-4 | 857 | X |  | --- |  | P | 36 | X |  | --- |  | 9/90 | Admin | 9/18/90
| Microbiology Laboratory | [5 empty] | W | 57 | X
| Improvements (920710) | [5 empty] | C | 764 | X
857
U. | Senior Vice Chancellor, Academic | 1328 | X |  | --- |  | P | 44 | X |  | --- |  | 8/90 | Admin | 8/20/90
| Affairs MR II Animal Care Facility | [5 empty] | W | 99 | X
| Phase II (920150) | [5 empty] | C | 1185 | X
1328
V. | The Medical Center at UCSF | 500 | HR |  | --- |  | P | 15 | HR |  | --- |  | 8/90 | Admin | 8/20/90
| ACC-C Level Family Practice | [5 empty] | W | 30 | HR
| Offices (920180) | [5 empty] | C | 455 | HR
500
W. | Emergency Power Improvements | 4000 | LB |  | --- |  | P | 275 | LB |  | --- |  | 10/90 | Admin | 10/18/90
| (920990) | [5 empty] | W | 325 | LB
[7 empty] | C | 3400 | LB
4000
X. | The Medical Center at UCSF L-G | 1000 | HR |  | --- |  | P | 50 | HR | W | 50 | HR | 2/91 | Admin | 2/19/91
| Gamma Unit Installation (926234) | [5 empty] | W | 50 | HR | C | 850 | HR
[8 empty] | 100 |  |  | 900
Y. | The Medical Center at UCSF | 740 | HR |  | --- |  | P | 50 | HR | C | 600 | HR | 3/91 | Admin | 3/20/91
| Moffitt/Long Seismic Joint Repair | [5 empty] | W | 90 | HR
| and Upgrade (920160) | [6 empty] | 140
| Federal Funds (F) | 188 | F |  | --- |  |  | 188 | F |  | ---
| Gift Funds (G) | 9800 | G |  | --- |  |  | 9800 | G |  | ---
| Hospital Reserves (HR) | 2940 | HR |  | 75 | HR |  | 1365 | HR |  | 1500 | HR
| Bank Loans or Bonds (LB) | 16926 | LB |  | --- |  |  | 16926 | LB |  | ---
| Federal Funds/Reserves other than | 0 | [5 empty] | 0
| University Registration Fees (F/N) | 760 | F/N |  | --- |  |  | 760 | F/N |  | ---
| Other (X) | 6216 | X |  | --- |  |  | 6124 | X |  | 92 | X
| TOTAL | 36830 |  |  | 75 |  |  | 35163 |  |  | 1592

## Santa Barbara
SANTA BARBARA CAMPUS
1989-90 NON-STATE CAPITAL BUDGET
($000)
[6 empty] | C U R R E N T S T A T U S | [8 empty] | PRIOR ACTION/COMMENTS
|  | Project | [6 empty] | Beyond |  |  |  | Approval
| Project | Cost |  | Prefunded |  | 1989-90 |  |  | 1989-90 |  | Action |  | Letter | Date | Action | Cost
A. | Residence Halls, Renovation | 6116 | LB | --- | P | 165 | LB |  | --- |  | 11/89 | Regents | 5/14/90
| Program Phase V, San Rafael |  |  |  | W | 203 | LB
| Towers (980940) |  |  |  | C | 5298 | LB
[5 empty] | E | 450 | LB
6116
B. | Sierra Nevada Aquatic Research | 175 | F | --- | P | 12 | X |  | --- |  | 5/90 | Admin | 5/1/90
| Laboratory (980880) | 162 | X |  | W | 15 | X
|  | 15 | G |  | C | 175 | F
|  | 352 |  |  | C | 129 | X
[5 empty] | C | 15 | G
[5 empty] | E | 6 | X
352
C. | Institute for Theoretical Physics | 5525 | LB | --- |  | --- |  | P | 145 | U | 5/93 | Interim | 6/16/93 | 2/89 | 1988-91 CIP | 4950
| Building (980990) (Formerly: | 1000 | U |  |  |  |  | W | 175 | U |  |  |  | 3/90 | 1988-91 & 1989-92 CIP | 6550
| Institute for Theoretical Physics | 257 | X |  |  |  |  | C | 680 | U |  |  |  | 3/90 | 1989-93 CIP | 6669
| Office Building #980660) | 6782 | [5 empty] | C | 5121 | LB
[8 empty] | C | 257 | X
[8 empty] | E | 404 | LB
6782
D. | Recreation Center/Aquatics Complex | 12987 | LB | --- |  | --- |  | P | 629 | X | 2/93 | Admin | 2/2/93 | 10/90 | 1989-92 CIP | 13873
| (980440) | 628 | R |  |  |  |  | P | 99 | R |  |  |  | 1/91 | 1990-93 CIP | 13798
|  | 1029 | X |  |  |  |  | W | 519 | R |  |  |  | (* LB reduced)
|  | 14644 | [5 empty] | W | 65 | X |  |  |  | 11/91 | 1991-94 CIP | 14244
[8 empty] | C | 10 | R |  |  |  | (** LB increased; R & X reduced)
[8 empty] | C | 12724 | LB
[8 empty] | C | 335 | X
[8 empty] | E | 263 | LB
14644
E. | University Center Expansion | 675 | X | --- | P | 473 | X | P | 202 | X | 11/91 | Regents | 2/2/93 | 6/90 | 1989-92 CIP | 15534
| (980590) | 675 | R |  | W | 475 | R | P | 200 | R
|  | 300 | G |  | C | 11770 | LB | W | 200 | N
|  | 200 | N |  | E | 1791 | LB | W | 251 | LB
|  | 17413 | LB |  |  | 14509 |  | C | 3601 | LB
|  | 19263 | [5 empty] | E | 300 | G
4754
F. | Upgrade General Classroom | 1300 | X | --- | P | 43 | X |  | --- |  | 6/90 | Admin | 6/26/90
| (980950) |  |  |  | W | 53 | X
[5 empty] | C | 1177 | X
[5 empty] | E | 27 | X
1300
G. | Relocate Materials Processing | 305 | X | --- | P | 5 | X |  | --- |  | 10/90 | Admin | 10/9/90
| Laboratory (980930) |  |  |  | W | 22 | X
[5 empty] | C | 278 | X
305
H. | Cheadle Hall Seismic Renovation | 3200 | LB | --- | P | 103 | LB |  | --- |  | 7/90 | Admin | 7/13/90
| (988771) |  |  |  | W | 123 | LB
[5 empty] | C | 2974 | LB
3200
| Federal Funds (F) | 175 | F | --- |  | 175 | F |  | ---
| Gift Funds (G) | 315 | G | --- |  | 15 | G |  | 300 | G
| Bank Loans or Bonds (LB) | 45241 | LB | --- |  | 22877 | LB |  | 22364 | LB
Reserves other than University
| Registration Fees (N) | 200 | N | --- |  | --- |  |  | 200 | N
| Registration Fees (R) | 1303 | R | --- |  | 475 | R |  | 828 | R
| Regents' Appropriation (U) | 1000 | U | --- |  | --- |  |  | 1000 | U
| Other (X) | 3728 | X | --- |  | 2240 | X |  | 1488 | X
| TOTAL | 51962 |  | --- |  | 25782 |  |  | 26180

## Santa Cruz
SANTA CRUZ CAMPUS
1989-90 NON-STATE CAPITAL BUDGET
($000)
[8 empty] | C U R R E N T S T A T U S | [6 empty] | PRIOR ACTION/COMMENTS
|  | Project | [7 empty] | Beyond |  |  | Approval
| Project | Cost |  |  | Prefunded |  |  | 1989-90 |  | 1989-90 | Action |  | Letter | Date |  | Action | Cost
A. | Visual Arts Faculty/Graduate Studio | 400 | X |  | --- |  | P | 17 | X | --- | 6/90 | Admin | 6/13/90
| (970900) | [5 empty] | W | 20 | X
[7 empty] | C | 349 | X
[7 empty] | E | 14 | X
400
B. | Campus Emergency Water System | 1290 | LB |  | --- |  | P | 58 | LB | --- | 10/90 | Admin | 10/18/90
| (976029) | [5 empty] | W | 71 | LB
[7 empty] | C | 1161 | LB
1290
C. | College Eight Housing, Phase I | 16064 | LB | P | 530 | LB | C | 184 | N | --- | 7/89 | Admin | 7/26/89 | 9/86 |  | 1986-89 CIP | 15161
| (976280) | 384 | N | P | 10 | X | [7 empty] | 9/87 |  | 1986-89 CIP | 16388
|  | 1024 | X | W | 500 | LB | [7 empty] | 6/88 |  | 1986-89 & 1987-90 CIP | 16888
|  | 17472 |  | W | 30 | X | [7 empty] | 12/88 |  | 1988-91 CIP | 17288
|  |  |  | C | 13789 | LB
|  |  |  | C | 460 | X
|  |  |  | C | 200 | N
|  |  |  | C | 400 | LB
|  |  |  | C | 524 | X
|  |  |  | E | 845 | LB
17288
| Bank Loans or Bonds (LB) | 17354 | LB |  | 16064 | LB |  | 1290 | LB | ---
Reserves other than University
| Registration Fee (N) | 384 | N |  | 200 | N |  | 184 | N | ---
| Other (X) | 1424 | X |  | 1024 |  |  | 400 | X | ---
| TOTAL | 19162 |  |  | 17288 |  |  | 1874 |  | ---

## Summary
1989-90 NON-STATE FUNDED PROJECTS
($ in thousands)
| UCB | UCD | UCI | UCLA | UCR | UCSD | UCSF | UCSB | UCSC | OTHER | TOTAL
Federal (F) | --- | 677 | --- | --- | --- | --- | 188 | 175 | --- | --- | 1040
Gifts (G) | 21748 | 3900 | --- | 6968 | 455 | 1911 | 9800 | 15 | --- | --- | 44797
Hospital Reserves (HR) | --- | 2068 | 241 | 5133 | --- | --- | 1365 | --- | --- | --- | 8807
Bank Loans or Bonds (LB) | 6927 | 24356 | 36170 | 56502 | 1503 | 26050 | 16926 | 22877 | 1290 | --- | 192601
Reserves Other Than University
Registration Fees (N) | --- | 1245 | --- | 30 | --- | --- | --- | --- | 184 | --- | 1459
Registration Fees (R) | --- | 300 | --- | --- | --- | --- | --- | 475 | --- | --- | 775
Regents' Appropriations (U) | --- | --- | --- | --- | 179 | --- | --- | --- | --- | --- | 179
Other (X) | 1100 | 8795 | 1000 | 6436 | 2000 | 2782 | 6124 | 2240 | 400 | --- | 30877
Federal Funds/Reserves other than
University Registration Fee (F/N) | --- | --- | --- | --- | --- | --- | 760 | --- | --- | --- | 760
TOTAL | 29775 | 41341 | 37411 | 75069 | 4137 | 30743 | 35163 | 25782 | 1874 | --- | 281295