## Berkeley
BERKELEY CAMPUS
1991-92 NON-STATE CAPITAL BUDGET
($000)
[9 empty] | C U R R E N T S T A T U S | [8 empty] | PRIOR ACTION/COMMENTS
|  |  | Project | [8 empty] | Beyond |  |  |  | Approval
| Project |  | Cost |  |  | Prefunded |  |  | 1991-92 |  |  | 1991-92 |  | Action |  | Letter | Date | Action | Cost
A. | NO PROJECT
B. | Life Sciences Building Renovation | ( | 48199 | ) | ( P | 938 | ) |  | - - - |  | ( E | 3592 | ) | 1/94 | Regents' | 3/30/94 | 10/85 | 1986-89 CIP | 62357
| for Ecology Evolutionary Biology |  | 24049 | G | P | 1626 | G |  |  |  | E | 1796 | G |  | Admin |  | 11/86 | 1987-90 CIP | 62357
| (912274) |  | 19083 | X | P | 85 | X |  |  |  | C | 18179 | X |  |  |  | 11/87 | 1988-91 CIP | 67746
|  |  | 91331 |  | ( W | 2603 | ) |  |  |  |  | 23567 |  |  |  |  | 11/88 | 1989-92 CIP | 69547
[5 empty] | W | 94 | G | [9 empty] | 11/89 | 1990-93 CIP | 69936
[5 empty] | W | 69 | X | [9 empty] | 10/90 | 1991-94 CIP | 70035
[5 empty] | ( C | 41066 | ) | [9 empty] | 11/91 | 1992-95 CIP | 70080
[5 empty] | C | 20533 | G | [9 empty] | 10/92 | 1993-96 CIP | 73152
[5 empty] | C | 750 | X
67764
C. | UC Berkeley University House |  | 998 | LB | P | 55 | LB | P | 4 | LB |  | - - - |  | 5/92 | Admin | 5/12/92 | 10/90 | 1989-92 CIP | 850
| Seismic Safety Corrections |  |  |  | W | 75 | LB | W | 54 | LB
| (912627) |  |  |  | C | 720 | LB | C | 90 | LB
[6 empty] | 850 |  |  | 148
D. | Lecture Halls Modernization |  | 785 | U |  | - - - |  | P | 21 | U |  | - - - |  | 3/92 | Admin | 3/13/92
| (912633) | [6 empty] | W | 81 | U
[8 empty] | C | 683 | U
785
E. | Richmond Field Station, Bldg. 420: |  | 400 | F |  | - - - |  | P | 25 | F |  | - - - |  | 1/92 | Chancellor | 1/31/92
| Earthquake Engineering Research |  | 100 | X |  |  |  | W | 30 | F
| Center Earthquake Shake Table |  | 500 |  |  |  |  | C | 345 | F
| Impr. (912641) | [6 empty] | C | 100 | X
500
F. | Etcheverry Hall: FANUC Faculty |  | 400 | G |  | - - - |  | P | 22 | G |  | - - - |  | 3/92 | Chancellor | 3/3/92
| Conference Room (912644) | [6 empty] | W | 46 | G
[8 empty] | C | 292 | G
[8 empty] | E | 40 | G
400
G. | Parking Structure "D" Seismic |  | 2550 | LB |  | - - - |  | P | 188 | LB |  | - - - |  | 6/92 | Admin | 6/25/92
| Corrections and Rehabilitation | [6 empty] | W | 359 | LB
| (912640) | [6 empty] | C | 2003 | LB
2550
H. | Seismic Safety Corrections, Earth |  | 975 | LB |  | - - - |  | P | 100 | LB | C | 100 | LB | 6/93 | Admin | 6/23/93 | 12/92 | 1991-94 CIP | 875
| Sciences Building (912613) | [6 empty] | W | 150 | LB
[8 empty] | C | 625 | LB
875
I. | Seismic Safety Corrections, North |  | 918 | LB |  | - - - |  | P | 35 | LB | C | 218 | LB | 6/93 | Admin | 6/23/93 | 12/92 | 1991-94 CIP | 700
| Gate Hall, Step 1 (912656) | [6 empty] | W | 60 | LB
[8 empty] | C | 605 | LB
700
J. | Interbuilding Communications |  | 375 | X |  | - - - |  | P | 20 | X |  | - - - |  | 6/92 | Chancellor | 6/25/92
| Conduit System: Physical | [6 empty] | W | 20 | X
| Sciences Precinct (912391) | [6 empty] | C | 335 | X
375
| Federal Funds (F) |  | 400 | F |  | - - - |  |  | 400 | F |  | - - -
| Gift Funds (G) |  | 24449 | G |  | 22253 | G |  | 400 | G |  | 1796 | G
| Bank Loans or Bonds (LB) |  | 5441 | LB |  | 850 | LB |  | 4273 | LB |  | 318 | LB
| Regents' Appropriations (U) |  | 785 | U |  | - - - |  |  | 785 | U |  | - - -
| Others (X) |  | 19558 | X |  | 904 | X |  | 475 | X |  | 18179
| TOTAL |  | 50633 |  |  | 24007 |  |  | 6333 |  |  | 20293
| STATE FUNDS | ( | 48199 | ) | ( | 44607 | ) | ( | - - - | ) | ( | 3592 | )

## Davis
DAVIS CAMPUS
1991-92 NON-STATE CAPITAL BUDGET
($000)
[9 empty] | C U R R E N T S T A T U S | [8 empty] | PRIOR ACTION/COMMENTS
|  |  | Project | [8 empty] | Beyond |  |  |  | Approval
| Project |  | Cost |  |  | Prefunded |  |  | 1991-92 |  |  | 1991-92 |  | Action |  | Letter | Date |  | Action | Cost
A. | Patient Support Services Building |  | 18440 | LB |  | - - - |  | P | 1048 | LB |  | - - - |  | 7/91 | Regents | 8/5/91
| (934990) | [6 empty] | W | 1572 | LB
[8 empty] | C | 15820 | LB
18440
B. | UCDMC North/South Wing 4th |  | 3749 | HR |  | - - - |  | P | 319 | HR |  | - - - |  | 7/91 | Admin | 7/23/91
| Floor Reconstruction and | [6 empty] | W | 479 | HR
| Renovation (935130) | [6 empty] | C | 2951 | HR
3749
C. | NO PROJECT
D. | UCDMC Intensive Care Unit |  | 999 | HR | P | 149 | HR | C | 850 | HR |  | - - - |  | 11/91 | Admin | 11/14/91 | 11/86 |  | 1987-90 CIP | 1856
| Expansion Project at UCDMC | ( | 2345 | ) | ( W | 171 | ) | [9 empty] | 11/87 |  | 1988-91 CIP | 2494
| (934840) |  | 3344 |  | ( C | 2174 | )
2494
E. | UCDMC Fleet Services (934980) |  | 2943 | N |  | - - - |  | P | 152 | N |  | - - - |  | 9/91 | Chancellor | 9/17/91
[8 empty] | W | 228 | N
[8 empty] | C | 2563 | N
2943
F. | Repro Graphics Services Center |  | DELETED |  |  | - - - |  |  | - - - |  |  | - - - |  | Deleted
| Alterations (931640) | [12 empty] | by campus
G. | UCDMC Operating Room |  | 999 | HR | P | 314 | HR | C | 685 | HR |  | - - - |  | ?/93 | Admin | ( Letter | 11/87 |  | 1988-91 CIP | 5216
| Expansion Project (934820) | ( | 4902 | ) | ( W | 361 | ) | [8 empty] | Pending )
|  |  | 5901 |  | ( C | 4541 | )
5216
H. | NO PROJECT
I. | West Campus Wastewater System |  | 1780 | X | S | 105 | X | C | 207 | X |  | - - - |  | 5/92 | Admin | 5/19/92 | 6/91 |  | 1990-91 CIP | 1573
| Connection (938043) |  |  |  | P | 92 | X
[5 empty] | W | 62 | X
[5 empty] | C | 1314 | X
1573
J. | Memorial Union North Courtyard |  | 424 | N |  | - - - |  | P | 40 | N |  | - - - |  | 6/92 | Admin | 6/25/92
| Renovation (931580) |  | 140 | R |  |  |  | W | 50 | N
|  |  | 564 |  |  |  |  | C | 334 | N
[8 empty] | C | 140 | R
564
K. | NO PROJECT
L. | Classroom Renovation Phase I |  | 400 | X |  | - - - |  | P | 25 | X |  | - - - |  | 5/92 | Admin | 5/19/92
| (931660) | [6 empty] | W | 25 | X
[8 empty] | C | 300 | X
[8 empty] | E | 50 | X
400
M. | California Primate Research |  | 443 | F |  | - - - |  | P | 15 | F |  | - - - |  | 3/92 | Chancellor | 3/11/92
| Center Modular Laboratory | [6 empty] | W | 30 | F
| Building (935000) | [6 empty] | C | 398 | F
443
N. | UCDMC X Street Expansion |  | 2494 | HR |  | - - - |  | P | 91 | HR |  | - - - |  | 5/92 | Admin | 5/4/92
| (935170) | [6 empty] | W | 136 | HR
[8 empty] | C | 2267 | HR
2494
O. | Primero Housing Replacement |  | DELETED |  |  | - - - |  |  | - - - |  |  | - - - |  |  | Deleted by campus |  | 5/92 |  | 1991-94 CIP | 33627
| (936312) | [16 empty] | ( | replaced by North Campus
Inclusion Area Project, June 1997)
P. | UCDMC Parking Lot #18 (936572) |  | 525 | N |  | - - - |  | P | 21 | N |  | - - - |  | 4/92 | Chancellor | 4/24/92
[8 empty] | W | 32 | N |  |  |  |  | Approved
[8 empty] | C | 472 | N
525
Q. | Life Sciences Expansion: Briggs |  | 1066 | U | P | 1066 | U |  | - - - |  | ( W | 1044 | ) | 11/92 | Regents' | N/A | 10/90 |  | 1991-94 CIP | 19124
| Hall Addition (931120) |  | 3158 | X | [6 empty] | ( C | 24664 | ) |  | Budget |  | 10/91 |  | 1992-95 CIP | 29146
|  | ( | 25708 | ) | [6 empty] | E | 3158 | X
|  |  | 29932 | [8 empty] | 28866
| Federal Funds (F) |  | 443 | F |  | - - - |  |  | 443 | F |  | - - -
| Hospital Reserve Funds (HR) |  | 8241 | HR |  | 463 | HR |  | 7778 | HR |  | - - -
| Bank Loans or Bonds (LB) |  | 18440 | LB |  | - - - |  |  | 18440 | LB |  | - - -
Reserves other than University
| Registration Fee (N) |  | 3892 | N |  | - - - |  |  | 3892 | N |  | - - -
Funds from Sources Yet to be
| Determined (Q) |  |  |  |  | - - - |  |  | - - - |  |  | - - -
| Registration Fees (R) |  | 140 | R |  | - - - |  |  | 140 | R |  | - - -
| Regents' Appropriations (U) |  | 1066 | U |  | 1066 | U |  | - - -
| Other (X) |  | 5338 | X |  | 1573 | X |  | 607 | X |  | 3158 | X
| TOTAL |  | 37560 |  |  | 3102 |  |  | 31300 |  |  | 3158
| STATE FUNDS | ( | 32955 | ) | ( | 7247 | ) | ( | - - - | ) | ( | 25708 | )

## Irvine
IRVINE CAMPUS
1991-92 NON-STATE CAPITAL BUDGET
($000)
[9 empty] | C U R R E N T S T A T U S | [8 empty] | PRIOR ACTION/COMMENTS
|  |  | Project | [8 empty] | Beyond |  |  |  | Approval
| Project |  | Cost |  |  | Prefunded |  |  | 1991-92 |  |  | 1991-92 |  | Action |  | Letter | Date | Action | Cost
A. | Fine Arts Photo Lab Renovation |  | 320 | X |  | - - - |  | P | 20 | X |  | - - - |  | 11/91 | Chancellor | 11/21/91
| and Addition (991385) | [6 empty] | W | 23 | X
[8 empty] | C | 277 | X
320
B. | Irvine Hall Renovations (994092) |  | 425 | X |  | - - - |  | P | 13 | X |  | - - - |  | 7/92 | Chancellor | 7/10/92
[8 empty] | W | 17 | X
[8 empty] | C | 355 | X
[8 empty] | E | 40 | X
425
C. | Social Sciences Unit 2 (992060) |  | 1225 | U |  | - - - |  | P | 1225 | U | ( W | 1278 | ) | 11/91 | Regents' | N/A | 10/90 | 1991-94 CIP | 32992
|  | ( | 32545 | ) | [6 empty] | ( C | 28391 | ) |  | Budget
|  |  | 33770 | [7 empty] | ( E | 2876 | )
32545
| Regents' Appropriations (U) |  | 1225 | U |  | - - - |  |  | 1225 | U |  | - - -
| Other (X) |  | 745 | X |  | - - - |  |  | 745 | X |  | - - -
| TOTAL |  | 1970 |  |  | - - - |  |  | 1970 |  |  | - - -
| STATE FUNDS | ( | 32545 | ) | ( | - - - | ) | ( | - - - | ) | ( | 32545 | )

## Los Angeles
LOS ANGELES CAMPUS
1991-92 NON-STATE CAPITAL BUDGET
($000)
[9 empty] | C U R R E N T S T A T U S | [8 empty] | PRIOR ACTION/COMMENTS
|  |  | Project | [8 empty] | Beyond |  |  |  | Approval
| Project |  | Cost |  |  | Prefunded |  |  | 1991-92 |  |  | 1991-92 |  | Action |  | Letter | Date | Action | Cost
A. | Health Sciences Building 6th Floor |  | 1406 | X | P | 108 | X | C | 61 | X |  | - - - |  | 5/92 | Admin | 5/12/92 | 11/88 | 1988-91 CIP | 1236
| Anatomy and Cell Biology |  |  |  | W | 152 | X | [9 empty] | 11/90 | 1990-93 CIP | 1345
| Laboratory Alteration (945420) |  |  |  | C | 1085 | X
1345
B. | Parking Service and Ridesharing |  | 4534 | LB | P | 120 | LB | C | 668 | LB |  | - - - |  | 10/91 | Admin | 10/22/91 | 1/87 | 1986-89 CIP | 2163
| Office Expansion and Renovation |  | 118 | X | W | 240 | LB | C | 118 | X | [6 empty] | 1/89 | 1988-91 CIP | 3834
| (Formerly: Campus Parking |  | 4652 |  | C | 3205 | LB | E | 32 | LB
| Service Expansion/Ridesharing |  |  |  | E | 269 | LB |  | 818
| Relocation) (946670) |  |  |  |  | 3834
C. | Chemistry and Biological Sciences |  | 7500 | G | ( P | 1350 | ) | C | 4249 | G | ( E | 1200 | ) | 9/92 | State | N/A | 10/85 | 1986-89 CIP | 36805
| Addition (941080) | ( | 40234 | ) | ( W | 1486 | ) | [7 empty] | Budget Act |  | 11/86 | 1987-90 CIP | 36075
|  |  | 47734 |  | ( C | 36198 | ) | [9 empty] | 11/87 | 1988-91 CIP | 36805
[5 empty] | C | 3251 | G | [9 empty] | 11/89 | 1990-93 CIP | 36891
[6 empty] | 42285 | [10 empty] | 10/90 | 1991-94 CIP | 43462
[17 empty] | 11/91 | 1992-95 CIP | 47711
D. | Seismic Reconstruction of Moore |  | 16900 | LB |  | - - - |  | P | 1497 | LB |  | - - - |  | 6/92 | Admin | 6/16/92
| Hall, Math Sciences, Bunche Hall | [6 empty] | W | 1601 | LB
| (Phase 1) (948720) | [6 empty] | C | 13802 | LB
16900
E. | White Mountain Research Station, |  | 486 | X |  | - - - |  | C | 283 | X | C | 171 | X | 5/92 | Admin | 5/12/92
| Crooked Creek Facility Alt. | [6 empty] | E | 3 | X | E | 29 | X
| (942620) | [7 empty] | 286 |  |  | 200
F. | UCLA Medical Center CHS Annex |  | 4647 | HR | P | 86 | HR | C | 176 | HR |  | - - - |  | 10/91 | Admin | 10/22/91 | 11/87 | 1987-90 CIP | 3240
| Building Replacement (Formerly: |  |  |  | W | 182 | HR | [9 empty] | 9/88 | 1988-91 CIP | 4471
| UCLA Medical Center Hospital |  |  |  | C | 4203 | HR
| Annex Replacement Building) |  |  |  |  | 4471
(944870)
G. | Parking Structures 8 and 14 |  | 2120 | LB |  | - - - |  | P | 64 | LB |  | - - - |  | 6/92 | Admin | 6/16/92
| Seismic and Lighting Renovation | [6 empty] | W | 85 | LB
| (946715) | [6 empty] | C | 1971 | LB
2120
H. | UCLA Medical Center 3rd Floor |  | 1097 | HR | P | 81 | HR | W | 95 | HR | C | 921 | HR | ?/92 | Admin | (Letter
| Pediatric Inpatient Alterations | [14 empty] | Pending)
(944570)
I. | Lake Arrowhead Conference |  | 683 | N |  | - - - |  | P | 17 | N | C | 333 | N | 8/93 | Chancellor | 8/16/93 | 5/92 | 1991-94 CIP | 350
| Center, Swimming Pool | [6 empty] | W | 21 | N
| Modernization (946180) | [6 empty] | C | 312 | N
350
J. | East Melnitz Building (942490) |  | 355 | X | P | 195 | X | C | 175 | LB |  | - - - |  | 9/92 | Admin | 9/24/92 | 5/90 | 1989-90 CIP | 4025
|  |  | 3845 | LB | W | 160 | X
|  |  | 4200 |  | C | 3155 | LB
[5 empty] | E | 515 | LB
4025
K. | Murphy Hall 1st Floor Graduate |  | 500 | X |  | - - - |  | P | 19 | X |  | - - - |  | 9/92 | Admin | 9/24/92
| Division Alterations (942280) | [6 empty] | W | 38 | X
[8 empty] | C | 443 | X
500
L. | UCLA Medical Center Pediatric |  | 1650 | HR |  | - - - |  | P | 82 | HR | C | 316 | HR | 9/92 | Admin | 9/24/92 | 1/89 | 1988-91 CIP | 1334
| Catheterization Lab Alterations | [6 empty] | W | 158 | HR
| (945290) | [6 empty] | C | 1094 | HR
1334
M. | Health Sciences Building Medical |  | DELETED |  |  | - - - |  |  | - - - |  |  | - - - |  | 3/93 | Deleted by
| Center A-Level Ethylene Oxide | [13 empty] | campus
Sterilizer Alterations (945820)
N. | UCLA Medical Center Main |  | 26100 | HR | P | 2280 | HR | C | 9685 | HR |  | - - - |  | 9/92 | Admin | 9/29/92 | 9/86 | 1986-89 CIP | 26540
| Operating Room Suite Expansion |  | 35000 | LB | W | 5244 | HR | [9 empty] | 7/87 | 1987-90 CIP | 36600
| (944880) (Formerly: Medical |  | 61100 |  | C | 8891 | HR | [9 empty] | 9/89 | 1989-92 CIP | 51415
| Center Operating Room #10 |  |  |  | C | 35000 | LB | [9 empty] | 3/91 | 1990-93 CIP | 59002
| Expansion) |  |  |  |  | 51415
O. | Powell Library Seismic Renovation |  | 271 | U | S | 271 | U | ( C | 31735 | ) |  | - - - |  | 9/92 | State | N/A | 11/87 | 1988-91 CIP | 29030
| (942510) | ( | 35228 | ) | ( P | 1542 | ) | [7 empty] | Budget Act |  | 11/88 | 1989-92 CIP | 34547
|  |  | 35499 |  | ( W | 1951 | ) | [9 empty] | 11/89 | 1990-93 CIP | 35692
[6 empty] | 3764 | [10 empty] | 10/90 | 1991-94 CIP | 36002
| Gifts (G) |  | 7500 | G |  | 3251 | G |  | 4249 | G |  | - - -
| Hospital Reserve Funds (HR) |  | 33494 | HR |  | 20967 | HR |  | 11290 | HR |  | 1237 | HR
| Bank Loans or Bonds (LB) |  | 62399 | LB |  | 42504 | LB |  | 19895 | LB |  | - - -
| Regents' Appropriation (U) |  | 271 | U |  | 271 |  |  | - - - |  |  | - - -
Reserves other than University
| Registration Fee (N) |  | 683 | N |  |  |  |  | 350 | N |  | 333 | N
| Other (X) |  | 2865 | X |  | 1700 | X |  | 965 | X |  | 200 | X
|  |  | 107212 |  |  | 68693 |  |  | 36749 |  |  | 1770
| STATE FUNDS | ( | 75462 | ) | ( | 42527 | ) | ( | 31735 | ) | ( | 1200 | )

## Riverside
RIVERSIDE CAMPUS
1991-92 NON-STATE CAPITAL BUDGET
($000)
[8 empty] | C U R R E N T S T A T U S | [9 empty] | PRIOR ACTION/COMMENTS
|  |  | Project | [8 empty] | Beyond |  |  |  | Approval
| Project |  | Cost |  |  | Prefunded |  |  | 1991-92 |  |  | 1991-92 |  | Action |  | Letter | Date |  | Action | Cost
A. | Public Services Building (950388) |  | DELETED |  |  | - - - |  |  | - - - |  |  | - - - |  | Deleted
by campus
B. | Entomology Teaching and Research |  | 1129 | G |  | - - - |  | P | 24 | G |  | - - - |  | 12/91 | Chancellor | 12/9/91
| Facility (950364) | [6 empty] | W | 37 | G
[8 empty] | C | 1068 | G
1129
C. | Interim Facilities Phase 2 (950384) |  | 2000 | X |  | - - - |  | P | 40 | X |  | - - - |  | 6/92 | Admin | 6/16/92
[8 empty] | W | 64 | X
[8 empty] | C | 1896 | X
2000
D. | Parking Services Building (950388) |  | 909 | X |  | - - - |  | P | 35 | X |  | - - - |  | 6/92 | Chancellor | 6/29/92
[8 empty] | W | 35 | X
[8 empty] | C | 797 | X
[8 empty] | E | 42 | X
909
E. | Central Utility Plant Boiler Renewal, | ( | 3268 | ) | P | 93 | X | ( C | 1466 | ) |  | - - - |  | 10/90 | Regents' | N/A | 11/89 |  | 1990-93 CIP | 2517
| Phase 2 (950371) |  | 244 | X | W | 151 | X | [7 empty] | Budget
|  |  | 3512 |  | ( C | 1802 | )
2046
F. | Humanities and Social Science |  | 553 | X |  | - - - |  | P | 553 | X | ( W | 794 | ) | 11/92 | Regents' | N/A | 10/90 |  | 1991-94 CIP | 19076
| Building, Unit 1 (950356) | ( | 19523 | ) | [6 empty] | ( C | 17605 | ) |  | Budget |  | 10/91 |  | 1992-95 CIP | 19533
|  |  | 20076 | [7 empty] | ( E | 1124 | )
19523
| Gifts (G) |  | 1129 | G |  | --- |  |  | 1129 | G |  | ---
| Other (X) (Campus Funds) |  | 3706 | X |  | 244 |  |  | 3462 | X |  | ---
| TOTAL |  | 4835 |  |  | 244 |  |  | 4591 |  |  | ---
| STATE FUNDS | ( | 22791 | ) | ( | 1802 | ) | ( | 1466 | ) | ( | 19523 | )

## San Diego
SAN DIEGO CAMPUS
1991-92 NON-STATE CAPITAL BUDGET
($000)
[9 empty] | C U R R E N T S T A T U S | [8 empty] | PRIOR ACTION/COMMENTS
|  |  | Project | [8 empty] | Beyond |  |  |  | Approval
| Project |  | Cost |  |  | Prefunded |  |  | 1991-92 |  |  | 1991-92 |  | Action |  | Letter | Date |  | Action | Cost
A. | Recreation/Intramural and Athletic |  | 29500 | LB |  | - - - |  | P | 1513 | X |  | - - - |  | 9/91 | Regents | 3/18/92
| Complex (RIMAC) (961910) |  | 2000 | R |  |  |  | W | 1918 | R
|  |  | 2000 | X |  |  |  | C | 487 | X
|  |  | 33500 |  |  |  |  | C | 82 | R
[8 empty] | C | 28400 | LB
[8 empty] | C | 1100 | LB
33500
B. | UCSD Medical Center Inpatient |  | 2076 | HR | P | 362 | HR | C | 2622 | LB | C | 1530 | HR | 2/94 | Admin | 2/2/94 | 5/86 |  | 1985-88 & 1986-89 CIP | 29450
| Tower Completion and |  | 2622 | LB | ( P | 511 | ) |  |  |  | C | 105 | G |  |  |  | 11/87 |  | 1988-91 CIP | 32301
| Modernization Project (964950) |  | 105 | G | ( W | 1196 | ) |  |  |  | E | 184 | HR |  |  |  | 1/90 |  | 1989-92 CIP | 34079
|  | ( | 33717 | ) | ( C | 32010 | ) |  |  |  |  | 1819 |  |  |  |  | 12/92 |  | 1992-95 CIP | 36701
|  |  | 38520 |  |  | 34079
C. | UCSD Medical Center Emergency |  | 3621 | LB |  | - - - |  | P | 87 | LB |  | - - - |  | 3/92 | Admin | 3/25/92 | 11/87 |  | 1987-90 CIP | 2522
| Power Upgrade (EPU) Project | [6 empty] | W | 160 | LB
| (965020) | [6 empty] | C | 3374 | LB
3621
D. | Clinical Sciences Building (965030) |  | 6825 | G | P | 755 | X | W | 25 | X |  | - - - |  | 9/92 | Admin | 9/24/92 | 3/88 |  | 1987-90 CIP | 25165
|  |  | 15165 | LB | W | 245 | X | C | 825 | G
|  |  | 3000 | U | W | 762 | U |  | 850
|  |  | 1025 | X | C | 2238 | U
|  |  | 26015 |  | C | 6000 | G
[5 empty] | C | 15165 | LB
25165
E. | UCSD Medical Center, Outpatient |  | 4118 | LB | P | 125 | LB | P | 22 | LB |  | - - - |  | 7/92 | Admin | 7/21/92 | 10/89 |  | 1989-92 CIP | 3584
| Center Renovations and Cardiac |  |  |  | W | 324 | LB | W | 281 | LB
| Catheterization Suite (965060) |  |  |  | C | 3135 | LB | C | 231 | LB
[6 empty] | 3584 |  |  | 534
F. | UCSD Medical Center Regional |  | 1804 | HR |  | - - - |  | P | 111 | HR | P | 230 | HR |  | Chancellor | delegated | 9/92 |  | 1991-94 | 3182
| Burn Center Expansion & |  | 513 | G |  |  |  | W | 55 | G | W | 125 | HR
| Modernization (965170) |  | 1025 | X |  |  |  | C | 976 | X | W | 49 | X
|  |  | 3342 |  |  |  |  | C | 1338 | HR | C | 458 | G
[9 empty] | 2480 |  |  | 862
G. | UCSDMC Emergency Department |  | 112 | HR |  | - - - |  | P | 42 | HR |  | - - - |  | 4/92 | Admin | 4/14/92
| Expansion & Renovation (965160) |  | 415 | X |  |  |  | W | 70 | HR
|  |  | 527 |  |  |  |  | W | 24 | X
[8 empty] | C | 391 | X
527
H. | Second Floor Completion, Cellular |  | 3052 | LB | P | 85 | LB | C | 822 | X |  | - - - |  | 12/92 | Admin | 12/23/92 | 3/89 |  | 1988-91 CIP | 3052
| and Molecular Medicine (Formerly: |  | 822 | X | W | 105 | LB
| Second Floor Completion Project, |  | 3874 |  | C | 2862 | LB
| Molecular Biology Research |  |  |  |  | 3052
Facility Unit II) (961900)
I. | University Center and Bookstore |  | 3147 | G | P | 307 | X | P | 115 | N |  | - - - |  | 8/92 | Admin | 8/24/92 | 5/85 |  | 1984-87 CIP | 18650
| (Formerly: University Center, |  | 14150 | LB | W | 407 | X | W | 171 | N
| Bookstore and Student Center |  | 1460 | N | C | 13452 | LB | C | 1129 | G
| Renovations) (961410/961420) |  | 1151 | R | C | 500 | R | C | 599 | N
|  |  | 3215 | X | C | 1700 | G | C | 651 | R
|  |  | 23123 |  | C | 500 | N | C | 1838 | X
[5 empty] | E | 300 | G | E | 18 | G
[6 empty] | 17166 |  | E | 75 | N
[8 empty] | E | 698 | LB
[8 empty] | E | 663 | X
5957
J. | UCSD Medical Center Bannister |  | 500 | G |  | - - - |  | P | 80 | G | C | 18 | HR |  | Chancellor | delegated | 8/92 |  | 1991-94 CIP | 1845
| Family House (965200) |  | 1424 | HR |  |  |  | W | 165 | G | C | 61 | G |  |  |  | 6/94 |  | 1993-96 CIP | 1862
|  |  | 1924 |  |  |  |  | C | 255 | G |  | 79
[8 empty] | C | 1345 | HR
1845
K. | Campus Energy Management |  | 6130 | LB |  | - - - |  | P | 140 | LB | C | 250 | X | 3/95 | Admin | 3/15/95 | 6/92 |  | 1991-94 CIP | 5385
| System (966067) |  | 250 | X |  |  |  | W | 300 | LB | [6 empty] | 2/93 |  | 1991-94 CIP | 5740
|  |  | 6380 |  |  |  |  | C | 5690 | LB | [6 empty] | 8/93 |  | 1991-94 CIP | 6130
6130
L. | Stephen Birch Aquarium-Museum |  | 8238 | G | P | 372 | G | P | 52 | G |  | - - - |  | 8/92 | Admin | 8/24/92 | 10/83 |  | 1984-87 CIP | 8000
| (Formerly: Ocean Interpretive |  | 438 | LB | W | 473 | G | W | 67 | G | [6 empty] | 1/87 |  | 1986-89 | 8590
| Center) (961230) |  | 8676 |  | C | 6327 | G | C | 947 | G | [6 empty] | 9/88 |  | 1988-91 CIP | 7610
[5 empty] | C | 438 | LB |  | 1066
7610
M. | Shiley Eye Center (964990) |  | 2532 | G | P | 180 | G | P | 25 | HR |  | - - - |  | 5/92 | Admin | 5/12/92 | 5/88 |  | 1987-90 CIP | 7059
|  |  | 516 | HR | W | 230 | G | W | 50 | HR
|  |  | 4056 | LB | C | 1390 | G | C | 441 | HR
|  |  | 500 | X | C | 500 | X | C | 732 | G
|  |  | 7604 |  | C | 4056 | LB |  | 1248
6356
N. | Student Center Building C Remodel |  | 14 | G |  | - - - |  | P | 14 | G |  | - - - |  | 8/92 | Chancellor | 8/17/92
| and Expansion (962130) |  | 331 | X |  |  |  | P | 3 | X
|  |  | 345 |  |  |  |  | W | 47 | X
[8 empty] | C | 281 | X
345
O. | Social Sciences Building (961930) |  | 473 | U |  | - - - |  | P | 473 | U | ( W | 623 | ) | 11/92 | Regents' | N/A | 10/90 |  | 1991-94 CIP | 14553
|  | ( | 14835 | ) | [6 empty] | ( C | 13130 | ) |  | Budget |  | 10/91 |  | 1992-95 CIP | 14899
|  |  | 15308 | [7 empty] | ( E | 1082 | )
14835
P. | Galbraith Hall Reinforcement |  | 1997 | LB | P | 66 | LB | W | 25 | LB | C | 77 | X | 8/93 | Admin | 8/13/93 | 7/90 |  | 1989-92 CIP | 1440
| (968716) |  | 330 | X | W | 56 | LB | C | 532 | LB | [6 empty] | 9/91 |  | 1991-94 CIP | 1840
|  |  | 2327 |  | C | 1318 | LB | C | 253 | X | [6 empty] | 6/92 |  | 1991-94 CIP | 2250
[6 empty] | 1440 |  |  | 810
| Gift Funds (G) |  | 23950 | G |  | 16972 | G |  | 4450 | G |  | 624 | G
| Hospital Reserves (HR) |  | 5932 | HR |  | 362 | HR |  | 3422 | HR |  | 2545 | HR
| Bank Loans or Bonds (LB) |  | 84849 | LB |  | 41187 | LB |  | 45007 | LB |  | - - -
Reserves other than University
| Registration Fee (N) |  | 1460 | N |  | 500 | N |  | 960 | N |  | - - -
| Registration Fees (R) |  | 3151 | R |  | 500 | R |  | 2651 | R |  | - - -
| Regents' Appropriation (U) |  | 3473 | U |  | 3000 | U |  | 473 | U |  | - - -
| Other (X) |  | 9913 | X |  | 2214 | X |  | 7323 | X |  | 376 | X
| TOTAL |  | 132728 |  |  | 64735 |  |  | 64286 |  |  | 3545
| STATE FUNDS | ( | 48552 | ) | ( | 33717 | ) | ( | - - - | ) | ( | 14835 | )

## San Francisco
SAN FRANCISCO CAMPUS
1991-92 NON-STATE CAPITAL BUDGET
($000)
[9 empty] | C U R R E N T S T A T U S | [8 empty] | PRIOR ACTION/COMMENTS
|  |  | Project | [8 empty] | Beyond |  |  |  | Approval
| Project |  | Cost |  |  | Prefunded |  |  | 1991-92 |  |  | 1991-92 |  | Action |  | Letter | Date |  | Action | Cost
A. | The Medical Center at UCSF MU |  | 200 | HR | P | 75 | HR | P | 100 | HR |  | - - - |  | 10/91 | Admin | 10/22/91 | 7/91 |  | 1991-94 CIP | 3200
| 3,4,5 - East Tower Relocation |  | 3085 | LB |  |  |  | W | 25 | HR
| (920920) |  | 3285 |  |  |  |  | W | 285 | LB
[8 empty] | C | 2800 | LB
3210
B. | The Medical Center at UCSF |  | 850 | HR |  | - - - |  | W | 90 | HR |  | - - - |  | 4/92 | Admin | 4/14/92
| Mount Zion Accounting Relocation | [6 empty] | C | 490 | HR
| (926244) | [6 empty] | E | 270 | HR
850
C. | The Medical Center at UCSF |  | 2900 | HR |  | - - - |  | P | 50 | HR |  | - - - |  | 10/91 | Admin | 10/22/91
| ACC-Code Corrections Phase I & | [6 empty] | W | 100 | HR
| MRI Relocation (920340) | [6 empty] | C | 2750 | HR
2900
D. | The Medical Center at UCSF ML |  | 715 | LB |  | - - - |  | P | 34 | LB |  | - - - |  | 10/91 | Admin | 10/22/91
| Emergency Power District | [6 empty] | W | 69 | LB
| Modification (924040) | [6 empty] | C | 612 | LB
715
E. | The Medical Center at UCSF |  | 1450 | LB |  | - - - |  | P | 70 | LB |  | - - - |  | 10/91 | Admin | 10/22/91
| M-14 East Wing Inpatient Unit | [6 empty] | W | 150 | LB
| Renovation (924070) | [6 empty] | C | 1230 | LB
1450
F. | The Medical Center at UCSF |  | 1050 | LB |  | - - - |  | P | 55 | LB |  | - - - |  | 10/91 | Admin | 10/22/91
| M-15S Perinatal Services | [6 empty] | W | 111 | LB
| Renovation (920740) | [6 empty] | C | 884 | LB
1050
G. | The Medical Center at UCSF The |  | 1527 | LB |  | - - - |  | P | 32 | LB |  | - - - |  | 10/91 | Admin | 10/22/91
| Moffitt Hospital Elevator | [6 empty] | W | 72 | LB
| Modernization Project (924080) | [6 empty] | C | 1423 | LB
1527
H. | UCSF LPPI Neurogenetics |  | 1604 | X |  | - - - |  | P | 47 | X | C | 556 | X | 9/91 | Chancellor | 9/27/91 | 5/89 |  | 1988-91 CIP | 1048
| Laboratory Improvements | [6 empty] | W | 84 | X
| (920650) | [6 empty] | C | 917 | X
1048
I. | School of Medicine, U1 & 4 |  | 480 | X | P | 23 | X | C | 234 | X |  | - - - |  | 5/92 | Admin | 5/19/92 | 4/89 |  | 1988-91 CIP | 271
| Orthopaedic Surgery |  |  |  | W | 39 | X
| Improvements (920760) |  |  |  | C | 184 | X
246
J. | School of Medicine, Mount Zion |  | 59315 | LB |  | - - - |  | P | 2260 | LB |  | - - - |  | 3/92 | Regents | 5/8/92
| Research Building (926074) | [6 empty] | W | 2605 | LB
[8 empty] | C | 48625 | LB
[8 empty] | E | 5825 | LB
59315
K. | VC-BFS, MC B-1 Police |  | 1201 | X |  | - - - |  | P | 41 | X |  | - - - |  | 5/91 | Chancellor | 5/15/91
| Department Improvements | [6 empty] | W | 84 | X
| (920320) | [6 empty] | C | 1043 | X
[8 empty] | E | 33 | X
1201
L. | Millberry Union Level I Renovations |  | 1399 | LB |  | - - - |  | P | 46 | LB |  | - - - |  | 5/92 | Admin | 5/12/92
| & Level J Bookstore Alterations | [6 empty] | W | 92 | LB
| (924440) | [6 empty] | C | 1261 | LB
1399
M. | The Medical Center at UCSF L-3 |  | 1000 | HR |  | - - - |  | P | 67 | HR |  | - - - |  | 5/92 | Admin | 5/12/92
| Neuroradiology Laboratory Renov. | [6 empty] | W | 104 | HR
| (924090) | [6 empty] | W | 829 | HR
1000
N. | SOM, HSW-8 Physiology |  | 423 | X |  | - - - |  | P | 29 | X |  | - - - |  | 7/91 | Chancellor | 7/29/91
| Laboratory Alts. (920350) | [6 empty] | W | 46 | X
[8 empty] | C | 348 | X
423
O. | SOM, U-B Biosafety Laboratory Alts. |  | 1121 | X |  | - - - |  | P | 54 | X |  | - - - |  | 1/92 | Chancellor | 1/13/92
| (920310) | [6 empty] | W | 114 | X
[8 empty] | C | 953 | X
1121
P. | SOM, LS-3 Orthopaedic Surgery |  | 1515 | X |  | - - - |  | P | 96 | X |  | - - - |  | 1/92 | Chancellor | 1/13/92
| Laboratory Alts. (920330) | [6 empty] | W | 154 | X
[8 empty] | C | 1265 | X
1515
Q. | SOM, Mt Z E1-1,2 Harold Brunn |  | 1100 | X |  | - - - |  | P | 75 | X |  | - - - |  | 1/92 | Chancellor | 1/13/92
| Bldg. Remodel (926204) | [6 empty] | W | 106 | X
[8 empty] | C | 919 | X
1100
R. | SOM, A-C Human Genome |  | 2146 | X |  | - - - |  | P | 190 | X |  | - - - |  | 1/92 | Chancellor | 1/13/92
| Research Lab. Alts. (924030) | [6 empty] | W | 206 | X
[8 empty] | C | 1750 | X
2146
S. | The Medical Center @ UCSF MZ |  | 2100 | HR | P | 125 | HR | W | 100 | HR |  | - - - |  | 7/92 | Admin | 7/21/92
| C,J Life Safety Code Corrections |  |  |  | W | 75 | HR | C | 1800 | HR
| (924210) |  |  |  |  | 200 |  |  | 1900
T. | School of Medicine, U-4 |  | 1385 | X |  | - - - |  | P | 97 | X |  | - - - |  | 2/92 | Chancellor | 12/91
| Otolaryngology Laboratory Alts. | [6 empty] | W | 120 | X
| (924000) | [6 empty] | C | 1168 | X
1385
U. | School of Dentistry, C-5 Oral & |  | 500 | X |  | - - - |  | P | 42 | X |  | - - - |  | 2/92 | Chancellor | 12/20/91
| Maxillofacial Surgery Laboratory | [6 empty] | W | 47 | X
| Alts. (924180) | [6 empty] | C | 411 | X
500
V. | School of Dentistry C-6 Growth & |  | 997 | X |  | - - - |  | P | 72 | X |  | - - - |  | 3/92 | Chancellor | 3/6/92
| Development Laboratory Alts. | [6 empty] | W | 100 | X
| (924370) | [6 empty] | C | 825 | X
997
W. | School of Medicine, HSW-16 |  | 3998 | X |  | - - - |  | P | 132 | X |  | - - - |  | 3/92 | Chancellor | 3/6/92
| Surgery Laboratory Renovations | [6 empty] | W | 273 | X
| (924300) | [6 empty] | C | 3593 | X
3998
X. | The Medical Center at UCSF MZ |  | 2500 | HR |  | - - - |  | P | 123 | HR |  | - - - |  | 6/92 | Admin | 6/25/92
| J-6, 7 Building Alts. (924330) | [6 empty] | W | 230 | HR
[8 empty] | C | 2147 | HR
2500
Y. | School of Medicine, HSE-8 |  | 2500 | G |  | - - - |  | P | 150 | G |  | - - - |  | 6/93 | Admin | 6/14/93 | 5/92 |  | 1991-94 CIP | 6690
| Physiology Laboratory Renovations |  | 4190 | X |  |  |  | P | 251 | X |  |  |  |  | ( Changed
| (924170) |  | 6690 |  |  |  |  | W | 194 | G |  |  |  |  | fund source )
[8 empty] | W | 325 | X
[8 empty] | C | 2156 | G
[8 empty] | C | 3614 | X
6690
Z. | School of Medicine, U-B Medicine |  | 1093 | X |  | - - - |  | P | 33 | X |  | - - - |  | 6/92 | Admin | 6/16/92
| Department Alts. (924450) | [6 empty] | W | 49 | X
[8 empty] | C | 1011 | X
1093
AA. | The Medical Center at UCSF MZ |  | 805 | HR | P | 40 | HR | W | 55 | HR |  | - - - |  | 8/92 | Admin | 8/11/92
| A-4E Nursing Unit Improvements |  |  |  | W | 10 | HR | C | 700 | HR
| (924270) |  |  |  |  | 50 |  |  | 755
BB. | School of Medicine, SFGH 1-1 |  | 270 | X |  | - - - |  | P | 16 | X |  | - - - |  | 5/92 | Chancellor | 5/15/92
| Gallo Research Center Alts. | [6 empty] | W | 24 | X
| (924740) | [6 empty] | C | 230 | X
270
CC. | Proctor Foundation - 95 Kirkham |  | 272 | G |  | - - - |  | P | 10 | G |  | - - - |  | 5/92 | Chancellor | 5/20/92
| 3rd Floor Laboratory Alts. (924500) | [6 empty] | W | 12 | G
[8 empty] | C | 250 | G
272
DD. | The Medical Center at UCSF Moffitt |  | 852 | HR |  | - - - |  | P | 30 | HR |  | - - - |  | 8/92 | Admin | 8/14/92
| Dumbwaiter Renewal Project | [6 empty] | W | 38 | HR
| (924650) | [6 empty] | C | 784 | HR
852
EE. | The Medical Center at UCSF MZ |  | 3024 | HR |  | - - - |  | P | 138 | HR |  | - - - |  | 9/92 | Admin | 9/30/92
| J-1, 2 and 8 Alterations (925110) | [6 empty] | W | 275 | HR
[8 empty] | C | 2611 | HR
3024
FF. | Library Release Space | ( | 18715 | ) | ( P | 749 | ) | P | 209 | G | ( C | 14885 | ) | 11/92 | Regents' | N/A | 11/89 |  | 1990-93 CIP | 19348
| Improvements (925340) |  | 6586 | G | ( W | 1156 | ) | W | 164 | G | C | 6213 | G |  | Budget |  | 10/90 |  | 1991-94 CIP | 19586
|  |  | 1300 | U | C | 1300 | U |  | 373 |  | ( E | 1925 | ) |  |  |  | 11/91 |  | 1992-95 CIP | 26571
|  |  | 26601 |  |  | 3205 | [5 empty] | 23023
GG. | Parnassus Fire Alarm and Life | ( | 6965 | ) | ( P | 292 | ) | ( C | 2111 | ) | ( C | 4387 | ) | 11/91 | Regents' | N/A | 11/89 |  | 1990-93 CIP | 8241
| Safety System (928620) |  | 2473 | HR | P | 95 | HR | C | 142 | HR | C | 2121 | HR |  | Budget |  | 10/90 |  | 1991-94 CIP | 7726
|  |  | 771 | X | P | 9 | X | C | 258 | X | C | 504 | X
|  |  | 10209 |  | ( W | 175 | ) |  | 2511 |  |  | 7012
[5 empty] | W | 115 | HR
686
HH. | Parnassus Fire Protection and | ( | 3524 | ) | ( P | 355 | ) | ( W | 126 | ) | ( W | 190 | ) | 11/91 | Regents' | N/A | 11/89 |  | 1990-93 CIP | 7856
| Water Supply System (928622) |  | 3211 | LB | P | 7 | HR | W | 104 | LB | W | 36 | HR |  | Budget |  | 10/90 |  | 1991-94 CIP | 7856
|  |  | 415 | HR | P | 13 | X | C | 57 | HR | W | 9 | X |  |  |  | 11/91 |  | 1992-93 CIP | 9096
|  |  | 1718 | U | W | 3 | HR | C | 2662 | LB | ( C | 2853 | )
|  |  | 228 | X | W | 123 | X | W | 137 | U | C | 312 | HR
|  |  | 9096 |  |  | 501 |  | C | 1581 | U | C | 445 | LB
[9 empty] | 4667 |  | C | 83 | X
3928
| Gifts (G) |  | 9358 | G |  | - - - |  |  | 3145 | G |  | 6213 | G
| Hospital Reserves (HR) |  | 17119 | HR |  | 545 | HR |  | 14105 | HR |  | 2469 | HR
| Bank Loans or Bonds (LB) |  | 71752 | LB |  | - - - |  |  | 71307 | LB |  | 445 | LB
| Regents' Appropriations (U) |  | 3018 | U |  | 1300 | U |  | 1718 | U |  | - - -
| Other (X) |  | 23022 | X |  | 391 | X |  | 21479 | X |  | 1152 | X
| TOTAL |  | 124269 |  |  | 2236 |  |  | 111754 |  |  | 10279
| STATE FUNDS | ( | 29204 | ) | ( | 2727 | ) | ( | 2237 | ) | ( | 24240 | )

## Santa Barbara
SANTA BARBARA CAMPUS
1991-92 NON-STATE CAPITAL BUDGET
($000)
[9 empty] | C U R R E N T S T A T U S | [8 empty] | PRIOR ACTION/COMMENTS
|  |  | Project | [8 empty] | Beyond |  |  |  | Approval
| Project |  | Cost |  |  | Prefunded |  |  | 1991-92 |  |  | 1991-92 |  | Action |  | Letter | Date | Action | Cost
A. | Rob Gym Lighting (980441) |  | 196 | X |  | - - - |  | P | 15 | X |  | - - - |  | 9/91 | Chancellor | 9/23/91
|  |  | 197 | R |  |  |  | W | 19 | X
|  |  | 393 |  |  |  |  | C | 162 | X
[8 empty] | C | 197 | R
393
B. | Military Science Replacement Facility |  | 1592 | X |  | - - - |  | P | 81 | X |  | - - - |  | 2/92 | Chancellor | 2/4/92
| (981000) | [6 empty] | W | 54 | X
[8 empty] | C | 1457 | X
1592
C. | Marine Science Trailers (981010) |  | 300 | X |  | - - - |  | P | 20 | X |  | - - - |  | 1/92 | Chancellor | 1/28/92
[8 empty] | W | 30 | X
[8 empty] | C | 250 | X
300
D. | Energy Conservation Bond Project |  | 3415 | LB |  | - - - |  | P | 80 | LB |  | - - - |  | 7/92 | Admin | 7/10/92
| (988822) | [6 empty] | W | 176 | LB
[8 empty] | C | 3159 | LB
3415
E. | University Center Expansion |  | 761 | X | P | 473 | X | P | 202 | X | C | 86 | X | 1/94 | Regents | 1/20/94 | 6/90 | 1989-92 CIP | 15534
| (980590) |  | 675 | R | W | 475 | R | P | 200 | R | C | 300 | G |  | (Finance Action) |  | 11/91 | 1990-93 CIP | 19263
|  |  | 200 | N | C | 11770 | LB | W | 200 | N | C | 1400 | LB
|  |  | 300 | G | E | 1791 | LB | W | 251 | LB | E | 100 | LB
|  |  | 18913 | LB |  | 14509 |  | C | 3601 | LB |  | 1886
|  |  | 20849 | [5 empty] | 4454
F. | Main Campus Water Loop |  | 1301 | U | P | 30 | X | W | 138 | U |  | - - - |  | 2/93 | Admin | 2/10/93 |  | Originally slated as a State-funded
| Improvements (986056) |  | 30 | X |  |  |  | C | 1163 | U | [7 empty] | project with "P" from University
|  |  | 1331 | [5 empty] | 1301 | [8 empty] | Funds
G. | NO PROJECT
H. | Recreation Center/Aquatics Complex |  | 12987 | LB |  | - - - |  | P | 629 | X |  | - - - |  | 2/93 | Admin | 2/2/93 | 10/90 | 1989-92 CIP | 13873
| (980440) |  | 628 | R |  |  |  | P | 99 | R | [6 empty] | 1/91 | 1990-93 CIP | 13798
|  |  | 1029 | X |  |  |  | W | 519 | R | [6 empty] | (* LB reduced)
|  |  | 14644 |  |  |  |  | W | 65 | X | [6 empty] | 11/91 | 1991-94 CIP | 14244
[8 empty] | C | 10 | R | [6 empty] | (** LB increased; X & R reduced)
[8 empty] | C | 12724 | LB
[8 empty] | C | 335 | X
[8 empty] | E | 263 | LB
14644
I. | Humanities and Social Sciences |  | 944 | X |  | - - - |  | P | 944 | X | ( W | 1193 | ) | 11/95 | Regents' | N/A | 10/90 | 1991-94 CIP | 30400
| Building (980830) | ( | 31122 | ) | [6 empty] | ( C | 27814 | ) |  | Budget |  | 11/91 | 1992-95 CIP | 31126
|  |  | 32066 | [7 empty] | ( E | 2115 | ) |  |  |  | 11/92 | 1993-96 CIP | 31989
[12 empty] | 31122 |  |  |  |  | 11/93 | 1994-97 CIP | 32032
[17 empty] | 11/94 | 1995-98 CIP | 32056
| Gifts (G) |  | 300 | G |  | - - - |  |  | - - - |  |  | 300 | G
| Bank Loans or Bonds (LB) |  | 35315 | LB |  | 13561 | LB |  | 20254 | LB |  | 1500 | LB
Reserves other than University
| Registration Fee (N) |  | 200 | N |  | - - - |  |  | 200 | N |  | - - -
| Registration Fees (R) |  | 1500 | R |  | 475 | R |  | 1025 | R |  | - - -
| Regents' Appropriations (U) |  | 1301 | U |  | - - - |  |  | 1301 | U |  | - - -
| Other (X) |  | 4852 | X |  | 503 | X |  | 4263 | X |  | 86 | X
| TOTAL |  | 43468 |  |  | 14539 |  |  | 27043 |  |  | ---
| STATE FUNDS | ( | 31122 | ) | ( | - - - | ) | ( | - - - | ) | ( | 31122 | )

## Santa Cruz
SANTA CRUZ CAMPUS
1991-92 NON-STATE CAPITAL BUDGET
($000)
[8 empty] | C U R R E N T S T A T U S | [8 empty] | PRIOR ACTION/COMMENTS
|  | Project | [8 empty] | Beyond |  |  |  | Approval
| Project | Cost |  |  | Prefunded |  |  | 1991-92 |  |  | 1991-92 |  | Action |  | Letter | Date |  | Action | Cost
A. | Humanities Graduate Student | 445 | X |  | - - - |  | P | 19 | X |  | - - - |  | 7/91 | Admin | 7/23/91
| Annex at Oakes College (970935) | [5 empty] | W | 21 | X
[7 empty] | C | 379 | X
[7 empty] | E | 26 | X
445
B. | College Nine Residence Halls | 1633 | N |  | - - - |  | P | 572 | N |  | - - - |  | 9/91 | Regents | 5/15/92
| (976292) | 15284 | LB |  |  |  | W | 637 | N
|  | 16917 |  |  |  |  | C | 424 | N
[7 empty] | C | 14301 | LB
[7 empty] | E | 983 | LB
16917
C. | College Nine Apartments (976290) | 14171 | LB | P | 355 | N |  | - - - |  | P | 178 | N | 9/97 | Regents | 9/29'97 | 1/91 |  | 1990-93 CIP | 9467
|  | 2416 | N | W | 328 | N |  |  |  | W | 831 | LB |  |  |  | 8/91 |  | 1991-94 CIP | 9730
|  | 16587 |  | C | 6426 | LB |  |  |  | C | 6914 | LB |  |  |  | 5/92 |  | 1991-94 CIP | 10280
|  |  |  | C | 1005 | N |  |  |  |  | 7923 |  |  |  |  | 10/93 |  | 1993-96 CIP* | 10280
|  |  |  | E | 550 | N | [11 empty] | (*admin - change of fund source)
8664
D. | LML Discovery Center (970940) | 550 | X |  | - - - |  | P | 23 | X | P | 222 | G |  | Chancellor | delegated | 6/91 |  | 1991-94 CIP | 550
| (previously titled the Marine | 4350 | G |  |  |  | W | 28 | X | W | 217 | G
| Sciences Teaching Laboratory) | 4900 |  |  |  |  | C | 489 | X | C | 3911 | G
[7 empty] | E | 10 | X |  | 4350
550
| Bank Loans or Bonds (LB) | 29455 | LB |  | 6426 | LB |  | 15284 | LB |  | 7745 | LB
| Gift Funds (G) | 4350 | G |  | - - - |  |  | - - - |  |  | 4350 | G
Reserves other than University
| Registration Fees (N) | 4049 | N |  | 2238 | N |  | 1811 | N |  | 178 | N
| Other (X) | 995 | X |  | - - - |  |  | 995 | X |  | - - -
| TOTAL | 38849 |  |  | 8664 |  |  | 18090 |  |  | 12273

## ANR
DIVISION OF
AGRICULTURE AND NATURAL RESOURCES
1991-92 NON-STATE CAPITAL BUDGET
($000)
[9 empty] | C U R R E N T S T A T U S | [7 empty] | PRIOR ACTION/COMMENTS
|  |  | Project | [8 empty] | Beyond |  |  |  | Approval
| Project |  | Cost |  |  | Prefunded |  |  | 1991-92 |  |  | 1991-92 |  | Action |  | Letter | Date | Action | Cost
A. | West Side Irrigation System |  | 25 | U |  | --- |  | P | 25 | U | ( W | 36 | ) | 11/92 | Regents' | N/A | 11/91 | 1992-95 CIP | 776
| (931950) | ( | 756 | ) | [6 empty] | ( C | 720 | ) |  | Budget
|  |  | 781 | [8 empty] | 756
| Regents' Appropriation (U) |  | 25 | U |  | --- |  |  | 25 | U |  | ---
| TOTAL |  | 25 |  |  | --- |  |  | 25 |  |  | ---
| STATE FUNDS | ( | 756 | ) | ( | --- | ) | ( | --- | ) | ( | 756 | )

## U-Wide
OFFICE OF THE PRESIDENT
1991-92 NON-STATE CAPITAL BUDGET
($000)
[6 empty] | C U R R E N T S T A T U S | [6 empty] | PRIOR ACTION/COMMENTS
|  | Project | [5 empty] | Beyond |  |  | Approval
| Project | Cost |  | Prefunded |  | 1991-92 |  | 1991-92 | Action |  | Letter | Date | Action | Cost
A. | University of California, | 29900 | LB | - - - | P | 793 | LB | - - - | 11/91 | Regents | N/A | 9/92 | Project deferred indefinitely
| Washington, D.C. Center |  |  |  | W | 905 | LB | [5 empty] | per President Gardner
[5 empty] | C | 26702 | LB
[5 empty] | E | 1500 | LB
29900
| Bank Loans or Bonds (LB) | 29900 | LB | - - - |  | 29900 | LB | - - -
| TOTAL | 29900 |  | - - - |  | 29900 |  | - - -

## Summary
1991-92 NON-STATE FUNDED PROJECTS
($ in thousands)
| UCB | UCD | UCI |  | UCLA | UCR | UCSD | UCSF | UCSB | UCSC | OTHER | TOTAL
Federal (F) | 400 | 443 | - - - |  | - - - | - - - | - - - | - - - | - - - | - - - | - - - | 843
Gifts (G) | 400 | - - - | - - - |  | 4249 | 1129 | 4450 | 3145 | - - - | - - - | - - - | 13373
Hospital Reserves (HR) | - - - | 7778 | - - - |  | 11290 | - - - | 3422 | 14105 | - - - | - - - | - - - | 36595
Bank Loans or Bonds (LB) | 4273 | 18440 | - - - |  | 19895 | - - - | 45007 | 71307 | 20254 | 15284 | 29900 | 224360
Reserves Other Than University
Registration Fees (N) | - - - | 3892 | - - - |  | 350 | - - - | 960 | - - - | 200 | 1811 | - - - | 7213
Funds From Sources Yet To Be
Determined (Q) | - - - | - - - | - - - |  | - - - | - - - | - - - | - - - | - - - | - - - | - - - | 0
Registration Fees (R) | - - - | 140 | - - - |  | - - - | - - - | 2651 | - - - | 1025 | - - - | - - - | 3816
Regents' Appropriations (U) | 785 | - - - | 1225 |  | - - - | - - - | 473 | 1718 | 1301 | - - - | 25 | 5527
Other (X) | 475 | 607 | 745 |  | 965 | 3462 | 7323 | 21479 | 4263 | 995 | - - - | 40314
TOTAL | 6333 | 31300 | 1970 | 0 | 36749 | 4591 | 64286 | 111754 | 27043 | 18090 | 29925 | 332041