## Summary
1992-93 NON-STATE FUNDED PROJECTS
($ in thousands)
| UCB | UCD | UCI | UCLA | UCR | UCSD | UCSF | UCSB | UCSC | OTHER | TOTAL | PERCENT OF TOTAL
Bank Loans or Bonds (LB) | 33691 | 200137 | 10053 | 57600 | 4548 | 63155 | 90332 | 14310 | 302 | 0 | 474128 | 75.32%
Other (X) | 2302 | 6396 | 109 | 7768 | 0 | 10365 | 13231 | 17491 | 0 | 500 | 58162 | 9.239%
Gifts (G) | 15340 | 10 | 14430 | 10207 | 1000 | 2780 | 16783 | 63 | 0 | 205 | 60818 | 9.661%
Federal (F) | 0 | 1136 | 0 | 0 | 0 | 0 | 2000 | 0 | 0 | 373 | 3509 | 0.5574%
Hospital Reserves (HR) | 0 | 3281 | 0 | 316 | 0 | 0 | 22739 | 0 | 0 | 0 | 26336 | 4.184%
Registration Fees (R) | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 3230 | 0 | 0 | 3430 | 0.5449%
Reserves other than Registration Fees (N) | 638 | 0 | 0 | 600 | 583 | 0 | 0 | 750 | 547 | 0 | 3118 | 0.4953%
TOTAL | 51971 | 210960 | 24592 | 76691 | 6131 | 76300 | 145085 | 35844 | 849 | 1078 | 629501 | 100%
INDIVIDUAL CAMPUS PERCENT OF TOTAL | 8.256% | 33.51% | 3.907% | 12.18% | 0.9739% | 12.12% | 23.05% | 5.694% | 0.1349% | 0.1712% | 100%
STATE FUNDS | 16774 | 1044 | 1278 | 3756 | 794 | 11027 | 19272 | 3937 | 0 | 0 | 57882

## Berkeley
BERKELEY CAMPUS
1992-93 NON-STATE CAPITAL BUDGET
($ in thousands)
[6 empty] | C U R R E N T S T A T U S | [10 empty] | PRIOR ACTION/COMMENTS
|  |  | Project | [8 empty] | Beyond |  |  |  | Approval
| Project |  | Cost |  |  | Prefunded |  |  | 1998-99 |  |  | 1998-99 |  | Action |  | Letter | Date | Action | Cost
A. | College of Chemistry, Unit 3 |  | 14288 | G | P | 30 | X | ( C | 13182 | ) |  | - - - |  | 9/92 | Regents | 9/29/92 | 10/82 | 1983-86 CIP | 22199
| (912390) |  | 10440 | LB | P | 518 | G | C | 8235 | LB | [6 empty] | 10/83 | 1984-87 CIP | 30100
|  |  | 30 | X | W | 2221 | G | C | 10549 | G | [6 empty] | 5/89 | 1983-86 & 1988-91 CIP | 32846
|  | ( | 13182 | ) |  | 2769 |  | E | 2205 | LB | [6 empty] | 11/90 | 1991-94 CIP | 35277
|  |  | 37940 |  |  |  |  | E | 1000 | G | [6 empty] | 9/91 | 1992-95 CIP | 37940
35171
B. | Business Administration Building |  | 38400 | G | S | 75 | G | C | 6600 | LB |  | - - - |  | 12/92 | Admin | 12/23/92 | 10/82 | 1983-86 CIP | 25720
| (911480) |  | 6600 | LB | P | 1425 | G | [9 empty] | 5/87 | 1986-89 CIP | 36000
|  |  | 45000 |  | W | 2500 | G | [9 empty] | 2/91 | 1990-93 CIP | 45000
[5 empty] | C | 34400 | G
38400
C. | Silver Lab Expansion (912341) |  | 12979 | LB |  | - - - |  | P | 550 | LB | C | 150 | F | ??/98 | Admin | pending | 1/93 | 1992-95 CIP | 12760
|  |  | 150 | F |  |  |  | W | 900 | LB | C | 337 | X |  |  |  | 9/93 | Finance Authorization | 13870
|  |  | 561 | X |  |  |  | C | 11439 | LB | E | 224 | X |  |  |  | 10/97 | 1997-00 CIP | 14020
|  |  | 13690 |  |  |  |  | E | 90 | LB |  | 711
12979
D. | Eshleman Hall & King Union Fire |  | 2095 | X |  | - - - |  | P | 166 | X |  | - - - |  | 3/93 | Admin | 3/17/93
| Alarm & Fire Sprinkler Systems | [6 empty] | W | 337 | X
| (912667) | [6 empty] | C | 1592 | X
2095
E. | Strawberry Field Expansion |  | 1995 | G |  | - - - |  | P | 115 | G |  | - - - |  | 1/93 | Chancellor | 1/20/93
| (912658) | [6 empty] | W | 225 | G
[8 empty] | C | 1655 | G
1995
F. | 2100 Channing Student Housing |  | 11700 | LB | A | 930 | LB | A | 304 | LB |  | - - - |  | 6/93 | Regents | 6/14/93 | 9/87 | 1987-90 CIP | 8426
| (912664) (Formerly: Shattuck |  |  |  | P | 259 | LB | P | 521 | LB
| and Channing Student Housing) |  |  |  | W | 319 | LB | W | 151 | LB
[5 empty] | C | 6663 | LB | C | 2223 | LB
[5 empty] | E | 255 | LB | E | 75 | LB
[6 empty] | 8426 |  |  | 3274
G. | NO PROJECT
H. | Warren Hall: Suite 158 Teaching |  | 430 | N |  | - - - |  | P | 25 | N |  | - - - |  | 4/93 | Chancellor | 4/22/93
| Laboratory Renovation for | [6 empty] | W | 56 | N
| Biomedical and Environmental | [6 empty] | C | 349 | N
| Health Science (912660) | [7 empty] | 430
I. | Seismic Safety Corrections, Earth |  | 975 | LB | P | 100 | LB | C | 100 | LB |  | - - - |  | 6/93 | Admin | 6/23/93 | 12/92 | 1991-94 CIP | 875
| Sciences Building (912613) |  |  |  | W | 150 | LB
[5 empty] | C | 625 | LB
875
J. | Seismic Safety Corrections, North |  | 918 | LB | P | 35 | LB | C | 218 | LB |  | - - - |  | 6/93 | Admin | 6/23/93 | 12/92 | 1991-94 CIP | 700
| Gate Hall, Step 1 (912656) |  |  |  | W | 60 | LB
[5 empty] | C | 605 | LB
700
K. | Seismic Safety Corrections, |  | 6157 | LB | P | 262 | LB | C | 80 | LB |  | - - - |  | 6/93 | Admin | 6/23/93 | 5/90 | 1989-92 CIP | 8200
| University Hall (912585) |  |  |  | W | 489 | LB
[5 empty] | C | 5326 | LB
6077
L. | Warren Hall: Suite 141 Research |  | 208 | N |  | - - - |  | P | 25 | X |  | - - - |  | 6/93 | Chancellor | 6/28/93
| Laboratory, Remodeling for BEHS |  | 207 | X |  |  |  | W | 30 | X
| (912662) |  | 415 |  |  |  |  | C | 208 | N
[8 empty] | C | 152 | X
415
M. | Life Sciences Renovation for | ( | 48199 | ) | (P | 938 | ) | (E | 3592 | ) | C | 18083 | X | 1/94 | Regents' | 3/30/94 | 10/85 | 1986-89 CIP | 62357
| Ecology and Evolutionary Biology |  | 24049 | G | P | 1626 | G | E | 1796 | G |  |  |  |  | Admin |  | 11/86 | 1987-90 CIP | 62357
| (912274) |  | 19083 | X | P | 85 | X |  | 5388 | [7 empty] | 11/87 | 1988-91 CIP | 67746
|  |  | 91331 |  | (W | 2603 | ) | [9 empty] | 11/88 | 1989-92 CIP | 69547
[5 empty] | W | 94 | G | [9 empty] | 11/89 | 1990-93 CIP | 69936
[5 empty] | W | 69 | X | [9 empty] | 10/90 | 1991-94 CIP | 70035
[5 empty] | (C | 41066 | ) | [9 empty] | 11/91 | 1992-93 CIP | 70080
[5 empty] | C | 20533 | G | [9 empty] | 10/92 | 1993-94 CIP | 73152
[5 empty] | C | 750 | X
67764
| Gift Funds (G) |  | 78732 | G |  | 63392 | G |  | 15340 | G |  | 0
| Federal (F) |  | 150 | F |  | 0 |  |  | 0 |  |  | 150 | F
| Bank Loans or Bonds (LB) |  | 49769 | LB |  | 16078 | LB |  | 33691 | LB |  | 0
Reserves other than University
| Registration Fee (N) |  | 638 | N |  | 0 |  |  | 638 | N |  | 0
| Others (X) |  | 21976 | X |  | 30 | X |  | 2302 | X |  | 18644 | X
| TOTAL |  | 151265 |  |  | 79500 |  |  | 51971 |  |  | 18794
| STATE FUNDS | ( | 61381 | ) | ( | 44607 | ) | ( | 16774 | ) | ( | 0 | )

## Davis
DAVIS CAMPUS
1992-93 NON-STATE CAPITAL BUDGET
($ in thousands)
[9 empty] | C U R R E N T S T A T U S | [8 empty] | PRIOR ACTION/COMMENTS
|  |  | Project | [8 empty] | Beyond |  |  |  | Approval
| Project |  | Cost |  |  | Prefunded |  |  | 1992-93 |  |  | 1992-93 |  | Action |  | Letter | Date | Action | Cost
A. | UCDMC Inpatient Radiology |  | 10121 | LB |  | - - - |  | P | 823 | LB |  | - - - |  | 8/92 | Regents | 8/24/92
| Expansion/Renovation (935100) | [6 empty] | W | 819 | LB
[8 empty] | C | 8479 | LB
10121
B. | UCDMC Parking Structure II |  | 12904 | LB |  | - - - |  | P | 629 | LB |  | - - - |  | 8/92 | Regents | 8/24/92
| (936573) | [6 empty] | W | 944 | LB
[8 empty] | C | 11217 | LB
[8 empty] | E | 114 | LB
12904
C. | UCD School of Medicine Research |  | 15625 | LB |  | - - - |  | P | 913 | LB |  | - - - |  | 8/92 | Regents | 8/24/92
| Building III (935030) | [6 empty] | W | 1370 | LB
[8 empty] | C | 12304 | LB
[8 empty] | E | 1038 | LB
15625
D. | UCDMC Tower II Project (934700) |  | 148320 | LB |  | - - - |  | P | 11100 | LB | C | 14428 | HR | 3/99 | Admin | 3/4/99 | 9/92 | 1992-95 CIP | 155748
|  |  | 14428 | HR |  |  |  | W | 8900 | LB | [6 empty] | 11/94 | 1994-97 CIP | 155748
|  |  | 162748 |  |  |  |  | C | 128320 | LB | [7 empty] | change of scope
148320
E. | UCDMC Central Processing Et0 |  | 474 | HR |  | - - - |  | P | 14 | HR |  | - - - |  | 11/92 | Admin | 11/03/92
| Sterilizer Retrofit and Exhaust | [6 empty] | W | 60 | HR
| System (935190) | [6 empty] | C | 400 | HR
474
F. | Sproul Hall Seismic Upgrade |  | 585 | F | P | 200 | LB | C | 585 | F |  | - - - |  | 1/93 | Admin | 1/7/93 | 7/90 | 1989-92 CIP | 4900
| (938706) |  | 4900 | LB | W | 335 | LB
|  |  | 5485 |  | C | 4365 | LB
4900
G. | Center for Comparative Medicine |  | 14006 | LB |  | - - - |  | P | 298 | LB | P | 287 | LB | 5/94 | Admin: | 9/12/94 | 1/93 | 1992-95 CIP | 14240
| (CCM) (935070) |  | 1400 | F |  |  |  | W | 406 | LB | P | 40 | F |  | Regents
|  |  | 15406 |  |  |  |  | C | 11688 | LB | W | 80 | F |  | (May - Design)
[8 empty] | E | 775 | LB | C | 552 | LB
[9 empty] | 13167 |  | C | 1280 | F
2239
H. | Neurosciences Communications |  | 615 | X |  | - - - |  | P | 30 | X |  | - - - |  | 1/93 | Chancellor | 1/5/93
| Infrastructure (931700) | [6 empty] | W | 36 | X
[8 empty] | C | 549 | X
615
I. | Academic Surge Tenant |  | 410 | X |  | - - - |  | P | 23 | X |  | - - - |  | 1/93 | Chancellor | 1/6/93
| Improvements for Engineering | [6 empty] | W | 27 | X
| (931670) | [6 empty] | C | 360 | X
410
J. | Life Sciences Expansion: Briggs |  | 2634 | X |  | - - - |  | P | 161 | X |  | - - - |  | 2/93 | Chancellor | 2/16/93
| Hall Addition Courtyard Level Shell | [6 empty] | W | 119 | X
| Space (931650) | [6 empty] | C | 2354 | X
2634
K. | UCDMC Radiology Interim Project |  | 481 | HR |  | - - - |  | P | 35 | HR | C | 124 | HR | 7/96 | Chancellor | delegated | 5/93 | 1992-95 CIP | 357
| (935210) | [6 empty] | W | 48 | HR
[8 empty] | C | 274 | HR
357
L. | Academic Surge Building Tenant |  | 326 | F |  | - - - |  | P | 10 | X |  | - - - |  | 4/93 | Chancellor | 4/12/93
| Improvements for Bohart Museum |  | 10 | G |  |  |  | W | 25 | X
| (931710) |  | 354 | X |  |  |  | C | 310 | X
|  |  | 690 |  |  |  |  | E | 326 | F
[8 empty] | E | 10 | G
[8 empty] | E | 9 | X
690
M. | Growth Chamber Building (931690) |  | 1204 | X |  | - - - |  | P | 25 | X | C | 135 | X |  | Chancellor | delegated | 5/93 | 1992-95 CIP | 1069
[8 empty] | W | 92 | X
[8 empty] | C | 952 | X
1069
N. | Renovate Surge I and II for IGA |  | 495 | X |  | - - - |  | P | 10 | X |  | - - - |  | 5/93 | Chancellor | 5/28/93
| (931730) | [6 empty] | W | 25 | X
[8 empty] | C | 400 | X
[8 empty] | E | 60 | X
495
O. | Life Sciences Expansion: |  | 1066 | U | P | 1066 | U | ( W | 1044 | ) | ( C | 24664 | ) | 11/92 | Regents' | N/A | 10/90 | 1991-94 CIP | 19124
| Briggs Hall Addition (931120) |  | 3224 | X | [6 empty] | E | 3224 | X |  | Budget |  | 10/91 | 1992-95 CIP | 29146
|  | ( | 25708 | ) | [7 empty] | 27888
29998
P. | 48th and 49th Street Relocation |  | 2450 | HR |  | - - - |  | P | 120 | HR |  | - - - |  | 9/93 | Admin | 9/27/93
| (935220) | [6 empty] | W | 180 | HR
[8 empty] | C | 2150 | HR
2450
Q. | CEPRAP Greenhouse Facility |  | 225 | F |  | - - - |  | P | 16 | F |  |  |  | 6/93 | Chancellor | 6/28/93
| (931680) |  | 150 | X |  |  |  | W | 42 | F
|  |  | 375 |  |  |  |  | C | 167 | F
[8 empty] | C | 150 | X
375
R. | DANR Support Services Building |  | 669 | X |  | - - - |  | P | 8 | X |  | - - - |  | 9/93 | Admin | 9/15/93
| (931800) | [6 empty] | W | 33 | X
[8 empty] | C | 628 | X
669
| Federal Funds (F) |  | 1136 | F |  | 0 |  |  | 1136 | F |  | 0
| Gifts (G) |  | 10 | G |  | 0 |  |  | 10 | G |  | 0
| Hospital Reserve Funds (HR) |  | 17833 | HR |  | 0 |  |  | 3281 | HR |  | 14552 | HR
| Bank Loans or Bonds (LB) |  | 205876 | LB |  | 4900 | LB |  | 200137 | LB |  | 839 | LB
| Regents' Appropriations (U) |  | 1066 | U |  | 1066 | U |  | 0 |  |  | 0
| Other (X) |  | 9755 | X |  | 0 |  |  | 6396 | X |  | 3359 | X
| TOTAL |  | 235676 |  |  | 5966 |  |  | 210960 |  |  | 18750
| STATE FUNDS | ( | 25708 | ) | ( | 0 | ) | ( | 1044 | ) | ( | 24664 | )
235676

## Irvine
IRVINE CAMPUS
1992-93 NON-STATE CAPITAL BUDGET
($ in thousands)
[9 empty] | C U R R E N T S T A T U S | [8 empty] | PRIOR ACTION/COMMENTS
|  |  | Project | [8 empty] | Beyond |  |  |  | Approval
| Project |  | Cost |  |  | Prefunded |  |  | 1992-93 |  |  | 1992-93 |  | Action |  | Letter | Date | Action | Cost
A. | Neuroscience Research Facility |  | 10781 | G |  | - - - |  | P | 1200 | G | C | 2649 | X | 3/96 | Admin | 3/25/96 | 1/93 | 1992-95 CIP | 21125
| (994055) |  | 10053 | LB |  |  |  | W | 1455 | G | C | 781 | G |  |  |  | 7/95 | 1994-97 CIP | 22702
|  |  | 2649 | X |  |  |  | C | 7345 | G |  | 3430
|  |  | 23483 |  |  |  |  | C | 10053 | LB
20053
B. | Bonney Center Expansion |  | 4430 | G |  | - - - |  | P | 274 | G |  | - - - |  | 4/93 | Chancellor | 4/15/93
| (991715) | [6 empty] | W | 66 | G
[8 empty] | C | 4090 | G
4430
C. | Social Sciences Unit 2 (992060) |  | 1225 | U | P | 1225 | U | (W | 1278 | ) | (C | 27698 | ) | 11/92 | Regents' | N/A | 10/90 | 1991-94 CIP | 32992
|  | ( | 31798 | ) | [6 empty] | (E | 2822 | ) |  | Budget |  | 10/91 | 1992-95 CIP | 33770
|  |  | 33023 | [8 empty] | 30520
D. | Science Lecture Hall Building |  | 28 | X |  | - - - |  | P | 28 | X | (W | 35 | ) | 11/92 | Regents' | N/A | 10/91 | 1992-95 CIP | 1103
| Alterations and Seismic | ( | 1123 | ) | [6 empty] | (C | 834 | ) |  | Budget
| Improvements (991030) |  | 1151 | [7 empty] | (E | 254 | )
1123
E. | Gateway Building Seismic |  | 163 | X |  | - - - |  | P | 81 | X | (W | 89 | ) | 11/92 | Regents' | N/A
| Improvements (991235) | ( | 1148 | ) | [6 empty] | W | 13 | X |  | Budget
|  |  | 1311 | [7 empty] | (C | 1059 | )
[11 empty] | C | 69 | X
1230
| Gifts (G) |  | 15211 | G |  | 0 |  |  | 14430 | G |  | 781 | G
| Bank Loans or Bonds (LB) |  | 10053 | LB |  | 0 |  |  | 10053 | LB |  | 0
| Regents' Appropriations (U) |  | 1225 | U |  | 1225 | U |  | 0 |  |  | 0
| Others (X) |  | 2840 | X |  | 0 |  |  | 109 | X |  | 2731 | X
| TOTAL |  | 29329 |  |  | 1225 |  |  | 24592 |  |  | 3512
| STATE FUNDS | ( | 34069 | ) | ( | - - - | ) | ( | 1278 | ) | ( | 32791 | )

## Los Angeles
LOS ANGELES CAMPUS
1992-93 NON-STATE CAPITAL BUDGET
($ in thousands)
[9 empty] | C U R R E N T S T A T U S | [8 empty] | PRIOR ACTION/COMMENTS
|  |  | Project | [8 empty] | Beyond |  |  |  | Approval
| Project |  | Cost |  |  | Prefunded |  |  | 1992-93 |  |  | 1992-93 |  | Action |  | Letter | Date |  | Action | Cost
A. | Doris & Louis Factor Health |  | 6500 | G |  | - - - |  | S | 221 | G |  | - - - |  | 7/92 | Regents | 8/24/92
| Sciences Building 8, 9 and 10 | [6 empty] | P | 211 | G
| Jonsson Comprehensive Cancer | [6 empty] | W | 319 | G
| Center Alterations (945460) | [6 empty] | C | 5749 | G
6500
B. | Anderson Graduate School of |  | 26466 | G | P | 2670 | G | E | 2907 | G | C | 593 | X | 11/96 | Admin | 12/5/96 | 1/88 |  | 1987-90 CIP | 67234
| Management (942500) | ( | 27141 | ) | (W | 1315 | ) |  |  |  | C | 27200 | LB |  |  |  | 11/88 |  | 1989-92 CIP | 59266
|  |  | 593 | X | W | 2950 | G |  |  |  |  | 27793 |  |  |  |  | 11/89 |  | 1990-93 CIP | 65840
|  |  | 27200 | LB | (C | 25826 | ) | [9 empty] | 3/91 |  | 1990-93 CIP | 67692
|  |  | 81400 |  | C | 17939 | G | [9 empty] | 6/95 |  | 1994-97 CIP | 79290
50700
C. | UCLA Medical Center Pediatric |  | 1650 | HR | P | 82 | HR | C | 316 | HR |  | - - - |  | 9/92 | Admin | 9/24/92 | 1/89 |  | 1988-91 CIP | 1334
| Catheterization Laboratory |  |  |  | W | 158 | HR
| Alterations (945290) |  |  |  | C | 1094 | HR
1334
D. | Ackerman Union Life Safety |  | 38700 | LB |  | - - - |  | P | 3000 | LB | C | 11800 | LB | 3/97 | Regents | pending | 9/87 |  | 1987-90 CIP | 5500
| Renovation/Building Expansion |  | 2500 | X |  |  |  | W | 6000 | LB | [6 empty] | 3/88 |  | 1988-91 CIP | 17543
| (940376) |  | 600 | N |  |  |  | C | 16900 | LB | [6 empty] | 3/91 |  | 1990-93 CIP ("P" only) | 888
|  |  | 200 | R |  |  |  | C | 2500 | X | [6 empty] | 9/92 |  | 1992-95 CIP | 30200
|  |  | 42000 |  |  |  |  | C | 600 | N
[8 empty] | C | 200 | R
[8 empty] | E | 1000 | LB
30200
E. | Kerckhoff Hall Life Safety |  | 30700 | LB |  | - - - |  | P | 3070 | LB |  | - - - |  | 3/97 | Admin | pending | 9/87 |  | Part of Ackerman | N/A
| Renovation (948790) | [6 empty] | W | 1073 | LB | [6 empty] | 3/88 |  | Part of Ackerman | N/A
[8 empty] | C | 26557 | LB | [6 empty] | 3/91 |  | 1990-93 CIP ("P" only) | 852
[9 empty] | 30700 | [7 empty] | 9/92 |  | 1992-95 CIP | 27300
F. | Health Sciences Building -- |  | DELETED |  |  | - - - |  |  | - - - |  |  | - - - |  | 9/92 | Deleted
| Medical Center A-Level | [13 empty] | by Campus
Ethylene Oxide Sterilizer
Alts. (945820)
G. | Chemistry and Biological |  | 7500 | G | (P | 1350 | ) | (E | 1200 | ) |  | - - - |  | 11/91 | Regents' | N/A | 11/85 |  | 1986-89 CIP | 36805
| Sciences Addition (941080) | ( | 40234 | ) | (W | 1486 | ) | [7 empty] | Budget |  | 11/86 |  | 1987-90 CIP | 36075
|  |  | 47734 |  | (C | 36198 | ) | [9 empty] | 11/87 |  | 1988-91 CIP | 36805
[5 empty] | C | 7500 | G | [9 empty] | 11/89 |  | 1990-93 CIP | 36891
[6 empty] | 46534 | [10 empty] | 10/90 |  | 1991-94 CIP | 43462
[17 empty] | 11/91 |  | 1992-95 CIP | 47711
H. | Electrical Distribution System, |  | 317 | X | (P | 100 | ) | (C | 2556 | ) |  | - - - |  | 11/91 | Regents' | N/A | 10/88 |  | 1989-92 CIP | 2943
| Step 3 (946112) | ( | 2816 | ) | (W | 160 | ) | [7 empty] | Budget |  | 10/89 |  | 1990-93 CIP | 3046
|  |  | 3133 |  | PW | 30 | X
[5 empty] | C | 287 | X
577
I. | Medical Plaza 300 1st Floor |  | 510 | X |  | - - - |  | P | 30 | X |  | - - - |  | 10/92 | Chancellor | 10/2/92
| Psychiatry Shell Improvements | [6 empty] | W | 100 | X
| (945088) | [6 empty] | C | 380 | X
510
J. | Molecular Neurosciences |  | 48260 | G |  | - - - |  |  | - - - |  | P | 2508 | G | 3/96 | Regents | pending | 1/93 |  | 1992-95 CIP | 38905
| Research Center (945930) | [9 empty] | W | 2056 | G
[11 empty] | C | 43246 | G
[11 empty] | E | 450 | G
48260
K. | Science and Technology |  | 45000 | LB |  | - - - |  |  | - - - |  | P | 2913 | LB | 9/95 | Admin | 9/21/95 | 3/90 |  | 1989-92 CIP | 55775
| Research Building (942030) | [9 empty] | W | 2321 | LB |  |  |  | 5/93 |  | 1992-95 CIP | 47794
| (Formerly: Institute of | [9 empty] | C | 34766 | LB
| Plasma and Fusion | [9 empty] | E | 5000 | LB
| Research, Center for | [10 empty] | 45000
Advanced Accelerators)
L. | Wooden Center East Addition |  | 4455 | X |  | - - - |  | P | 167 | X |  | - - - |  | 6/93 | Chancellor | 6/2/93
| (940820) | [6 empty] | W | 215 | X
[8 empty] | C | 4073 | X
4455
M. | Wilson Center for Medical |  | 350 | G |  | - - - |  | P | 66 | X |  | - - - |  | 6/93 | Chancellor | 6/2/93
| Students at Jerry Lewis Building |  | 200 | X |  |  |  | W | 58 | X
| (945750) |  | 550 |  |  |  |  | C | 56 | X
[8 empty] | C | 350 | G
[8 empty] | E | 20 | X
550
N. | Campus Fire Alarm System |  | 103 | X |  | - - - |  | P | 103 | X | (W | 111 | ) | 11/92 | Regents' | N/A
| Upgrade, Phase 1 (946222) | ( | 2578 | ) | [6 empty] | (C | 2467 | ) |  | Budget
|  |  | 2681 | [8 empty] | 2578
O. | Law Library Addition and Related |  | 9648 | G |  | - - - |  | (P | 677 | ) | (W | 838 | ) | 11/92 | Regents' | N/A | 10/91 |  | 1992-95 CIP | 22530
| Improvements (943080) | ( | 13532 | ) |  |  |  | P | 450 | G | W | 556 | G |  | Budget
|  |  | 23180 | [5 empty] | 1127 |  | (C | 12017 | )
[11 empty] | C | 7971 | G
[11 empty] | E | 671 | G
22053
| Gifts (G) |  | 98724 | G |  | 31059 | G |  | 10207 | G |  | 57458 | G
| Hospital Reserve Funds (HR) |  | 1650 | HR |  | 1334 | HR |  | 316 | HR |  | 0
| Bank Loans or Bonds (LB) |  | 189860 | LB |  | 0 |  |  | 57600 | LB |  | 84000 | LB
Reserves other than Reg
| Fee Reserves (N) |  | 600 | N |  | 0 |  |  | 600 | N |  | 0
| Registration Fee Reserves (R) |  | 200 | R |  | 0 |  |  | 200 | R |  | 0
| Other - Campus Funds (X) |  | 8678 | X |  | 317 | X |  | 7768 | X |  | 593 | X
|  |  | 299712 |  |  | 32710 |  |  | 76691 |  |  | 142051
| STATE FUNDS | ( | 86301 | ) | ( | 66435 | ) | ( | 3756 | ) | ( | 15433 | )

## Riverside
RIVERSIDE CAMPUS
1992-93 NON-STATE CAPITAL BUDGET
($ in thousands)
[9 empty] | C U R R E N T S T A T U S | [8 empty] | PRIOR ACTION/COMMENTS
|  |  | Project | [8 empty] | Beyond |  |  |  | Approval
| Project |  | Cost |  |  | Prefunded |  |  | 1992-93 |  |  | 1992-93 |  | Action |  | Letter | Date | Action | Cost
A. | Holiday Inn Renovation for UCR Extension (958511) |  | 4448 | LB |  | - - - |  | P | 180 | LB |  | - - - |  | 2/93 | Admin | 2/2/93
[8 empty] | W | 240 | LB
[8 empty] | C | 3828 | LB
[8 empty] | E | 200 | LB
4448
B. | Graduate School of Management Building Upgrades (958955) |  | 1000 | G |  | - - - |  | P | 10 | G |  | - - - |  | 6/93 | Admin | 6/30/93
[8 empty] | W | 20 | G
[8 empty] | C | 460 | G
[8 empty] | E | 510 | G
1000
C. | Student Commons Expansion |  | 5140 | LB | P | 180 | LB | P | 25 | N |  | - - - |  | 6/93 | Admin | 6/23/93 | 5/89 | 1988-91 CIP | 5040
| (950368) |  | 583 | N | W | 280 | LB | W | 39 | N
|  |  | 5723 |  | C | 4480 | LB | C | 100 | LB
[5 empty] | E | 100 | LB | E | 519 | N
[6 empty] | 5040 |  |  | 683
D. | Humanities and Social Science |  | 553 | X | P | 553 | X | (W | 794 | ) | ( C | 17605 | ) | 11/92 | Regents' | N/A | 10/90 | 1991-94 CIP | 19076
| Building, Unit 1 (950356) | ( | 19523 | ) | [6 empty] | ( E | 1124 | ) |  | Budget |  | 10/91 | 1992-95 CIP | 19533
|  |  | 20076 | [8 empty] | 18729
| Gifts (G) |  | 1000 | G |  | 0 |  |  | 1000 | G |  | 0
| Bank Loans or Bonds (LB) |  | 9588 | LB |  | 5040 | LB |  | 4548 | LB |  | 0
Reserves other than University
| Registration Fee (N) |  | 583 | N |  | 0 |  |  | 583 | N |  | 0
| Campus Funds (X) |  | 553 | X |  | 553 | X |  | 0 |  |  | 0
| TOTAL |  | 11724 |  |  | 5593 |  |  | 6131 |  |  | 0
| STATE FUNDS | ( | 19523 | ) | ( | 0 | ) | ( | 794 | ) | ( | 18729 | )

## San Diego
SAN DIEGO CAMPUS
1992-93 NON-STATE CAPITAL BUDGET
($ in thousands)
[9 empty] | C U R R E N T S T A T U S | [8 empty] | PRIOR ACTION/COMMENTS
|  |  | Project | [8 empty] | Beyond |  |  |  | Approval
| Project |  | Cost |  |  | Prefunded |  |  | 1992-93 |  |  | 1992-93 |  | Action |  | Letter | Date | Action | Cost
A. | Institute of Geophysics and |  | 1962 | G | P | 238 | G | C | 746 | X | C | 51 | G | 12/94 | Admin | 12/21/94 | 3/90 | 1989-92 CIP | 7149
| Planetary Physics Building, Unit 2 |  | 4624 | LB | W | 306 | G | E | 248 | X | C | 53 | LB |  |  |  | 3/90 | 1989-92 CIP | 7356
| (962040) |  | 1208 | X | C | 1367 | G |  | 994 |  | C | 214 | X |  |  |  | 9/92 | 1992-95 CIP | 7660
|  |  | 7794 |  | C | 4571 | LB |  |  |  |  | 318 |  |  |  |  | 5/93 | 1992-95 CIP | 7476
6482
B. | UCSD Medical Center - Fourth |  | 1424 | G |  | - - - |  | P | 84 | G | C | 382 | G |  | Chancellor | delegated | 9/92 | 1992-95 CIP | 1041
| Floor Remodel, Phase 1 (965260) | [6 empty] | W | 150 | G | E | 1 | G
[8 empty] | C | 807 | G |  | 383
1041
C. | Student Center Building C |  | 14 | G |  | - - - |  | P | 17 | X |  | - - - |  | 8/92 | Chancellor | 8/17/92
| Remodel and Expansion (962130) |  | 331 | X |  |  |  | W | 47 | X
|  |  | 345 |  |  |  |  | C | 267 | X
[8 empty] | C | 14 | G
345
D. | Seismic Corrections, Urey Hall |  | 175 | X | P | 175 | X | (W | 200 | ) |  | - - - |  | 11/91 | Regents' | N/A
| (968714) | ( | 3880 | ) |  |  |  | (C | 3680 | ) |  |  |  |  | Budget
|  |  | 4055 | [5 empty] | 3880
E. | Basic Science Building 2nd/3rd |  | 331 | X |  | - - - |  | P | 12 | X |  | - - - |  | 11/92 | Chancellor | 11/13/92
| Floor Laboratory and Office | [6 empty] | W | 15 | X
| Renovations (965290) | [6 empty] | C | 304 | X
331
F. | Torrey Pines Center South Third |  | 605 | X |  | - - - |  | P | 30 | X |  | - - - |  | 8/93 | Chancellor | 8/12/93
| Floor Renovations (962140) | [6 empty] | W | 50 | X
[8 empty] | C | 425 | X
[8 empty] | E | 100 | X
605
G. | Powell Structures Laboratory |  | 1604 | X |  | - - - |  | P | 100 | X |  | - - - |  | 3/93 | Admin | 3/17/93
| Expansion (962170) |  | 1000 | G |  |  |  | W | 120 | X
|  |  | 2604 |  |  |  |  | C | 1384 | X
[8 empty] | C | 1000 | G
2604
H. | Science and Engineering Research |  | 29215 | LB |  | - - - |  | P | 800 | LB |  | - - - |  | 12/94 | Admin | 12/21/94 | 1/93 | 1992-95 CIP | 26225
| Facility (962072) | [6 empty] | W | 1030 | LB | [7 empty] | (w/o finance approval)
[8 empty] | C | 24877 | LB | [6 empty] | 9/93 | finance approval | 25993
[8 empty] | E | 2508 | LB
29215
I. | Thermal Energy Storage (966070) |  | 4585 | LB |  | - - - |  | P | 220 | LB |  | - - - |  | 3/93 | Regents | 3/30/93
|  |  | 400 | X |  |  |  | W | 256 | LB
|  |  | 4985 |  |  |  |  | C | 4109 | LB
[8 empty] | E | 400 | X
4985
J. | Seismic Corrections: |  | 352 | X |  | - - - |  | P | 13 | X |  | - - - |  | 3/93 | Chancellor | 3/30/93
| Bonner-Mayer Bridge and | [6 empty] | W | 17 | X
| Matthews' Campus, Building 605 | [6 empty] | C | 322 | X
| (968733) | [7 empty] | 352
K. | Molecular Biology Research |  | 29355 | LB |  | - - - |  | P | 979 | X |  | - - - |  | 5/93 | Interim | 6/16/93 | 3/90 | 1989-92 CIP | 28825
| Facility, Unit 3 (MBRF) |  | 3208 | X |  |  |  | W | 1259 | X | [6 empty] | 3/90 | 1989-92 CIP | 31593
|  |  | 32563 |  |  |  |  | C | 970 | X
[8 empty] | C | 27180 | LB
[8 empty] | E | 2175 | LB
32563
L. | UCSDMC -- Eleventh Operating |  | 1200 | LB | P | 48 | LB |  | - - - |  |  | - - - |  | 5/93 | Admin | 5/12/93 | 8/90 | 1989-92 CIP | 1200
| Room (965150) |  |  |  | W | 139 | LB | [7 empty] | ( revised scope )
[5 empty] | C | 1013 | LB
1200
M. | Scripps Crossing (S10) (962120) |  | 725 | G |  | - - - |  | P | 25 | G |  | - - - |  | 6/93 | Chancellor | 6/16/93
|  |  | 40 | X |  |  |  | W | 40 | X
|  |  | 765 |  |  |  |  | C | 700 | G
765
N. | Building 201 and 202 Renovations |  | 1039 | X |  | - - - |  | P | 20 | X |  | - - - |  | 6/93 | Chancellor | 6/15/93
| and Seismic Corrections (962210) | [6 empty] | W | 52 | X
[8 empty] | C | 967 | X
1039
O. | Social Sciences Building (961930) |  | 473 | X | P | 473 | X | (W | 623 | ) | ( C | 13130 | ) | 11/91 | Regents' | N/A | 10/90 | 1991-94 CIP | 14553
|  | ( | 14835 | ) | [6 empty] | ( E | 1082 | ) |  | Budget |  | 10/91 | 1992-95 CIP | 14899
|  |  | 15308 | [8 empty] | 14212
P. | Warren - University Center Utilities |  | 114 | X | P | 114 | X | (W | 129 | ) |  | - - - |  | 11/91 | Regents' | N/A | 10/90 | 1991-94 CIP | 3735
| Loop, Phase 1 (966068) | ( | 2752 | ) |  |  |  | (C | 2623 | ) |  |  |  |  | Budget
|  |  | 2866 | [5 empty] | 2752
Q. | Central Plant Equipment |  | 1499 | X | P | 115 | X | (W | 410 | ) |  | - - - |  | 11/91 | Regents' | N/A | 11/89 | 1990-93 CIP | 3234
| Improvements 2 (966062) | ( | 3772 | ) |  |  |  | (C | 3362 | ) |  |  |  |  | Budget |  | 10/90 | 1991-94 CIP | 3309
|  |  | 5271 |  |  |  |  | C | 1384 | X
5156
R. | Mandeville Renovations (961740) |  | 127 | X | P | 48 | X |  | - - - |  | (C | 1240 | ) | 11/92 | Regents' | N/A | 10/90 | 1991-94 CIP | 1297
|  | ( | 1464 | ) | W | 79 | X |  |  |  | (E | 224 | ) |  | Budget |  | 11/91 | 1992-95 CIP | 1325
|  |  | 1591 |  |  | 127 | [5 empty] | 1464
S. | Classroom Building 1 (961770) |  | 933 | X | P | 406 | X |  | - - - |  | (C | 11419 | ) | 10/94 | Regents' | N/A | 11/91 | 1992-95 CIP | 11986
|  | ( | 11760 | ) | W | 527 | X |  |  |  | (E | 341 | ) |  | Budget |  | 10/92 | 1993-96 CIP | 12682
|  |  | 12693 |  |  | 933 | [5 empty] | 11760 |  |  |  |  | 11/93 | 1994-97 CIP | 12693
T. | Galbraith Hall Reinforcement |  | 1997 | LB | P | 66 | LB | C | 77 | X |  | - - - |  | 8/93 | Admin | 8/13/93 | 7/90 | 1989-92 CIP | 1440
| (968716) |  | 330 | X | W | 81 | LB | [9 empty] | 9/91 | 1991-94 CIP | 1840
|  |  | 2327 |  | C | 1850 | LB | [9 empty] | 6/92 | 1991-94 CIP | 2250
[5 empty] | C | 253 | X
2250
| Gift Funds (G) |  | 5125 | G |  | 1911 | G |  | 2780 | G |  | 434 | G
| Bank Loans or Bonds (LB) |  | 70976 | LB |  | 7768 | LB |  | 63155 | LB |  | 53 | LB
| Other (X) |  | 12769 | X |  | 2190 | X |  | 10365 | X |  | 214 | X
| TOTAL |  | 88870 |  |  | 11869 |  |  | 76300 |  |  | 701
| STATE FUNDS | ( | 38463 | ) | ( | --- | ) | ( | 11027 | ) | ( | 27436 | )

## San Francisco
SAN FRANCISCO CAMPUS
1992-93 NON-STATE CAPITAL BUDGET
($ in thousands)
[9 empty] | C U R R E N T S T A T U S | [8 empty] | PRIOR ACTION/COMMENTS
|  |  | Project | [8 empty] | Beyond |  |  |  | Approval
| Project |  | Cost |  |  | Prefunded |  |  | 1992-93 |  |  | 1992-93 |  | Action |  | Letter | Date | Action | Cost
A. | The Medical Center at UCSF, |  | 3225 | HR | P | 75 | HR | C | 3050 | HR |  | - - - |  | 12/92 | Admin | 12/23/92 | 7/91 | 1991-94 CIP | 3200
| ACC-6 Code Corrections Phase 3 |  |  |  | W | 100 | HR
| and Surgery Practice Renovation |  |  |  |  | 175
(920770)
B. | School of Medicine, SFGH 5-5 |  | 700 | X |  | - - - |  | P | 42 | X |  | - - - |  | 7/92 | Chancellor | 7/24/92
| General Clinical Research Center | [6 empty] | W | 88 | X
| (920170) | [6 empty] | C | 570 | X
700
C. | School of Medicine, U-2 |  | 150 | G |  | - - - |  | P | 11 | G |  | - - - |  | 7/92 | Chancellor | 7/24/92
| Molecular Genetics Laboratory |  | 153 | X |  |  |  | W | 14 | G
| Alterations (924600) |  | 303 |  |  |  |  | C | 125 | G
[8 empty] | C | 153 | X
303
D. | The Medical Center at UCSF |  | 2068 | HR |  | - - - |  | P | 94 | HR |  | - - - |  | 2/93 | Admin | 2/10/93
| Mount Zion J-3, 4 & 5 Alterations | [6 empty] | W | 188 | HR
| (924670) | [6 empty] | C | 1786 | HR
2068
E. | The Medical Center at UCSF |  | 1340 | HR |  | - - - |  | P | 62 | HR |  | - - - |  | 2/93 | Admin | 2/10/93
| Mount Zion G Dialysis Relocation | [6 empty] | W | 122 | HR
| (925270) | [6 empty] | C | 1156 | HR
1340
F. | The Millberry Union H-Level |  | 404 | HR |  | - - - |  | P | 35 | X |  | - - - |  | 3/93 | Admin | 3/17/93
| Transformer Installation (924250) |  | 596 | X |  |  |  | W | 45 | X
|  |  | 1000 |  |  |  |  | C | 516 | X
[8 empty] | C | 404 | HR
1000
G. | The Medical Center at UCSF |  | 1560 | HR |  | - - - |  | P | 71 | HR |  | - - - |  | 3/93 | Admin | 3/17/93
| M-14S Inpatient Unit Renovations | [6 empty] | W | 141 | HR
| (924420) | [6 empty] | C | 1348 | HR
1560
H. | The Medical Center at UCSF L-1 |  | 2080 | HR | P | 95 | HR | W | 33 | HR |  | - - - |  | 2/93 | Admin | 2/10/93
| Endoscopy Unit Relocation |  |  |  | W | 155 | HR | C | 1797 | HR
| (926254) |  |  |  |  | 250 |  |  | 1830
I. | The Medical Center at UCSF, |  | 39000 | LB |  | - - - |  | P | 1034 | LB |  | - - - |  | 11/92 | Regents | 2/10/93 | 3/90 | 1989-90 CIP | 42685
| UCSF/Mount Zion Outpatient | [6 empty] | W | 2348 | LB |  |  |  | Previous project (see "M" in
| Cancer Center (920910) | [6 empty] | C | 35618 | LB |  |  |  | 1989-90) pulled--Cancer Center
[9 empty] | 39000 |  |  |  |  | component reformulated as this
project
J-1. | The Medical Center at UCSF, M-G |  | 3980 | HR |  | - - - |  | P | 191 | HR |  | - - - |  | 6/93 | Admin | 6/4/93
| Materiel Services (920080) | [6 empty] | W | 383 | HR
[8 empty] | C | 3406 | HR
3980
J-2. | M-4 Miscellaneous O.R. |  | 700 | HR |  | - - - |  | P | 34 | HR |  | - - - |  | 6/93 | Admin | 6/4/93
| Alterations (920080) | [6 empty] | W | 67 | HR
[8 empty] | C | 599 | HR
700
K. | The Medical Center at UCSF, |  | 1084 | HR |  | - - - |  | P | 42 | HR |  | - - - |  | 2/93 | Admin | 2/10/93
| UCSF/Mount Zion J Building | [6 empty] | W | 98 | HR
| Exterior (924660) | [6 empty] | C | 944 | HR
1084
L. | Parnassus Central Utilities Plant |  | 60469 | LB |  | - - - |  | P | 1060 | LB |  |  |  | 2/94 | Interim | 5/19/97 | 1/93 | 1992-95 CIP | 50600
| (928006) |  | 500 | X |  |  |  | P | 500 | X
|  |  | 60969 |  |  |  |  | W | 4000 | LB
[8 empty] | C | 45040 | LB | C | 10369 | LB
50600
M. | The Medical Center at UCSF - |  | 1600 | HR |  | - - - |  | P | 73 | HR |  | - - - |  | 3/93 | Admin | 3/17/93
| ACC-H Electrical Substation | [6 empty] | W | 144 | HR
| Installation (924620) | [6 empty] | C | 1383 | HR
1600
N. | The Medical Center at UCSF, |  | 268 | HR |  | - - - |  | P | 12 | HR |  | - - - |  | 2/93 | Admin | 2/10/93
| UCSF/Mount Zion A, B, Seismic | [6 empty] | W | 24 | HR
| Joint Repair and Upgrade (925290) | [6 empty] | C | 232 | HR
268
O. | N-2, 3 Lecture Hall Lobby |  | 2535 | X |  | - - - |  | P | 256 | X |  | - - - |  | 4/93 | Chancellor | 4/9/93
| Expansion, Food Service | [6 empty] | W | 193 | X
| Relocation, Student Commons | [6 empty] | C | 2046 | X
| Alterations and Landscaping | [6 empty] | E | 40 | X
| Improvements (924460) | [7 empty] | 2535
P. | The Medical Center at UCSF, A-2 |  | 600 | HR |  | - - - |  | P | 30 | HR |  | - - - |  | 4/93 | Admin | 4/16/93
| Pediatric Treatment Center | [6 empty] | W | 60 | HR
| Renovation (924820) | [6 empty] | C | 510 | HR
600
Q. | School of Dentistry, S-5 |  | 701 | X |  | - - - |  | P | 35 | X |  | - - - |  | 3/92 | Chancellor | 3/6/92
| Stomatology Laboratory Alterations | [6 empty] | W | 70 | X
| (925250) | [6 empty] | C | 596 | X
701
R. | The Medical Center at UCSF, |  | 1217 | HR |  | - - - |  | P | 55 | HR |  | - - - |  | 6/93 | Admin | 6/14/93
| UCSF/Mount Zion Chiller/Cooling | [6 empty] | W | 107 | HR
| Tower Upgrade (924890) | [6 empty] | C | 1055 | HR
1217
S. | The Medical Center at UCSF, |  | 892 | HR |  | - - - |  | P | 44 | HR |  | - - - |  | 5/93 | Admin | 5/12/93
| UCSF/Mount Zion Pain | [6 empty] | W | 90 | HR
| Management/Quality Management | [6 empty] | C | 758 | HR
| Relocation (924930) | [7 empty] | 892
T. | School of Medicine, LPPI-1, |  | 1940 | G |  | - - - |  | P | 18 | G |  | - - - |  | 12/92 | Chancellor | 12/21/92
| Developmental Neurobiology | [6 empty] | W | 250 | G
| Laboratory Alterations (924240) | [6 empty] | C | 1672 | G
1940
U. | School of Medicine, HSE-9, 10, |  | 2000 | F |  | - - - |  | P | 625 | X |  | - - - |  | 5/93 | Regents | 10/4/93
| HSW-9 Biochemistry and |  | 8480 | G |  |  |  | W | 880 | X
| Biophysics Laboratory |  | 4500 | X |  |  |  | C | 2995 | X
| Improvements (924770) |  | 14980 |  |  |  |  | C | 2000 | F
[8 empty] | C | 8480 | G
14980
V. | UCH-CSB Emergency Power |  | 787 | LB |  | - - - |  | P | 28 | LB |  | - - - |  | 6/93 | Admin | 6/11/93
| Generator, UCH Ground Floor | [6 empty] | W | 35 | LB
| (924680) | [6 empty] | C | 724 | LB
787
W. | School of Medicine, Library-1 |  | 1177 | X |  | - - - |  | P | 25 | X |  | - - - |  | 6/93 | Chancellor | 6/18/93
| Computer Science Laboratory and | [6 empty] | W | 152 | X
| Office Alterations (924830) | [6 empty] | C | 1000 | X
1177
X. | NO PROJECT
Y. | School of Medicine, U-4 |  | 1856 | X |  | - - - |  | P | 107 | X |  | - - - |  | 6/93 | Chancellor | 6/18/93
| Orthopaedic Laboratory/Office | [6 empty] | W | 165 | X
| Alterations (920330) | [6 empty] | C | 1584 | X
1856
Z. | Library Release Space |  | 6586 | G | (P | 749 | ) | ( C | 14885 | ) | ( E | 1925 | ) | 11/92 | Regents' | N/A | 11/89 | 1990-93 CIP | 19348
| Improvements (925340) |  | 1300 | U | P | 209 | G | C | 6213 | G |  |  |  |  | Budget |  | 10/90 | 1991-94 CIP | 19586
|  | ( | 18715 | ) | (W | 1156 | ) |  | 21098 | [7 empty] | 11/91 | 1992-95 CIP | 26571
|  |  | 26601 |  | W | 164 | G
[5 empty] | C | 1300 | U
3578
AA. | Parnassus Fire Alarm and Life |  | 2473 | HR | (P | 292 | ) | ( C | 4387 | ) |  | - - - |  | 11/91 | Regents' | N/A | 11/89 | 1990-93 CIP | 8241
| Safety System (928620) |  | 771 | X | P | 95 | HR | C | 2121 | HR |  |  |  |  | Budget |  | 10/90 | 1991-94 CIP | 7726
|  | ( | 6965 | ) | P | 9 | X | C | 504 | X
|  |  | 10209 |  | ( W | 175 | ) |  | 7012
[5 empty] | W | 115 | HR
[5 empty] | ( C | 2111 | )
[5 empty] | C | 142 | HR
[5 empty] | C | 258 | X
3197
BB. | Parnassus Fire Protection Water |  | 415 | HR | ( P | 355 | ) | W | 25 | HR | ( W | 190 | ) | 11/92 | Regents' | N/A | 11/89 | 1990-93 CIP | 7856
| Supply System (928622) |  | 3211 | LB | P | 7 | HR | W | 9 | X | W | 11 | HR |  | Budget |  | 10/90 | 1991-94 CIP | 7856
|  |  | 1718 | U | P | 13 | X | C | 445 | LB | ( C | 2853 | ) |  |  |  | 11/91 | 1992-95 CIP | 9096
|  |  | 228 | X | ( W | 126 | ) |  | 479 |  | C | 312 | HR
|  | ( | 3524 | ) | W | 3 | HR |  |  |  | C | 83 | X
|  |  | 9096 |  | W | 123 | X |  |  |  |  | 3449
[5 empty] | W | 104 | LB
[5 empty] | W | 137 | U
[5 empty] | C | 57 | HR
[5 empty] | C | 2662 | LB
[5 empty] | C | 1581 | U
5168
| Federal Funds (F) |  | 2000 | F |  | 0 |  |  | 2000 | F |  | 0
| Gifts (G) |  | 17156 | G |  | 373 | G |  | 16783 | G |  | 0
| Hospital Reserves (HR) |  | 23906 | HR |  | 844 | HR |  | 22739 | HR |  | 323 | HR
| Bank Loans or Bonds (LB) |  | 103467 | LB |  | 2766 | LB |  | 90332 | LB |  | 10369 | LB
| Regents' Appropriations (U) |  | 3018 | U |  | 3018 | U |  | 0 |  |  | 0
| Other (X) |  | 13717 | X |  | 403 | X |  | 13231 | X |  | 83 | X
| TOTAL |  | 163264 |  |  | 7404 |  |  | 145085 |  |  | 10775
| STATE FUNDS | ( | 29204 | ) | ( | 4964 | ) | ( | 19272 | ) | ( | 4968 | )
Note on J198: Formula failed to convert

## Santa Barbara
SANTA BARBARA CAMPUS
1992-93 NON-STATE CAPITAL BUDGET
($ in thousands)
[9 empty] | C U R R E N T S T A T U S | [8 empty] | PRIOR ACTION/COMMENTS
|  |  | Project | [8 empty] | Beyond |  |  |  | Approval
| Project |  | Cost |  |  | Prefunded |  |  | 1992-93 |  |  | 1992-93 |  | Action |  | Letter | Date | Action | Cost
A. | Baseball Facility (980980) |  | 98 | G |  | - - - |  | C | 85 | X | P | 15 | G | 5/95 | Chancellor | N/A | 7/92 | 1992-93 CIP | 406
| (also see "G" in 94-95) |  | 145 | X |  |  |  | C | 63 | G | W | 20 | G |  | (change of fund source) |  | 11/92 | 1992-93 CIP | 441
|  |  | 146 | N |  |  |  |  | 148 |  | C | 52 | R
|  |  | 52 | R | [6 empty] | C | 146 | N
|  |  | 441 | [7 empty] | C | 60 | X
293
B. | Old Gym Renovation Project |  | 380 | X |  | - - - |  | P | 33 | X |  | - - - |  | 7/92 | Chancellor | 7/27/92
| (981020) | [6 empty] | W | 57 | X
[8 empty] | C | 290 | X
380
C. | Student Affairs and Administrative |  | 10181 | LB |  | - - - |  | P | 452 | X |  |  |  | 11/93 | Regents | 2/23/94 | 1/93 | 1993-95 CIP | 17086
| Services Building (980920) |  | 3550 | X |  |  |  | P | 280 | R
|  |  | 3230 | R |  |  |  | W | 458 | X
|  |  | 771 | U |  |  |  | W | 635 | R
|  |  | 750 | N |  |  |  | C | 750 | N
|  |  | 18482 |  |  |  |  | C | 771 | U
[8 empty] | C | 2640 | X
[8 empty] | C | 2315 | R
[8 empty] | C | 7112 | LB | C | 1396 | LB
[8 empty] | E | 1673 | LB
17086
D. | Reclaimed Water Laterals (986028) |  | 1000 | X |  | - - - |  | P | 100 | X |  | - - - |  | 10/92 | Chancellor | 10/28/92
[8 empty] | W | 116 | X
[8 empty] | C | 784 | X
1000
E. | Materials Research Lab. (981030) |  | 10797 | X |  | - - - |  | P | 736 | X | C | 552 | X | 1/99 | Admin | Pending | 1/93 | 1992-95 CIP | 9480
[8 empty] | W | 863 | X | [6 empty] | 5/96 | 1995-98 CIP | 10245
[8 empty] | C | 8639 | X
[8 empty] | E | 7 | X
10245
F. | Pardall-West Entry (986508) |  | 383 | X |  | - - - |  | P | 40 | X |  | - - - |  | 1/93 | Chancellor | 1/29/93
[8 empty] | W | 51 | X
[8 empty] | C | 292 | X
383
G. | Institute for Theoretical Physics |  | 5525 | LB |  | - - - |  | P | 145 | X |  | - - - |  | 5/93 | Interim | 6/16/93 | 2/89 | 1988-91 CIP | 4950
| Building (ITP) (980990) |  | 1000 | U |  |  |  | W | 175 | X | [6 empty] | 3/90 | 1989-92 CIP | 6550
|  |  | 1257 | X |  |  |  | C | 680 | X | [6 empty] | 3/90 | 1989-94 CIP | 6669
|  |  | 7782 |  |  |  |  | C | 5121 | LB
[8 empty] | C | 257 | X
[8 empty] | E | 404 | LB
6782
H. | Environmental Health and Safety |  | 596 | LB | P | 113 | X | C | 198 | X |  | - - - |  | 7/93 | Admin | 7/6/93 | 1/89 | 1988-91 CIP | 1043
| Facility, Phase 1 (980840) |  | 2443 | X | W | 127 | X | E | 2 | X | [6 empty] | 7/91 | 1990-93 CIP | 2839
|  |  | 3039 |  | C | 596 | LB |  | 200
[5 empty] | C | 1913 | X
[5 empty] | E | 90 | X
2839
I. | Modifications/Additions to |  | 1289 | LB | P | 30 | N | C | 378 | X |  | - - - |  | 7/93 | Admin | 8/13/93 | 5/89 | 1988-91 CIP | 1288
| University Children's |  | 149 | N | P | 14 | R | E | 13 | X | [6 empty] | 1/91 | 1990-93 CIP | 1963
| Center (980870) |  | 225 | R | W | 55 | R |  | 391
|  |  | 691 | X | C | 156 | R
|  |  | 2354 |  | C | 300 | X
[5 empty] | C | 119 | N
[5 empty] | C | 1257 | LB
[5 empty] | E | 32 | LB
1963
J. | Biology and Psychology Buildings |  | 50 | X | ( P | 70 | ) | ( W | 130 | ) |  | - - - |  | 11/91 | Regents' | N/A | 10/90 | 1991-94 CIP | 2797
| Renovations (980640) (Formerly: | ( | 2814 | ) | P | 50 | X | ( C | 2614 | ) |  |  |  |  | Budget
| Animal Care Facility Improvements) |  | 2864 |  |  | 120 |  |  | 2744
K. | Humanities and Social Sciences |  | 944 | X | P | 944 | X | ( W | 1193 | ) | ( C | 27814 | ) | 11/95 | Regents' | N/A | 10/90 | 1991-94 CIP | 30400
| Building (980830) | ( | 31122 | ) | [6 empty] | ( E | 2115 | ) |  | Budget |  | 11/91 | 1992-95 CIP | 31126
|  |  | 32066 | [8 empty] | 29929 |  |  |  |  | 11/92 | 1993-96 CIP | 31989
[17 empty] | 11/93 | 1994-97 CIP | 32032
[17 empty] | 11/94 | 1995-98 CIP | 32056
| Gifts (G) |  | 98 | G |  | 0 |  |  | 63 | G |  | 35 | G |  | 0
| Bank Loans or Bonds (LB) |  | 17591 | LB |  | 1885 | LB |  | 14310 | LB |  | 1396 | LB |  | 0
Reserves other than University
| Registration Fee (N) |  | 1045 | N |  | 149 | N |  | 750 | N |  | 146 | N |  | 0
University Registration Fee
| Reserves (R) |  | 3507 | R |  | 225 | R |  | 3230 | R |  | 52 | R |  | 0
| Others (X) |  | 21640 | X |  | 3537 | X |  | 17491 | X |  | 612 | X |  | 0
| TOTAL |  | 43881 |  |  | 5796 |  |  | 35844 |  |  | 2241 |  |  | 0
| STATE FUNDS | ( | 33936 | ) | ( | 70 | ) | ( | 3937 | ) | ( | 29929 | ) |  | 0

## Santa Cruz
SANTA CRUZ CAMPUS
1992-93 NON-STATE CAPITAL BUDGET
($ in thousands)
[9 empty] | C U R R E N T S T A T U S | [8 empty] | PRIOR ACTION/COMMENTS
|  |  | Project | [8 empty] | Beyond |  |  |  | Approval
| Project |  | Cost |  |  | Prefunded |  |  | 1992-93 |  |  | 1992-93 |  | Action |  | Letter | Date | Action | Cost
A. | College Ten Student Facilities and |  | 302 | LB |  | - - - |  | P | 7 | LB |  | - - - |  | 2/93 | Admin | 2/1/93
| Housing Office (976298) |  | 97 | N |  |  |  | P | 4 | N
|  |  | 399 |  |  |  |  | W | 16 | LB
[8 empty] | W | 4 | N
[8 empty] | C | 269 | LB
[8 empty] | C | 85 | N
[8 empty] | E | 10 | LB
[8 empty] | E | 4 | N
399
B. | Crown-Merrill Water Line |  | 450 | N |  | - - - |  | P | 30 | N |  | - - - |  | 4/93 | Admin | 4/1/93
| Replacement (976397) | [6 empty] | W | 30 | N
[8 empty] | C | 390 | N
450
| Bank Loans or Bonds (LB) |  | 302 | LB |  | 0 |  |  | 302 | LB |  | 0
Reserves other than University
| Registration Fees (N) |  | 547 | N |  | 0 |  |  | 547 | N |  | 0
| TOTAL |  | 849 |  |  | 0 |  |  | 849 |  |  | 0
| STATE FUNDS | ( | 0 | ) | ( | 0 | ) | ( | 0 | ) | ( | 0 | ) |  | 0

## U-Wide
DIVISION OF
AGRICULTURE AND NATURAL RESOURCES
1992-93 NON-STATE CAPITAL BUDGET
($ in thousands)
[9 empty] | C U R R E N T S T A T U S | [8 empty] | PRIOR ACTION/COMMENTS
|  |  | Project | [8 empty] | Beyond |  |  |  | Approval
| Project |  | Cost |  |  | Prefunded |  |  | 1992-93 |  |  | 1992-93 |  | Action |  | Letter | Date | Action | Cost
A. | Elkus 4-H Ranch Half Moon |  | 600 | G | P | 10 | G | P | 16 | G |  | 0 |  | 3/93 | Chancellor | 3/15/93 | 12/81 | 1981-84 CIP | 395
| Bay (930730) |  | 200 | X | W | 30 | G | W | 74 | G
|  |  | 800 |  | C | 355 | G | C | 115 | G
[6 empty] | 395 |  | C | 200 | X
405
A | Alternative Pest Control | ( | 19148 | ) | C | 1585 | F | S | 300 | X | ( S | 100 | ) | 11/98 | Regents' |  | 5/93 | 1993-96 CIP | 35000
| Quarantine and Containment |  | 16552 | F |  |  |  | P | 373 | F | ( P | 165 | ) |  | Budget |  | 11/93 | 1994-97 CIP | 35954
| Facilities for California (L939118) |  | 695 | G |  |  |  |  | 673 |  | P | 922 | F |  |  |  | 11/94 | 1995-98 CIP | 37572
|  |  | 7376 | X | [6 empty] | (C | 18343 | ) |  |  |  | 11/95 | 1996-99 CIP | 37588
|  |  | 43771 | [7 empty] | (E | 540 | ) |  |  |  | 11/96 | 1997-00 CIP | 38194
[11 empty] | E | 695 | G |  |  |  | 11/97 | 1998-01 CIP | 38746
[11 empty] | C | 7076 | X
[11 empty] | C | 13672 | F
41513
C. | West Side Irrigation System |  | 25 | X | P | 25 | X |  | 0 |  | ( W | 36 | ) | 11/92 | Regents' | N/A | 11/91 | 1992-95 CIP | 776
| (931950) | ( | 756 | ) | [6 empty] | ( C | 720 | ) |  | Budget
|  |  | 781 | [8 empty] | 756
| Federal Funds (F) |  | 16552 | F |  | 1585 |  |  | 373 | F |  | 14594 | F
| Gifts (G) |  | 1295 | G |  | 395 | G |  | 205 | G |  | 695 | G
| Other (X) |  | 7601 | X |  | 25 |  |  | 500 | X |  | 7076
| TOTAL |  | 25448 |  |  | 2005 |  |  | 1078 |  |  | 22365
| STATE FUNDS | ( | 19904 | ) | ( | 0 | ) | ( | 0 | ) | ( | 19904 | )