## Summary
1995-96 NON-STATE FUNDED PROJECTS
($ in thousands)
| UCB | UCD | UCI | UCLA | UCR | UCSD | UCSF | UCSB | UCSC | OTHER | TOTAL | Percent of Total
Bank Loans or Bonds (LB) | 0 | 8089 | 0 | 32062 | 1782 | 18480 | 31853 | 12180 | 1097 | 0 | 105543 | 30.28%
Other (X) | 7852 | 3510 | 1878 | 9677 | 245 | 9331 | 25289 | 12471 | 2504 | 0 | 72757 | 20.88%
Gifts (G) | 9308 | 912 | 2956 | 52124 | 0 | 6928 | 4077 | 300 | 0 | 0 | 76605 | 21.98%
Federal (F) | 1834 | 233 | 0 | 43039 | 0 | 0 | 0 | 0 | 0 | 2834 | 47940 | 13.76%
Hospital Reserves (HR) | 0 | 6595 | 1321 | 688 | 0 | 7397 | 5041 | 0 | 0 | 0 | 21042 | 6.038%
Registration Fees (R) | 0 | 3250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3250 | 0.9325%
Reserves other than Registration Fees (N) | 465 | 8229 | 1119 | 5859 | 0 | 5117 | 581 | 0 | 0 | 0 | 21370 | 6.132%
TOTAL | 19459 | 30818 | 7274 | 143449 | 2027 | 47253 | 66841 | 24951 | 3601 | 2834 | 348507 | 100%
INDIVIDUAL CAMPUS PERCENT OF TOTAL | 5.584% | 8.843% | 2.087% | 41.16% | 0.5816% | 13.56% | 19.18% | 7.159% | 1.033% | 0.8132% | 100%
STATE FUNDS | 10659 | 0 | 1607 | 4741 | 83 | 22896 | 1781 | 1105 | 0 | 18883 | 61755

## Berkeley
BERKELEY CAMPUS
1995-96 NON-STATE CAPITAL BUDGET
($000)
[9 empty] | C U R R E N T S T A T U S | [7 empty] | PRIOR ACTION/COMMENTS
|  |  | Project | [8 empty] | Beyond |  |  |  | Approval
| Project |  | Cost |  |  | Prefunded |  |  | 1995-96 |  |  | 1995-96 |  | Action |  | Letter | Date | Action | Cost
A. | McCone Hall Renovation (912200) |  | 7500 | G |  | - - - |  | P | 504 | G |  | - - - |  | 1/96 | Regents | 2/14/96
|  |  | 1500 | F |  |  |  | W | 662 | G
|  |  | 9000 |  |  |  |  | C | 6334 | G
[8 empty] | C | 1500 | F
9000
B. | Dwinelle Hall Expansion (912510) |  | 1564 | X | (P | 410 | ) | (C | 10659 | ) | (E | 878 | ) | 6/96 | Admin | 6/28/96
|  | ( | 12427 | ) | (W | 480 | ) | C | 1564 | X
|  |  | 13991 |  |  | 890 |  |  | 12223
C. | Latimer Hall: 8th Floor |  | 437 | G |  | - - - |  | P | 50 | G |  | - - - |  |  | Chancellor | Delegated
| Renovations for Biochemical | [6 empty] | W | 57 | G
| Research (912736) | [6 empty] | C | 330 | G
437
D. | North Gate Hall: Library/ Reading |  | 350 | G |  | - - - |  | P | 20 | G |  | - - - |  |  | Chancellor | Delegated
| Room and Related Renovations | [6 empty] | W | 30 | G
| (912776) | [6 empty] | C | 300 | G
350
E. | Hat Creek Radio Observatory: |  | 334 | F |  | - - - |  | P | 5 | F |  | - - - |  |  | Chancellor | Delegated
| Telescope Runway Expansion | [6 empty] | W | 14 | F
| (912778) | [6 empty] | C | 315 | F
334
F. | California Memorial Stadium |  | 150 | G |  | - - - |  | P | 2 | G |  | - - - |  |  | Chancellor | Delegated
| Scoreboards (912762) |  | 600 | X |  |  |  | W | 10 | G
|  |  | 750 |  |  |  |  | C | 88 | G
[8 empty] | C | 600 | X
[8 empty] | E | 50 | G
750
G. | Stern Hall Common Area |  | 465 | N |  | - - - |  | P | 9 | N |  | - - - |  |  | Chancellor | Delegated
| Improvements (912728) | [6 empty] | W | 26 | N
[8 empty] | C | 375 | N
[8 empty] | E | 55 | N
456
H. | Tolman Hall: Ground Floor |  | 950 | X |  | - - - |  | P | 52 | X |  | - - - |  |  | Chancellor | Delegated
| Renovation for Psychology | [6 empty] | W | 59 | X
| Department (912770) | [6 empty] | C | 839 | X
950
I. | Stephens Hall Renovations |  | 1417 | X |  | - - - |  | P | 25 | X | C | 467 | X |  | Chancellor | Delegated | N/A | 1995-98 CIP | 950
| Step 1 ( 912890) | [6 empty] | W | 125 | X
[8 empty] | C | 800 | X
950
J. | California Memorial Stadium Club |  | 450 | G |  | - - - |  | P | 45 | G |  | - - - |  |  | Chancellor | Delegated
| Room (912893) | [6 empty] | W | 30 | G
[8 empty] | C | 300 | G
[8 empty] | E | 75 | G
450
K. | 2607 Hearst: Renovations for the |  | 715 | G |  | - - - |  | P | 52 | G | C | 294 | G |  | Chancellor | Delegated | N/A | 1995-98 CIP | 521
| Graduate School of Pulbic Policy |  | 100 | X |  |  |  | W | 45 | G
| (912885) |  | 815 |  |  |  |  | C | 100 | X
[8 empty] | C | 324 | G
521
L. | Cory Hall: Installation of |  | 980 | X |  | - - - |  | P | 386 | X |  | - - - |  |  | Chancellor | Delegated
| Computer Network (912910) | [6 empty] | W | 58 | X
[8 empty] | C | 43 | X
[8 empty] | E | 493 | X
980
M. | Hearst Gymnasium Alterations |  | 443 | X |  | - - - |  | P | 70 | X |  | - - - |  |  | Chancellor | Delegated
| for ROTC (912896) | [6 empty] | W | 53 | X
[8 empty] | C | 320 | X
443
N. | Haviland Hall: Basement |  | 280 | X |  | - - - |  | P | 10 | X |  | - - - |  |  | Chancellor | Delegated
| Renovations for the School of | [6 empty] | W | 31 | X
| Social Welfare (912009) | [6 empty] | C | 239 | X
280
O. | Minor Hall Expansion Temporary |  | 440 | X |  | - - - |  | P | 20 | X |  | - - - |  |  | Chancellor | Delegated
| Facilities (912716) | [6 empty] | W | 20 | X
[8 empty] | C | 385 | X
[8 empty] | E | 15 | X
440
P. | Minor Hall Fourth Floor |  | 320 | X |  | - - - |  | P | 10 | X |  | - - - |  |  | Chancellor | Delegated
| Mechanical System (912717) | [6 empty] | W | 10 | X
[8 empty] | C | 300 | X
320
Q. | Doe Library Seismic Corrections, |  | 162 | X |  | - - - |  | P | 162 | X | (W | 241 | ) | 11/95 | Regents' | N/A
| Step 3 (912637) | ( | 4117 | ) | [6 empty] | (C | 3876 | ) |  | Budget
|  |  | 4279 | [8 empty] | 4117
R. | Seismic Safety Corrections, |  | 579 | X |  | - - - |  | P | 303 | X | (C | 4660 | ) | 11/95 | Regents' | N/A
| McCone Hall (912208) | ( | 4660 | ) |  |  |  | W | 276 | X |  |  |  |  | Budget
|  |  | 5239 | [5 empty] | 579
S. | Seismic Safety Corrections, |  | 84 | X |  | - - - |  | P | 84 | X | (W | 93 | ) | 11/95 | Regents' | N/A
| Dance Facility (912772) | ( | 1089 | ) | [6 empty] | (C | 996 | ) |  | Budget
|  |  | 1173 | [8 empty] | 1089
T. | Seismic Safety Corrections, |  | 150 | X |  | - - - |  | P | 150 | X | (W | 100 | ) | 11/95 | Regents' | N/A
| Graduate School of Public Policy | ( | 1775 | ) | [6 empty] | (C | 1675 | ) |  | Budget
| (912886) |  | 1925 | [8 empty] | 1775
U. | Seismic Safety Corrections, |  | 459 | X |  | - - - |  | P | 250 | X | (W | 200 | ) | 11/95 | Regents' | N/A
| San Pablo Services Facility | ( | 3301 | ) | [6 empty] | (C | 3101 | ) |  | Budget
| (912774) |  | 3760 | [7 empty] | C | 209 | X
3510
Federal funds(F) |  |  | 1834 | F |  | 0 |  |  | 1834 | F |  | 0 |  |  | 0
Gifts (G) |  |  | 9602 | G |  | 0 |  |  | 9308 | G |  | 294 |  |  | 0
Reserves other than University
Registration Fee (N) |  |  | 465 | N |  | 0 |  |  | 465 | N |  | 0 |  |  | 0
Other (campus funds) (X) |  |  | 8528 | X |  | 0 |  |  | 7852 | X |  | 676 | X |  | 0
| TOTAL |  | 20429 |  |  | 0 |  |  | 19459 |  |  | 970 |  |  | 0
| STATE FUNDS | ( | 27369 | ) | ( | 890 | ) | ( | 10659 | ) | ( | 15820 | ) |  | 0
[6 empty] | 20429 |  |  | 20429 |  |  | 0

## Davis
DAVIS CAMPUS
1995-96 NON-STATE CAPITAL BUDGET
($000)
[9 empty] | C U R R E N T S T A T U S | [7 empty] | PRIOR ACTION/COMMENTS
|  |  | Project | [8 empty] | Beyond |  |  |  | Approval
| Project |  | Cost |  |  | Prefunded |  |  | 1995-96 |  |  | 1995-96 |  | Action |  | Letter | Date | Action | Cost
A. | Residential Housing Network |  | 8229 | N |  | - - - |  | P | 377 | N |  | - - - |  | 11/95 | Regents | 2/14/96
| (936323) |  | 3089 | LB |  |  |  | W | 776 | N
|  |  | 11318 |  |  |  |  | C | 7076 | N
[8 empty] | C | 3089 | LB
11318
B. | East Hall (931930) |  | 5000 | LB |  | - - - |  | P | 300 | R |  | - - - |  | 1/96 | Regents | 2/14/96
|  |  | 3250 | R |  |  |  | W | 500 | R
|  |  | 1550 | X |  |  |  | C | 2450 | R
|  |  | 9800 |  |  |  |  | C | 1550 | X
[8 empty] | C | 4700 | LB
[8 empty] | E | 300 | LB
9800
C. | UCDMC Central Plant Replacement |  | 68400 | LB | P | 4736 | LB |  | - - - |  |  | - - - |  | 3/96 | Regents/ | 3/22/96 | 1/94 | 1993-96 CIP | 64562
| (934900) |  |  |  | W | 7103 | LB | [7 empty] | Admin
[5 empty] | C | 56561 | LB
68400
D. | UCDMC Hospital Infrastructure |  | 2359 | HR |  | - - - |  | P | 108 | HR |  | - - - |  |  | Chancellor | delegated
| (935120) | [6 empty] | W | 162 | HR
[8 empty] | C | 2089 | HR
2359
E. | UCDMC South 3 LDRP |  | 880 | HR |  | - - - |  | P | 80 | HR |  | - - - |  |  | Chancellor | delegated
| (935400) | [6 empty] | W | 120 | HR
[8 empty] | C | 680 | HR
880
F. | UCDMC Operating Room |  | 702 | HR |  | - - - |  | P | 22 | HR |  | - - - |  |  | Chancellor | delegated
| Storage Expansion (935470) | [6 empty] | W | 100 | HR
[8 empty] | C | 580 | HR
702
G. | Parking Lot 35 (936583) |  | 900 | X |  | - - - |  | P | 75 | X |  | - - - |  |  | Chancellor | delegated
[8 empty] | W | 85 | X
[8 empty] | C | 740 | X
900
H. | Sixteen College Park |  | 347 | X |  | - - - |  | P | 112 | X |  | - - - |  |  | Chancellor | delegated
| (932030) |  | 912 | G |  |  |  | C | 235 | X
|  |  | 1259 |  |  |  |  | C | 912 | G
1259
I. | Russell Boulevard Bike Path |  | 231 | F |  | - - - |  | P | 10 | X | C | 12 | X |  | Chancellor | delegated | N/A | 1995-98 CIP | 327
| Improvements |  | 108 | X |  |  |  | W | 15 | X
| ( 936586) |  | 339 |  |  |  |  | C | 71 | X
[8 empty] | C | 231 | F
327
J. | Unitrans Compressed Natural Gas |  | 233 | X | PW | 99 | X | C | 2 | F |  | - - - |  |  | Chancellor | delegated | 7/95 | 1994-97 CIP | 1185
| Facility (931820) |  | 1062 | F | C | 26 | X | C | 108 | X
|  |  | 1295 |  | C | 1060 | F |  | 110
1185
K. | UCDMC ASB I.S. Renovation |  | 942 | HR | P | 61 | HR | C | 125 | HR |  | - - - |  |  | Chancellor | delegated | 7/95 | 1994-97 CIP | 817
| (935250) |  |  |  | W | 102 | HR
[5 empty] | C | 654 | HR
817
L. | UCDMC Hospital Power |  | 474 | HR | P | 10 | HR | W | 3 | HR | C | 33 | HR |  | Chancellor | delegated | 7/95 | 1994-97 CIP | 410
| Conditioning (935300) |  |  |  | W | 55 | HR | C | 28 | HR | [6 empty] | N/A | 1995-98 CIP | 441
[5 empty] | C | 345 | HR |  | 31
410
M. | UCDMC Radiology Interim |  | 481 | HR | P | 35 | HR | C | 124 | HR |  | - - - |  |  | Chancellor | delegated | 5/93 | 1992-95 CIP | 358
| Project (935210) |  |  |  | W | 48 | HR
[5 empty] | C | 274 | HR
357
N. | UCDMC Child Care Center (935240) |  | 2710 | HR | P | 148 | HR | C | 2341 | HR |  | - - - |  |  | Chancellor | delegated | 7/95 | 1994-97 CIP | 2800
[5 empty] | W | 221 | HR
369
O. | UCDMC Vacuum System Upgrade
| (935350) |  | 356 | HR | P | 2 | HR | C | 33 | HR |  | - - - |  |  | Chancellor | delegated | 7/95 | 1994-97 CIP | 323
[5 empty] | W | 33 | HR
[5 empty] | C | 288 | HR
323
P. | Campus Wastewater Treatment | ( | 16174 | ) | P | 300 | X | P | 509 | X | (W | 842 | ) | 11/95 | Regents' | N/A | 11/94 | 1995-98 CIP | 16983
| Plant (936053) |  | 809 | X | [6 empty] | (W | 15332 | ) |  | Budget
|  |  | 16983 | [8 empty] | 16174
| Federal Funds (F) |  | 1293 | F |  | 1060 | F |  | 233 | F |  | 0 |  |  | 0
| Gifts (G) |  | 912 | G |  | 0 |  |  | 912 | G |  | 0 |  |  | 0
| Hospital Reserve Funds (HR) |  | 8904 | HR |  | 2276 | HR |  | 6595 | HR |  | 33 | HR |  | 0
| Bank Loans or Bonds (LB) |  | 76489 | LB |  | 68400 | LB |  | 8089 | LB |  | 0 |  |  | 0
Reserves other than Unversity
| Registration Fee (N) |  | 8229 | N |  | 0 |  |  | 8229 | N |  | 0 |  |  | 0
| University Registration Fee (R) |  | 3250 | R |  | 0 |  |  | 3250 | R |  | 0 |  |  | 0
| Other (i.e. campus funds) (X) |  | 3947 | X |  | 425 | X |  | 3510 | X |  | 12 | X |  | 0
| TOTAL |  | 103024 |  |  | 72161 |  |  | 30818 |  |  | 45 |  |  | 0
| STATE FUNDS | ( | 16174 | ) | ( | 0 | ) | ( | 0 | ) | ( | 16174 | ) |  | 0

## Irvine
IRVINE CAMPUS
1995-96 NON-STATE CAPITAL BUDGET
($000)
[9 empty] | C U R R E N T S T A T U S | [7 empty] | PRIOR ACTION/COMMENTS
|  |  | Project | [8 empty] | Beyond |  |  |  | Approval
| Project |  | Cost |  |  | Prefunded |  |  | 1995-96 |  |  | 1995-96 |  | Action |  | Letter | Date | Action | Cost
A. | Neuroscience Research Facility |  | 10781 | G | P | 1200 | G | C | 781 | G |  | - - - |  | 3/96 | Admin | 3/25/96 | 1/93 | 1992-95 CIP | 21125
| (994055) |  | 10053 | LB | W | 1455 | G | [9 empty] | 7/95 | 1994-97 CIP | 22702
|  |  | 2649 | X | C | 7345 | G
|  |  | 23483 |  | C | 10053 | LB
[5 empty] | C | 2649 | X
22702
B. | UCI Medical Plaza Tenant |  | 821 | HR |  | - - - |  | P | 42 | HR |  | - - - |  |  | Chancellor | delegated
| Improvements - Primary Care | [6 empty] | W | 39 | HR
| (994290) | [6 empty] | C | 740 | HR
821
C. | Clinical Cancer Center - 4th |  | 2175 | G |  | - - - |  | P | 238 | HR |  | - - - |  |  | Chancellor | delegated
| Floor Completion (994404) |  | 325 | X |  |  |  | W | 178 | HR
|  |  | 500 | HR |  |  |  | C | 84 | HR
|  |  | 3000 |  |  |  |  | C | 325 | X
[8 empty] | C | 2175 | G
3000
D. | Health Sciences Parking Lot |  | 800 | N |  | - - - |  | P | 35 | N |  | - - - |  |  | Chancellor | delegated
| Extension (996635) | [6 empty] | W | 43 | N
[8 empty] | C | 722 | N
800
E. | Financial Aid Office Renovation |  | 290 | X |  | - - - |  | P | 15 | X |  | - - - |  |  | Chancellor | delegated
| (991162) | [6 empty] | W | 14 | X
[8 empty] | C | 261 | X
290
F. | Widen Bridge Road-Mesa Road |  | 319 | N |  | - - - |  | P | 16 | N |  | - - - |  |  | Chancellor | delegated
| to California Avenue | [6 empty] | W | 15 | N
| (996549) | [6 empty] | C | 288 | N
319
G. | Dance Studio and Humanities | ( | 719 | ) |  | 43 | X | (W | 39 | ) |  | - - - |  | 11/95 | Regents' | N/A
| Hall Seismic Improvements |  | 43 | X |  |  |  | (C | 680 | ) |  |  |  |  | Budget
| (991075) |  | 762 | [5 empty] | 719
H. | Social Sciences Facilities | ( | 888 | ) |  | 35 | X | (W | 37 | ) |  | - - - |  | 11/95 | Regents' | N/A
| Seismic Improvements (991305) |  | 35 | X |  |  |  | (C | 851 | ) |  |  |  |  | Budget
|  |  | 923 | [5 empty] | 888
I. | UCIMC Academic Laboratory |  | 3264 | X |  | - - - |  | P | 1263 | X | (W | 300 | ) | 11/95 | Regents' | N/A
| Seismic Replacement Facility | ( | 19734 | ) | [6 empty] | (C | 18900 | ) |  | Budget
| (994400) |  | 22998 | [7 empty] | (E | 534 | )
[11 empty] | E | 2001 | X
21735
| Gifts (G) |  | 12956 | G |  | 10000 | G |  | 2956 | G |  | 0 |  |  | 0
| Hospital Reserves (HR) |  | 1321 | HR |  | 0 |  |  | 1321 | HR |  | 0 |  |  | 0
| Bank Loans or Bonds (LB) |  | 10053 | LB |  | 10053 | LB |  | 0 |  |  | 0 |  |  | 0
Reserves other than University
| Registration Fee (N) |  | 1119 | N |  | 0 |  |  | 1119 | N |  | 0 |  |  | 0
| Other (i.e. campus funds) (X) |  | 6606 | X |  | 2727 | X |  | 1878 | X |  | 2001 | X |  | 0
| TOTAL |  | 32055 |  |  | 22780 |  |  | 7274 |  |  | 2001 |  |  | 0
0
| STATE FUNDS | ( | 21341 | ) | ( | 0 | ) | ( | 1607 | ) | ( | 19734 | )
0

## Los Angeles
LOS ANGELES CAMPUS
1995-96 NON-STATE CAPITAL BUDGET
($000)
[9 empty] | C U R R E N T S T A T U S | [8 empty] | PRIOR ACTION/COMMENTS
|  |  | Project | [8 empty] | Beyond |  |  |  |  | Approval
| Project |  | Cost |  |  | Prefunded |  |  | 1995-96 |  |  | 1995-96 |  | Action |  |  | Letter | Date | Action | Cost
A. | Science and Technology Research |  | 45000 | LB |  | - - - |  | P | 2133 | LB | P | 780 | LB | 9/95 |  | Admin | 9/21/95 | 3/90 | 1989-92 CIP | 55775
| Building (942030) | [6 empty] | W | 1341 | LB | W | 980 | LB |  |  |  |  | 5/93 | 1992-95 CIP | 47794
[8 empty] | C | 20088 | LB | C | 14678 | LB
[8 empty] | E | 3000 | LB | E | 2000 | LB
[9 empty] | 26562 |  |  | 18438
B. | Molecular Neuroscience Research |  | 48260 | G |  | - - - |  | P | 2508 | G |  | - - - |  | 3/96 |  | Regents | 3/22/96 | 1/93 | 1992-95 CIP | 38905
| Center (945930) | [6 empty] | W | 2056 | G
[8 empty] | C | 43246 | G
[8 empty] | E | 450 | G
48260
C. | Rieber Hall Food Service Alterations |  | 5100 | LB |  | - - - |  | P | 152 | N |  | - - - |  | 5/96 |  | Admin | 5/17/96
| (946250) |  | 537 | N |  |  |  | W | 385 | N
|  |  | 5637 |  |  |  |  | W | 102 | LB
[8 empty] | C | 3834 | LB
[8 empty] | E | 1164 | LB
5637
D. | Royce Hall Seismic Corrections |  | 39157 | F |  |  |  | P | 1820 | F | C | 9245 | LB | 11/99 | To Regents |  | pending | 9/95 | Admin | 49686
| (948712) |  | 3010 | G |  |  |  | (P | 205 | )
|  |  | 296 | X |  |  |  | W | 2518 | F
|  |  | 9245 | LB |  |  |  | (W | 280 | )
|  | ( | 4351 | ) |  |  |  | W | 151 | G
|  |  | 56059 |  |  |  |  | C | 34819 | F
[8 empty] | (C | 3866 | )
[8 empty] | C | 2859 | G
[8 empty] | C | 296 | X
46814
E. | UES Temporary Classroom |  | 729 | X |  | - - - |  | PW | 60 | X |  | - - - |  |  |  | Chancellor | delegated
| Facilities (942817) | [6 empty] | C | 669 | X
729
F. | MP 200 B-2 Revlon Breast |  | 500 | G |  | - - - |  | P | 30 | G |  | - - - |  |  |  | Chancellor | delegated
| Center Renovation |  | 500 | HR |  |  |  | W | 100 | G
| -945110 |  | 1000 |  |  |  |  | C | 370 | G
[8 empty] | C | 500 | HR
1000
G. | Sunset East Site Development |  | 455 | X |  | - - - |  | P | 45 | X |  | - - - |  |  |  | Chancellor | delegated
| -946058 | [6 empty] | W | 35 | X
[8 empty] | C | 375 | X
455
H. | Parking Structure #5 AGSM Plaza |  | 515 | X |  | - - - |  | P | 69 | X |  | - - - |  |  |  | Chancellor | delegated
| Alterations (946061) |  | 50 | N |  |  |  | W | 46 | X
|  |  | 565 |  |  |  |  | C | 400 | X
[8 empty] | C | 50 | N
565
I. | Ueberroth Office for Protection of |  | 277 | X |  | - - - |  | P | 10 | X |  | - - - |  |  |  | Chancellor | delegated
| Research Subjects Alterations | [6 empty] | W | 20 | X
| (948180) | [6 empty] | C | 147 | X
[8 empty] | E | 100 | X
277
J. | Ackerman Grand Ballroom |  | 741 | N |  | - - - |  | PW | 5 | N |  | - - - |  |  |  | Chancellor | delegated
| Renovation (941190) | [6 empty] | C | 736 | N
741
K. | Santa Monica Pier Ocean Discovery |  | 324 | X |  | - - - |  | PW | 47 | X |  | - - - |  |  |  | Chancellor | delegated
| Center (942880) | [6 empty] | C | 277 | X
324
L. | SOM 34-115 Colicelli Wet Lab |  | 136 | X |  | - - - |  | P | 8 | X |  | - - - |  |  |  | Chancellor | delegated
| Renovation (945550) |  | 150 | F |  |  |  | W | 20 | X
|  |  | 286 |  |  |  |  | C | 108 | X
[8 empty] | C | 150 | F
286
M. | SOM 46-119 Wet Lab Renovation |  | 522 | X |  | - - - |  | P | 20 | X |  | - - - |  |  |  | Chancellor | delegated
| (945560) | [6 empty] | W | 50 | X
[8 empty] | C | 452 | X
522
N. | SOM 53-120 Physiology Wet Lab |  | 301 | X |  | - - - |  | P | 15 | X |  | - - - |  |  |  | Chancellor | delegated
| Renovation (945570) | [6 empty] | W | 20 | X
[8 empty] | C | 266 | X
301
O. | SOM 63-314 Neurobiology Wet |  | 400 | X |  |  |  | P | 10 | X | P | 40 | X |  |  | Chancellor | delegated | N/A | 1995-98 CIP | 302
| Laboratory Renovation (945580) | [6 empty] | W | 15 | X | W | 0 | X
[8 empty] | C | 277 | X | C | 58 | X
[9 empty] | 302 |  |  | 98
P. | SOM 73-152 Neurobiology Wet Lab |  | 302 | X |  | - - - |  | P | 10 | X |  | - - - |  |  |  | Chancellor | delegated
| Renovation (945590) | [6 empty] | W | 15 | X
[8 empty] | C | 277 | X
302
Q. | UCLA Satellite Medical Facilities |  | 1795 | N |  | - - - |  | P | 10 | X |  | - - - |  |  |  | Chancellor | delegated
| -945630 |  | 10 | X |  |  |  | P | 90 | N
|  |  | 1805 |  |  |  |  | W | 100 | N
[8 empty] | C | 1605 | N
1805
R. | NPI Wet Lab Alterations (945870) |  | 354 | G |  | - - - |  | S | 15 | G |  | - - - |  |  |  | Chancellor | delegated
[8 empty] | P | 15 | G
[8 empty] | W | 15 | G
[8 empty] | C | 289 | G
[8 empty] | E | 20 | G
354
S. | SOM 1P-109 Pathology Alterations |  | 188 | HR |  | - - - |  | P | 10 | X |  | - - - |  |  |  | Chancellor | delegated
| (945940) |  | 187 | X |  |  |  | W | 20 | X
|  |  | 375 |  |  |  |  | C | 157 | X
[8 empty] | C | 188 | HR
375
T. | Parking Services Access/ Control |  | 2736 | N |  | - - - |  | PW | 140 | N |  | - - - |  |  |  | Chancellor | delegated
| Alterations | [6 empty] | C | 2596 | N
| (946660) | [7 empty] | 2736
U. | CSB I Tank Seismic Repair |  | 1146 | F |  | - - - |  | (P | 127 | ) |  | - - - |  |  |  | Chancellor | delegated
| (948721) | ( | 127 | ) |  |  |  | P | 73 | F
|  |  | 1273 |  |  |  |  | W | 200 | F
[8 empty] | C | 873 | F
1273
V. | Kerckhoff Seismic Repair |  | 2366 | F |  | - - - |  | P | 50 | X |  | - - - |  |  |  | Chancellor | delegated
| (948759) |  | 621 | X |  |  |  | W | 200 | X
|  | ( | 263 | ) |  |  |  | C | 2366 | F
|  |  | 3250 |  |  |  |  | C | 371 | X
[8 empty] | (C | 263 | )
3250
W. | Medical Center BRI A and B Level |  | 2507 | X |  | - - - |  | P | 123 | X |  | - - - |  |  |  | Chancellor | delegated | 2/95 | 1994-97 CIP | 2507
| Alterations (945660) | [6 empty] | W | 250 | X
[8 empty] | C | 2134 | X
2507
X. | School of Medicine Pathology - |  | 1690 | X | P | 150 | HR | C | 1690 | X |  | - - - |  |  |  | Chancellor | delegated | 7/95 | 1994-97 CIP | 1700
| 1st Floor Renovation |  | 557 | HR | W | 250 | HR
| -945670 |  | 2247 |  | C | 157 | HR
557
Y. | Cyclotron Pharmacology Renovation |  | 380 | F |  | - - - |  | P | 40 | F | W | 65 | F |  |  | Chancellor | delegated | 5/95 | 1994-97 CIP | 302
| -945510 |  | 315 | X |  |  |  | C | 180 | F | C | 315 | X |  |  |  |  | N/A | 1995-98 CIP | 540
|  |  | 695 | [5 empty] | 220 |  | E | 95 | F
475
Z. | Public Policy Building |  | 4032 | X | P | 286 | X | W | 100 | X |  | - - - |  |  |  | Chancellor | delegated | 5/94 | 1993-96 CIP | 2255
| Refurbishment |  | 400 | LB | W | 143 | X | C | 400 | LB | [7 empty] | 6/95 | 1994-97 CIP | 3810
| -943480 |  | 4432 |  | C | 3381 | X | C | 122 | X
[6 empty] | 3810 |  |  | 622
AA. | Knudsen Hall Seismic Correction, | ( | 2579 | ) |  | - - - |  | P | 122 | X | (W | 145 | ) | 11/95 |  | Regents' | N/A
| Phase 1 (948725) |  | 122 | X | [6 empty] | (C | 2434 | ) |  |  | Budget
|  |  | 2701 | [8 empty] | 2579
BB. | Slichter Hall Seismic Correction | ( | 3320 | ) |  | - - - |  | P | 159 | X | (W | 185 | ) | 11/95 |  | Regents' | N/A
| (948705) |  | 159 | X | [6 empty] | (C | 3135 | ) |  |  | Budget
|  |  | 3479 | [8 empty] | 3320
| Gifts (G) |  | 52124 | G |  | 0 |  |  | 52124 | G |  | 0 |  |  |  | 0
| Federal Funds (F) |  | 43199 | F |  | 0 |  |  | 43039 | F |  | 160 |  |  |  | 0
| Hospital Reserves (HR) |  | 1245 | HR |  | 557 | HR |  | 688 | HR |  | 0 |  |  |  | 0
| Bank Loans or Bonds (LB) |  | 59745 | LB |  | 0 |  |  | 32062 | LB |  | 27683 | LB |  |  | 0
| Reserves other than Unviersity | [14 empty] | 0
| Registration Fee (N) |  | 5859 | N |  | 0 |  |  | 5859 | N |  | 0 |  |  |  | 0
| Other (i.e. campus funds) (X) |  | 13900 | X |  | 3810 | X |  | 9677 | X |  | 413 |  |  |  | 0
0
| TOTAL |  | 176072 |  |  | 4367 |  |  | 143449 |  |  | 28256 |  |  |  | 0
| STATE FUNDS | ( | 10640 | ) |  | 0 |  | ( | 4741 | ) | ( | 5899 | ) |  |  | 0

## Riverside
RIVERSIDE CAMPUS
1995-96 NON-STATE CAPITAL BUDGET
($000)
[9 empty] | C U R R E N T S T A T U S | [7 empty] | PRIOR ACTION/COMMENTS
|  |  | Project | [8 empty] | Beyond |  |  |  | Approval
| Project |  | Cost |  |  | Prefunded |  |  | 1995-96 |  |  | 1995-96 |  | Action |  | Letter | Date | Action | Cost
A. | Child Development Center (950405) |  | 1782 | LB |  | - - - |  | P | 30 | X |  | - - - |  |  | Chancellor | delegated
|  |  | 100 | X |  |  |  | W | 40 | X
|  |  | 1882 |  |  |  |  | C | 1782 | LB
[8 empty] | C | 7 | X
[8 empty] | E | 23 | X
1882
B. | Public Safety Building Seismic | ( | 1762 | ) | P | 87 | X | (W | 83 | ) | (C | 1597 | ) | 11/95 | Regents' | N/A | 11/94 | 1995-98 CIP | 1849
| Replacement (950416) |  | 87 | X | [6 empty] | (E | 82 | ) |  | Budget
|  |  | 1849 | [8 empty] | 1679
C. | Geology Building Seismic Upgrade | ( | 864 | ) |  |  |  | P | 45 | X | (W | 50 | ) | 11/95 | Regents' | N/A
| (950334) |  | 45 | X | [6 empty] | (C | 814 | ) |  | Budget
|  |  | 909 | [8 empty] | 864
D. | Physics Building Seismic Upgrade | ( | 887 | ) |  |  |  | P | 50 | X | (W | 57 | ) | 11/95 | Regents' | N/A
| (958717) |  | 50 | X | [6 empty] | (C | 830 | ) |  | Budget
|  |  | 937 | [8 empty] | 887
E. | Boyce Hall Seismic Upgrade | ( | 2422 | ) |  |  |  | P | 50 | X | (W | 143 | ) | 11/96 | Regents' | N/A | 11/95 | 1995-98 CIP | 2187
| (958715) |  | 50 | X | [6 empty] | (C | 2279 | ) |  | Budget
|  |  | 2472 | [8 empty] | 2422
| Banks Loans or Bonds (LB) |  | 1782 | LB |  | 0 |  |  | 1782 | LB |  | 0 |  |  | 0
| Other (i.e. Campus Funds) (X) |  | 332 | X |  | 87 | X |  | 245 | X |  | 0 |  |  | 0
| Gifts (G) |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
| TOTAL |  | 2114 |  |  | 87 |  |  | 2027 |  |  | 0 |  |  | 0
| STATE FUNDS | ( | 5935 | ) | ( | 0 | ) | ( | 83 | ) | ( | 5852 | ) |  | 0

## San Diego
SAN DIEGO CAMPUS
1995-96 NON-STATE CAPITAL BUDGET
($000)
[9 empty] | C U R R E N T S T A T U S | [7 empty] | PRIOR ACTION/COMMENTS
|  |  | Project | [8 empty] | Beyond |  |  |  | Approval
| Project |  | Cost |  |  | Prefunded |  |  | 1995-96 |  |  | 1995-96 |  | Action |  | Letter | Date | Action | Cost
A. | UCSD Medical Center Energy |  | 9005 | LB |  | - - - |  | P | 36 | X |  | - - - |  | 7/95 | Regents | 8/8/95
| Conservation Projects (966079) |  | 770 | X |  |  |  | W | 638 | X
|  |  | 9775 |  |  |  |  | C | 96 | X
[8 empty] | C | 9005 | LB
9775
B | Campus Energy Conservation |  | 9475 | LB |  | - - - |  | P | 41 | X |  | 752 | X |  |  | 3/13/96 | 11/95 | Regents | 10068
| Project, Phase I (968259) |  | 1332 | X |  |  |  | W | 500 | X
|  |  | 10807 |  |  |  |  | C | 39 | X
[8 empty] | C | 9475 | LB
10055
C. | Thornton Hospital and Perlman Ambulatory Care Center (965000) |  | 74147 | LB | P | 1785 | LB | C | 6470 | G |  | - - - |  | 6/96 | Admin | 6/24/96 | 5/87 | 1986-89 CIP | 62000
|  |  | 6470 | G | W | 3717 | LB | C | 6434 | HR | [6 empty] | 7/88 | 1988-91 CIP | 74147
|  |  | 6434 | HR | C | 68645 | LB | C | 20 | X
|  |  | 20 | X |  | 74147 |  |  | 12924
87071
D. | UCSDMC 5th Floor IMU |  | 334 | HR |  | - - - |  | P | 34 | HR |  | - - - |  |  | Chancellor | delegated
| (965360) | [6 empty] | W | 60 | HR
[8 empty] | C | 240 | HR
334
E. | Muir Biology 5th Floor Laboratories Remodel (962440) |  | 313 | X |  | - - - |  | P | 11 | X |  | - - - |  |  | Chancellor | delegated
[8 empty] | W | 13 | X
[8 empty] | C | 289 | X
313
F. | Central Utility Plant - Cooling Tower CT-7 (966125) |  | 560 | X |  | - - - |  | P | 20 | X |  | - - - |  |  | Chancellor | delegated
[8 empty] | W | 25 | X
[8 empty] | C | 515 | X
560
G. | Urey Hall 7th Floor Lab Renovation (962430) |  | 351 | X |  | - - - |  | P | 12 | X |  | - - - |  |  | Chancellor | delegated
[8 empty] | W | 16 | X
[8 empty] | C | 323 | X
351
H. | Torrey Pines Center South Suite 415 Tenant Improvements (962460) |  | 359 | X |  | - - - |  | P | 6 | X |  | - - - |  |  | Chancellor | delegated
[8 empty] | W | 7 | X
[8 empty] | C | 232 | X
[8 empty] | E | 114 | X
359
I. | UCSDMC Radiology Film Processing Room (965370) |  | 274 | HR |  | - - - |  | P | 18 | HR |  | - - - |  |  | Chancellor | delegated
[8 empty] | W | 26 | HR
[8 empty] | C | 212 | HR
[8 empty] | E | 18 | HR
274
J. | UCSDMC Arbor/Bachman Parking Structures Seismic Improvements (968739) |  | 422 | N |  | - - - |  | P | 50 | N |  | - - - |  |  | Chancellor | delegated
[8 empty] | W | 76 | N
[8 empty] | C | 296 | N
422
K. | Administrative Computing and Telecommunications - Central Utility Plant Renovation and Expansion (966126) |  | 897 | X |  | - - - |  | P | 5 | X |  | - - - |  |  | Chancellor | delegated
[8 empty] | W | 45 | X
[8 empty] | C | 847 | X
897
L. | Coast Apartments Renovation |  | 4183 | N |  | - - - |  | P | 163 | N |  | - - - |  |  | Chancellor | delegated
| (966300) | [6 empty] | W | 204 | N
[8 empty] | C | 3716 | N
[8 empty] | E | 100 | N
4183
M. | Dance Studio Facility (961820) |  | 3049 | X |  | - - - |  | P | 125 | X | C | 49 | X |  | Chancellor | delegated |  | 1995-98 CIP | 3000
[8 empty] | W | 150 | X
[8 empty] | C | 2725 | X
3000
N. | Underground Storage Tanks - |  | 503 | X |  | - - - |  | P | 6 | X |  | 85 | X |  | Chancellor | delegated | 1/96 | 1995-96 | 418
| Removal/Replacement/Cleanup | [6 empty] | W | 27 | X
| (966124) | [6 empty] | C | 385 | X
418
O. | UCSD Medical Center Regional Burn Center Expansion and Modernization (965170) |  | 1804 | HR | W | 111 | HR | P | 230 | HR |  | - - - |  |  | Chancellor | delegated | 9/92 | 1991-94 CIP | 3182
|  |  | 1025 | X | W | 55 | G | W | 125 | HR
|  |  | 513 | G | C | 976 | X | W | 49 | X
|  |  | 3342 |  | C | 1338 | HR | C | 458 | G
[6 empty] | 2480 |  |  | 862
P. | Urey Hall 6th Floor Biochemistry |  | 713 | X | P | 22 | X
| Remodel (962420) |  |  |  | W | 28 | X
[5 empty] | C | 613 | X | C | 50 | X |  | - - - |  |  | Chancellor | delegated | 4/95 | 1994-97 CIP | 666
[6 empty] | 663 |  |  | 50
Q. | University Center Building 303 Expansion and Upgrade (965270) |  | 374 | G | P | 59 | G |  |  |  |  | - - - |  |  | Chancellor | delegated | 10/94 | 1994-97 CIP | 1307
|  |  | 945 | X | W | 73 | G
|  |  | 1319 |  | C | 242 | G
[5 empty] | C | 933 | X | C | 12 | X
[6 empty] | 1307 |  |  | 12
R. | SIO Aquarium/Museum Plaza - Whale Educational Exhibit (962390) |  | 500 | G | P | 20 | G |  |  |  |  | - - - |  |  | Chancellor | delegated | 10/94 | 1994-97 CIP | 500
|  |  | 159 | X | W | 25 | G | W | 27 | X
|  |  | 659 |  | C | 455 | G | E | 132 | X
[6 empty] | 500 |  |  | 159
S. | Revelle College Dining Commons Remodel (966270) |  | 2230 | N | P | 74 | N |  |  |  |  | - - - |  |  | Chancellor | delegated | 5/95 | 1994-97 CIP | 2200
[5 empty] | W | 94 | N
[5 empty] | C | 1712 | N | E | 350 | N
[6 empty] | 1880 |  |  | 350
T. | Bonner Hall Improvements (962100) |  | 1994 | F | P | 100 | X |  |  |  |  | - - - |  |  | Chancellor | delegated | 6/95 | 1994-97 CIP | 2281
|  |  | 1346 | X | W | 130 | X
|  |  | 3340 |  | C | 57 | X
[5 empty] | C | 1994 | F | C | 1059 | X
[6 empty] | 2281 |  |  | 1059
U. | Voigt/Russell/Rupertus Parking Lots (966590) |  | 399 | X | P | 24 | N | P | 32 | N |  | - - - |  |  | Chancellor | delegated | 9/94 | 1994-97 CIP | 612
|  |  | 774 | N | W | 31 | N | W | 38 | N
|  |  | 1173 |  | C | 557 | N | C | 92 | N
[6 empty] | 612 |  | C | 399 | X
561
V. | Classroom Building 1 (961770) | ( | 11760 | ) | P | 406 | X | (E | 341 | ) |  | - - - |  | 10/94 | Regents' | N/A | 10/91 | 1992-95 CIP | 11986
|  |  | 933 | X | W | 527 | X | [7 empty] | Budget |  | 10/92 | 1993-96 CIP | 12682
|  |  | 12693 |  | (C | 11419 | ) | [9 empty] | 11/93 | 1994-97 CIP | 12693
12352
W. | UCDMC North Annex Seismic | ( | 6282 | ) | P | 214 | X | (W | 288 | ) | (E | 97 | ) | 10/95 | Regents' | N/A | 11/93 | 1994-97 CIP | 995
| Replacement Facility (965250) |  | 214 | X |  |  |  | (C | 5897 | ) |  |  |  |  | Budget |  | 11/94 | 1995-98 CIP | 1041
|  |  | 6496 | [5 empty] | 6185
X. | Vaughn Hall Replacement/ | ( | 2546 | ) | P | 100 | X | W | 131 | X | C | 1016 | X | 10/95 | Regents' | N/A | 11/93 | 1994-97 CIP | 2855
| Nierenberg Hall Annex (961800) |  | 1297 | X | W | 50 | X |  |  |  | (C | 2546 | ) |  | Budget |  | 11/94 | 1995-98 CIP | 3843
|  |  | 3843 |  |  | 150 | [5 empty] | 3562
Y. | Ritter Hall Seismic Replacement | ( | 16370 | ) | P | 609 | X | (W | 759 | ) |  | - - - |  | 10/95 | Regents' | N/A
| and Renovation (962410) |  | 609 | X |  |  |  | (C | 15611 | ) |  |  |  |  | Budget
|  |  | 16979 | [5 empty] | 16370
Z. | York Hall Improvements (962340) | ( | 4628 | ) |  | - - - |  | P | 204 | X | (W | 215 | ) | 10/95 | Regents' | N/A
|  |  | 204 | X | [6 empty] | (C | 4413 | ) |  | Budget
|  |  | 4832 | [8 empty] | 4628
| Federal Funds (F) |  | 1994 | F |  | 1994 | F |  | 0 |  |  | 0 |  |  | 0
| Gifts (G) |  | 7857 | G |  | 929 | G |  | 6928 | G |  | 0 |  |  | 0
| Hospital Reserves (HR) |  | 8846 | HR |  | 1449 | HR |  | 7397 | HR |  | 0 |  |  | 0
| Bank Loans or Bonds (LB) |  | 92627 | LB |  | 74147 | LB |  | 18480 | LB |  | 0 |  |  | 0
Reserves other than University
| Registration Fee (N) |  | 7609 | N |  | 2492 | N |  | 5117 | N |  | 0 |  |  | 0
| Other (i.e. campus funds) (X) |  | 15998 | X |  | 4765 | X |  | 9331 | X |  | 1902 | X |  | 0
| TOTAL |  | 134931 |  |  | 85776 |  |  | 47253 |  |  | 1902 |  |  | 0
| STATE FUNDS | ( | 41586 | ) | ( | 11419 | ) | ( | 22896 | ) | ( | 7271 | ) |  | 0

## San Francisco
SAN FRANCISCO CAMPUS
1995-96 NON-STATE CAPITAL BUDGET
($000)
[9 empty] | C U R R E N T S T A T U S | [7 empty] | PRIOR ACTION/COMMENTS
|  |  | Project | [8 empty] | Beyond |  |  |  | Approval
| Project |  | Cost |  | Prefunded |  |  |  | 1995-96 |  |  | 1995-96 |  | Action |  | Letter | Date | Action | Cost
A. | Laurel Heights Infrastructure |  | 30057 | LB |  | - - - |  | P | 1405 | X |  | - - - |  | 5/96 | Regents | 5/22/96
| and Tenant Improvement |  | 9266 | X |  |  |  | W | 2166 | X
| Project (921320) |  | 39323 |  |  |  |  | C | 4175 | X
[8 empty] | C | 30057 | LB
[8 empty] | E | 1520 | X
39323
B. | MU-H Student Health |  | 1796 | LB |  | - - - |  | P | 180 | LB |  | - - - |  |  | Chancellor | delegated
| Services/CPR Training Facility | [6 empty] | W | 270 | LB
| Renovation | [6 empty] | C | 1346 | LB
| (920320) | [7 empty] | 1796
C. | MU-J Commercial Space |  | 581 | N |  | - - - |  | P | 30 | N |  |  |  |  | Chancellor | delegated
| Development (921270) | [6 empty] | W | 56 | N
[8 empty] | C | 495 | N
581
D. | S-1 Lobby Improvements |  | 1175 | X |  | - - - |  | P | 65 | X |  | - - - |  |  | Chancellor | delegated
| (925340) |  | 100 | G |  |  |  | W | 115 | X
|  |  | 1275 |  |  |  |  | C | 995 | X
[8 empty] | C | 100 | G
1275
E. | Parnassus Network |  | 633 | X |  | - - - |  | P | 0 |  |  | - - - |  |  | Chancellor | delegated
| Infrastructure Improvements, | [6 empty] | W | 0
| Project 1 (920130) | [6 empty] | C | 633 | X
633
F. | UCH Phases 1,2 Acute |  | 1540 | X |  | - - - |  | P | 60 | X |  | - - - |  |  | Chancellor | delegated
| Seismic Hazard Corrections | [6 empty] | W | 115 | X
| (921050) | [6 empty] | C | 1365 | X
1540
G. | MC Long-G Radiation |  | 353 | HR |  | - - - |  | P | 19 | HR |  | - - - |  |  | Chancellor | delegated
| Oncology K-2 Linear | [6 empty] | W | 34 | HR
| Accelerator Installation | [6 empty] | C | 300 | HR
| (921180) | [7 empty] | 353
H. | MC Moffitt-13E Pediatric |  | 1799 | HR |  | - - - |  | P | 94 | HR |  | - - - |  |  | Chancellor | delegated
| Cardiac Catheterization Lab | [6 empty] | W | 173 | HR
| Remodel (929440) | [6 empty] | C | 1532 | HR
1799
I | MC Moffitt-3 Radiology |  | 383 | HR |  | - - - |  | P | 21 | HR |  | - - - |  |  | Chancellor | delegated
| Fluoroscopy Alterations | [6 empty] | W | 44 | HR
| (921150) | [6 empty] | C | 318 | HR
383
J. | MC Moffitt-5 Histology |  | 335 | HR |  | - - - |  | P | 21 | HR |  | - - - |  |  | Chancellor | delegated
| Ventilation Corrections | [6 empty] | W | 62 | HR
| (921170) | [6 empty] | C | 252 | HR
335
K. | MC MtZion 2330 Post St. -4,5 |  | 1430 | HR |  | - - - |  | P | 69 | HR |  | - - - |  |  | Chancellor | delegated
| Medical Office Building Tenant | [6 empty] | W | 106 | HR
| Improvements (921160) | [6 empty] | C | 1255 | HR
1430
L. | School of Dentistry MSB-7 |  | 611 | X |  | - - - |  | P | 38 | X |  | - - - |  |  | Chancellor | delegated
| Growth & Development | [6 empty] | W | 55 | X
| Laboratory Renovation | [6 empty] | C | 518 | X
| (921070) | [7 empty] | 611
M. | School of Medicine HSE-13 |  | 2746 | X |  | - - - |  | P | 186 | X |  | - - - |  |  | Chancellor | delegated
| Cardiovascular Institute | [6 empty] | W | 235 | X
| Research Laboratory | [6 empty] | C | 2325 | X
| Renovation (921140) | [7 empty] | 2746
N. | School of Medicine HSE-5 |  | 669 | X |  | - - - |  | P | 39 | X |  | - - - |  |  | Chancellor | delegated
| Liver Transplant Laboratory | [6 empty] | W | 51 | X
| Renovation (921000) | [6 empty] | C | 579 | X
669
O. | School of Medicine HSE-6,7 |  | 2252 | X |  | - - - |  | P | 206 | X | P | 95 | X | 2/99 | Admin | 9/24/99 | 12/95 | Chancellor Approved | 4200
| Neurology Lab Renovation |  | 3150 | G |  |  |  | W | 383 | X | W | 160 | X
| (921060) |  | 5402 |  |  |  |  | C | 3000 | G | C | 797 | X
[8 empty] | C | 611 | X | C | 150 | G
[9 empty] | 4200 |  |  | 1202
P. | School of Medicine Moffitt-9 |  | 695 | X |  | - - - |  | P | 51 | X |  | - - - |  |  | Chancellor | delegated
| Department of Medicine | [6 empty] | W | 79 | X
| Chairman's Suite Renovation | [6 empty] | C | 565 | X
| (921010) | [7 empty] | 695
Q. | School of Medicine |  | 977 | G |  | - - - |  | P | 61 | G |  | - - - |  |  | Chancellor | delegated
| MSB-10,11 Biochemistry | [6 empty] | W | 97 | G
| Laboratory Alteration (920830) | [6 empty] | C | 819 | G
977
R. | School of Medicine MSB-7 |  | 676 | X |  | - - - |  | P | 38 | X |  | - - - |  |  | Chancellor | delegated
| Physiology/Cell Biology | [6 empty] | W | 58 | X
| Research Laboratory | [6 empty] | C | 580 | X
| Renovation (921260) | [7 empty] | 676
S. | School of Medicine SFGH 1-2 |  | 2747 | X |  | - - - |  | P | 168 | X |  | - - - |  |  | Chancellor | delegated
| Surgery Research Laboratory | [6 empty] | W | 282 | X
| Renovation (920660) | [6 empty] | C | 2297 | X
2747
T. | School of Pharmacy UCH-G |  | 1012 | X |  | - - - |  | P | 66 | X |  | - - - |  |  | Chancellor | delegated
| Department of Pharmacy | [6 empty] | W | 129 | X
| Research Lab Renovation | [6 empty] | C | 817 | X
| (929510) | [7 empty] | 1012
U. | UCSF Disabled Access |  | 904 | X |  | - - - |  | P | 57 | X | P | 9 | HR |  | Chancellor | delegated
| Improvements (921280) |  | 215 | HR |  |  |  | W | 68 | X | W | 16 | HR
|  |  | 1119 |  |  |  |  | C | 779 | X | C | 190 | HR
[9 empty] | 904 |  |  | 215
V. | Parnassus Enterprise Network |  | 896 | X |  | - - - |  | P | 40 | X |  | - - - |  |  | Chancellor | delegated
| Infrastructure Improvements, |  | 624 | HR |  |  |  | W | 42 | X
| Project 3 (921310) |  | 1520 |  |  |  |  | C | 814 | X
[8 empty] | C | 624 | HR
1520
W. | Parnassus Fire Protection | ( | 3665 | ) | (P | 355 | ) | (C | 1781 | ) |  | - - - |  | 11/94 | Regents' | N/A | 11/89 | 1990-93 CIP | 8241
| Water Supply System (928622) |  | 4142 | U | (W | 316 | ) | C | 103 | HR |  |  |  |  | Budget |  | 10/90 | 1991-94 CIP | 7226
|  |  | 423 | HR | PW | 136 | X |  | 1884 | [7 empty] | 11/91 | 1992-95 CIP | 8993
|  |  | 228 | X | W | 9 | X | [9 empty] | 11/92 | 1993-96 CIP | 9096
|  |  | 8458 |  | W | 11 | HR | [9 empty] | 11/93 | 1994-97 CIP | 8372
[5 empty] | PWC | 92 | HR
[5 empty] | C | 217 | HR
[5 empty] | WC | 4142 | U
[5 empty] | C | 83 | X
[5 empty] | (C | 1213 | )
6574
X. | Medical Sciences Building | ( | 13313 | ) |  | - - - |  | P | 482 | X | (W | 622 | ) | 11/95 | Regents' | N/A
| Satety and Utility Improvements, |  | 482 | X | [6 empty] | (C | 12691 | ) |  | Budget
| Phase 1 (921030) |  | 13795 | [8 empty] | 13313
X. | Oyster Point Seismic | ( | 1033 | ) |  | - - - |  | P | 37 | X | (W | 48 | ) | 11/95 | Regents' | N/A
| Improvements (928020) |  | 396 | HR |  |  |  | P | 14 | HR | W | 18 | HR |  | Budget
|  |  | 37 | X |  |  |  |  | 51 |  | (C | 985 | )
|  |  | 1466 | [7 empty] | C | 364 | HR
1415
| Gifts (G) |  | 4227 | G |  | 0 |  |  | 4077 | G |  | 150 | G |  | 0
| Hospital Reserve Funds (HR) |  | 5958 | HR |  | 320 | HR |  | 5041 | HR |  | 597 | HR |  | 0
| Bank Loans or Bonds (LB) |  | 31853 | LB |  | 0 |  |  | 31853 | LB |  | 0 |  |  | 0
| Reserves other than University | [13 empty] | 0
| Registration Fees (N) |  | 581 | N |  | 0 |  |  | 581 | N |  | 0 |  |  | 0
| University Funds (U) |  | 4142 | U |  | 4142 | U |  | 0 | [5 empty] | 0
| Other (i.e. campus funds) (X) |  | 26569 | X |  | 228 | X |  | 25289 | X |  | 1052 | X |  | 0
| TOTAL |  | 73330 |  |  | 4690 |  |  | 66841 |  |  | 1799 |  |  | 0
| STATE FUNDS | ( | 18011 | ) | ( | 1884 | ) | ( | 1781 | ) | ( | 14346 | ) |  | 0

## Santa Barbara
SANTA BARBARA CAMPUS
1995-96 NON-STATE CAPITAL BUDGET
($000)
[9 empty] | C U R R E N T S T A T U S | [7 empty] | PRIOR ACTION/COMMENTS
|  |  | Project | [8 empty] | Beyond |  |  |  | Approval
| Project |  | Cost |  |  | Prefunded |  |  | 1995-96 |  |  | 1995-96 |  | Action |  | Letter | Date | Action | Cost
A. | Energy Conservation Project 2 |  | 11085 | LB |  | - - - |  | P | 332 | LB |  | - - - |  | 9/95 | Regents | 9/21/95
| (988800) | [6 empty] | W | 717 | LB
[8 empty] | C | 10036 | LB
11085
B. | Physical Sciences Building (980580) | ( | 32751 | ) | (P | 800 | ) | C | 1230 | X |  | - - - |  | 9/95 | Admin | 9/20/95
|  |  | 1230 | X | (W | 970 | )
|  |  | 33981 |  | (C | 28405 | )
[5 empty] | (E | 2576 | )
32751
C. | Materials Research Lab (981030) |  | 10797 | X | P | 350 | X | P | 386 | X | C | 552 | X | 10/98 | Admin | Pending | 1/93 | 1992-95 CIP | 9480
[8 empty] | W | 863 | X | [6 empty] | 5/96 | 1995-98 CIP | 10245
[8 empty] | C | 8639 | X
[8 empty] | E | 7 | X
9895
D. | 66kV Power Substation Improvement |  | 1095 | LB |  | - - - |  | P | 138 | LB |  | - - - |  |  | Chancellor | delegated
| Project (986032) | [6 empty] | W | 30 | LB
[8 empty] | C | 927 | LB
1095
E. | HSSB courtyard Improvements |  | 300 | G |  | - - - |  | P | 9 | G |  | - - - |  |  | Chancellor | delegated
| (980820) | [6 empty] | W | 17 | G
[8 empty] | C | 274 | G
300
F. | Tennis Court Relocation Project |  | 1000 | X |  | - - - |  | P | 72 | X |  | - - - |  |  | Chancellor | delegated
| (980605) | [6 empty] | W | 81 | X
[8 empty] | C | 847 | X
1000
G. | Humanities and Social Sciences | ( | 31122 | ) | P | 944 | X | (E | 1105 | ) | (E | 1010 | ) | 11/95 | Regents' | N/A | 10/90 | 1991-94 CIP | 30400
| Building (980830) |  | 944 | X | (W | 1193 | ) | [7 empty] | Budget |  | 11/91 | 1992-95 CIP | 31125
|  |  | 32066 |  | (C | 27814 | ) | [9 empty] | 11/92 | 1993-96 CIP | 31989
[6 empty] | 29951 | [10 empty] | 11/93 | 1994-97 CIP | 32032
[17 empty] | 11/94 | 1995-98 CIP | 32056
H. | Robertson Gymnasium Seismic | ( | 1310 | ) |  | - - - |  | P | 67 | X | (W | 109 | ) | 11/95 | Regents' | N/A
| Corrections (988777) |  | 67 | X | [6 empty] | (C | 1201 | ) |  | Budget
|  |  | 1377 | [8 empty] | 1310
I. | Water System Improvements | ( | 944 | ) |  | - - - |  | P | 58 | X | (C | 944 | ) | 11/95 | Regents' | N/A
| (986060) |  | 129 | X |  |  |  | W | 71 | X |  |  |  |  | Budget
|  |  | 1073 | [5 empty] | 129
J. | Engineering 1 Seismic Corrections | ( | 5450 | ) |  | - - - |  | P | 150 | X | (W | 306 | ) | 11/95 | Regents' | N/A
| (988778) |  | 150 | X | [6 empty] | (C | 5144 | ) |  | Budget
|  |  | 5600 | [8 empty] | 5450
| Gifts (G) |  | 300 | G |  | 0 |  |  | 300 | G |  | 0 |  |  | 0
| Bank Loans or Bonds (LB) |  | 12180 | LB |  | 0 |  |  | 12180 | LB |  | 0 |  |  | 0
| Reserves other than University | [13 empty] | 0
| Registration Fee (N) |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
| University Registration Fee | [13 empty] | 0
| Reserves (R) |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
| Other/Campus Funds (X) |  | 14317 | X |  | 1294 | X |  | 12471 | X |  | 552 | X |  | 0
| TOTAL |  | 26797 |  |  | 1294 |  |  | 24951 |  |  | 552 |  |  | 0
| STATE FUNDS | ( | 71577 | ) | ( | 61758 | ) | ( | 1105 | ) | ( | 8714 | ) |  | 0

## Santa Cruz
SANTA CRUZ CAMPUS
1995-96 NON-STATE CAPITAL BUDGET
($000)
[9 empty] | C U R R E N T S T A T U S | [7 empty] | PRIOR ACTION/COMMENTS
|  |  | Project | [8 empty] | Beyond |  |  |  | Approval
| Project |  | Cost |  |  | Prefunded |  |  | 1995-96 |  |  | 1995-96 |  | Action |  | Letter | Date | Action | Cost
A. | Kerr Hall Remodel, Phase 2 |  | 1433 | X |  | - - - |  | P | 57 | X |  | - - - |  |  | Chancellor | delegated
| (973021) | [6 empty] | W | 72 | X
[8 empty] | C | 1304 | X
1433
B. | Student Communications |  | - - - |  |  | - - - |  |  | - - - |  |  | - - - |  |  | Replaced by Student
| System (SCS), Phase 1 | [13 empty] | Communication System
| (976190) | [13 empty] | (see "A" in 1996-97)
C. | Natural Sciences 2 Seismic |  | 2021 | F | P | 255 | F | P | 45 | LB |  | - - - |  |  | Chancellor | delegated | 4/94 | 1993-96 CIP | 1779
| Repair (977491) |  | 1097 | LB | P | 30 | X | W | 198 | LB | [6 empty] | 6/95 | 1994-97 CIP | 4731
|  |  | 1657 | X | W | 142 | F | W | 6 | X
|  |  | 4775 |  | W | 58 | X | C | 854 | LB
[5 empty] | C | 1624 | F | C | 1065 | X
[5 empty] | C | 498 | X |  | 2168
2607
| Federal Funds (F) |  | 2021 | F |  | 2021 | F |  | 0 |  |  | 0 |  |  | 0
| Bank Loans or Bonds (LB) |  | 1097 | LB |  | 0 |  |  | 1097 | LB |  | 0 |  |  | 0
Reserves other than University
| Registration Fee (N) |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
| Other (i.e. Campus Funds) (X) |  | 3090 | X |  | 586 | X |  | 2504 | X |  | 0 |  |  | 0
| TOTAL |  | 6208 |  |  | 2607 |  |  | 3601 |  |  | 0 |  |  | 0
| STATE FUNDS | ( | 0 | ) | ( | 0 | ) | ( | 0 | ) | ( | 0 | ) |  | 0

## U-Wide
DIVISION OF
AGRICULTURE AND NATURAL RESOURCES
1995-96 NON-STATE CAPITAL BUDGET
($000)
[9 empty] | C U R R E N T S T A T U S | [7 empty] | PRIOR ACTION/COMMENTS
|  |  | Project | [8 empty] | Beyond |  |  |  | Approval
| Project |  | Cost |  |  | Prefunded |  |  | 1995-96 |  |  | 1995-96 |  | Action |  | Letter | Date | Action | Cost
A | Alternative Pest Control | ( | 19148 | ) | (S | 100 | ) | C | 2834 | F | (C | 18343 | ) | 11/98 | Regents' |  | 5/93 | 1993-96 CIP | 35000
| Quarantine and Containment |  | 16552 | F | S | 300 | X |  |  |  | (E | 540 | ) |  | Budget |  | 11/93 | 1994-97 CIP | 35954
| Facilities for California (L939118) |  | 695 | G | (P | 165 | ) |  |  |  | E | 695 | G |  |  |  | 11/94 | 1995-98 CIP | 37572
|  |  | 7376 | X | P | 1295 | F |  |  |  | C | 7076 | X |  |  |  | 11/95 | 1996-99 CIP | 37588
|  |  | 43771 |  | C | 4586 | F |  |  |  | C | 7837 | F |  |  |  | 11/96 | 1997-00 CIP | 38194
[6 empty] | 6446 | [5 empty] | 34491 |  |  |  |  | 11/97 | 1998-01 CIP | 38746
12892
| Federal Funds (F) |  | 16552 | F |  | 5881 | F |  | 2834 | F |  | 7837 | F |  | 0
| Gifts (G) |  | 695 | G |  | 0 |  |  | 0 |  |  | 695 | G |  | 0
| Other (X) |  | 7376 | X |  | 300 | X |  | 0 |  |  | 7076 |  |  | 0
| TOTAL |  | 24623 |  |  | 6181 |  |  | 2834 |  |  | 15608 |  |  | 0
| STATE FUNDS | ( | 19148 | ) | ( | 265 | ) | ( | 0 | ) | ( | 18883 | ) |  | 0