## Summary
1997-98 NON-STATE FUNDED PROJECTS
($ in thousands)
| UCB | UCD | UCI | UCLA | UCR | UCSD | UCSF | UCSB | UCSC | OTHER | TOTAL | Percent of Total
Bank Loans or Bonds (LB) | 45400 | 0 | 37750 | 3521 | 0 | 20041 | 2400 | 42000 | 16825 | 0 | 167937 | 40.74%
Other (X) | 10041 | 12765 | 1674 | 4822 | 590 | 4829 | 32857 | 1610 | 3595 | 0 | 72783 | 17.66%
Gifts (G) | 33881 | 63 | 1125 | 1501 | 0 | 0 | 1599 | 1158 | 4350 | 0 | 43677 | 10.6%
Federal (F) | 150 | 0 | 0 | 675 | 0 | 0 | 0 | 0 | 154 | 7837 | 8816 | 2.139%
Hospital Reserves (HR) | 0 | 61531 | 368 | 4088 | 0 | 13447 | 4969 | 0 | 0 | 0 | 84403 | 20.48%
Registration Fees (R) | 0 | 0 | 0 | 257 | 0 | 0 | 0 | 0 | 1016 | 0 | 1273 | 0.3088%
Reserves other than Registration Fees (N) | 19009 | 518 | 0 | 3144 | 0 | 3021 | 0 | 3000 | 4641 | 0 | 33333 | 8.086%
TOTAL | 108481 | 74877 | 40917 | 18008 | 590 | 41338 | 41825 | 47768 | 30581 | 7837 | 412222 | 100%
INDIVIDUAL CAMPUS PERCENT OF TOTAL | 26.32% | 18.16% | 9.926% | 4.369% | 0.1431% | 10.03% | 10.15% | 11.59% | 7.419% | 1.901% | 100%
STATE FUNDS | 32831 | 10784 | 0 | 1833 | 0 | 0 | 0 | 783 | 0 | 0 | 46231

## Berkeley
BERKELEY CAMPUS
1997-98 NON-STATE CAPITAL BUDGET
($ in thousands)
[9 empty] | C U R R E N T S T A T U S | [7 empty] | PRIOR ACTION/COMMENTS
|  |  | Project | [8 empty] | Beyond |  |  |  | Approval
| Project |  | Cost |  |  | Prefunded |  |  | 1997-98 |  |  | 1997-98 |  | Action |  | Letter | Date | Action | Cost
A. | Hearst Memorial Mining Building | ( | 34442 | ) | (S | 50 | ) | P | 400 | G | E | 2301 | G | 7/97 | Regents | 7/29/97 | 11/93 | 1994-97 CIP | 54832
| Seismic and Program |  | 33158 | G | (P | 1561 | ) | W | 718 | G
| Improvements (912623) |  | 67600 |  | W | 1282 | G | (W | 1972 | )
[6 empty] | 2893 |  | (C | 30859 | )
[8 empty] | C | 28457 | G
62406
B. | University Village Redevelopment |  | 45400 | LB |  |  |  | P | 3000 | LB |  |  |  | 9/97 | Regents | 9/29/97
| Step 1 (912800) |  | 10000 | N |  |  |  | W | 3000 | LB
|  |  | 55400 |  |  |  |  | C | 39400 | LB
[8 empty] | C | 9340 | N
[8 empty] | E | 660 | N
55400
C. | Silver Lab Expansion (912341) |  | 12979 | LB | P | 550 | LB | C | 150 | F |  |  |  | ??/98 | Admin | pending | 1/93 | 1992-95 CIP | 13760
|  |  | 150 | F | W | 900 | LB | C | 337 | X | [6 empty] | 9/93 | Finance Authorization | 13870
|  |  | 561 | X | C | 11439 | LB | E | 224 | X | [6 empty] | 10/97 | 1997-00 CIP | 14020
|  |  | 13690 |  | E | 90 | LB |  | 711
12979
D. | Haas Pavilion (912740) |  | 41000 | G | P | 1952 | G | W | 1250 | N | C | 6000 | G | 11/98 | Regents | 1/21/98 | 11/96 | 1996-99 CIP | 39500
|  |  | 3600 | LB | W | 2250 | G | C | 4850 | N | C | 5400 | X |  |  |  | 12/97 | 1997-00 CIP | 48000
|  |  | 6300 | X | C | 30098 | G | C | 420 | G |  | 11400
|  |  | 500 | R | C | 3600 | LB | E | 80 | G
|  |  | 6100 | N | C | 900 | X |  | 6600
|  |  | 57500 |  | C | 500 | R
[5 empty] | E | 200 | G
39500
E. | Chavez Center Renovations |  | 2053 | N |  |  |  | P | 210 | N |  | 315 | N | 98/99 | Chancellor | delegated | N/A | 1997-00 CIP | 1738
| (912918) | [6 empty] | W | 209 | N
[8 empty] | C | 1319 | N
1738
F. | Chavez Center: Golden Bear |  | 493 | N |  |  |  | P | 15 | N |  |  |  |  | Chancellor | delegated
| Restaurant Improvements | [6 empty] | W | 90 | N
| (912954) | [6 empty] | C | 345 | N
[8 empty] | E | 43 | N
493
G. | Hildebrand Hall, B-level |  | 2100 | G |  |  |  | P | 150 | G |  |  |  |  | Chancellor | delegated
| Renovation for Laser Laboratories | [6 empty] | W | 220 | G
| (912945) | [6 empty] | C | 1670 | G
[8 empty] | E | 60 | G
2100
H. | Hildebrand Hall: D-level |  | 740 | X |  |  |  | P | 70 | X |  |  |  |  | Chancellor | delegated
| Nanocrystal Laboratory |  | 110 | G |  |  |  | W | 80 | X
| Renovation (912955) |  | 850 |  |  |  |  | C | 109 | G
[8 empty] | C | 590 | X
[8 empty] | E | 1 | G
850
I. | Hill Area Electrical Substation, |  | 2350 | X |  |  |  | P | 79 | X |  |  |  |  | Chancellor | delegated
| Duct Bank, and Cable (912953) | [6 empty] | W | 79 | X
[8 empty] | C | 2192 | X
2350
J. | Hillside Terrace Parking (912914) |  | 2268 | N | P | 55 | N | W | 42 | N |  |  |  |  | Chancellor | delegated |  | 1996-99 CIP | 1590
[5 empty] | W | 73 | N | C | 636 | N
[5 empty] | C | 1462 | N |  | 678
1590
K. | Interbuilding Campus |  | 3728 | X |  |  |  | P | 80 | X |  |  |  |  | Chancellor | delegated
| Communications System, Step 1 | [6 empty] | W | 648 | X
| (912944) | [6 empty] | C | 2972 | X
[8 empty] | E | 28 | X
3728
L. | Moffitt Library Café/Microcomputer |  | 1596 | G |  |  |  | P | 125 | G |  |  |  |  | Chancellor | delegated
| Rooms (912958) | [6 empty] | W | 141 | G
[8 empty] | C | 1330 | G
1596
M. | University House Renovation, |  | 2218 | X |  |  |  | P | 200 | X | P | 40 | X | 5/99 | Chancellor | delegated | N/A | 1997-00 CIP | 1887
| Step 3 (912952) | [6 empty] | W | 200 | X | W | 80 | X
[8 empty] | C | 1320 | X | C | 190 | X
[8 empty] | E | 167 | X | E | 21 | X
[9 empty] | 1887 |  |  | 331
N. | Seismic Safety Corrections: |  | 9600 | LB |  |  |  | P | 775 | X | (W | 1224 | ) | 3/99 | Regents | 10375 | 11/97 | 1997-00 CIP | 17400
| Wurster Hall (912960) |  | 775 | G | [6 empty] | (C | 15401 | )
|  | ( | 16625 | ) | [6 empty] | W | 376 | LB
|  |  | 775 | X | [6 empty] | C | 9224 | LB
|  |  | 27775 | [7 empty] | C | 775 | G
27000
Federal funds(F) |  |  | 150 | F |  | 0 |  |  | 150 | F |  | 0 |  |  | 0
Gifts (G) |  |  | 78739 | G |  | 35782 | G |  | 33881 | G |  | 9076 | G |  | 0
External Financing (LB) |  |  | 71579 | LB |  | 16579 | LB |  | 45400 | LB |  | 9600 | LB |  | 0
Registration Fee (R) |  |  | 500 | R |  | 500 | R |  | 0 |  |  | 0 |  |  | 0
Reserves other than University | [14 empty] | 0
Registration Fee (N) |  |  | 20914 | N |  | 1590 | N |  | 19009 | N |  | 315 |  |  | 0
Other (campus funds) (X) |  |  | 16672 | X |  | 900 | X |  | 10041 | X |  | 5731 | X |  | 0
0
| TOTAL |  | 188554 |  |  | 55351 |  |  | 108481 |  |  | 24722 |  |  | 0
| STATE FUNDS | ( | 51067 | ) | ( | 1611 | ) | ( | 32831 | ) | ( | 16625 | )
188554
0

## Davis
DAVIS CAMPUS
1997-98 NON-STATE CAPITAL BUDGET
($000)
[9 empty] | C U R R E N T S T A T U S | [7 empty] | PRIOR ACTION/COMMENTS
|  |  | Project | [8 empty] | Beyond |  |  |  | Approval
| Project |  | Cost |  |  | Prefunded |  |  | 1997-98 |  |  | 1997-98 |  | Action |  | Letter | Date |  | Action | Cost
A. | Tower II Expansion, Phase II |  | 18140 | HR |  | - - - |  | P | 1440 | HR |  | - - - |  | 3/98 | Regents | 4/15/98
| (935660) | [6 empty] | W | 2160 | HR
[8 empty] | C | 14540 | HR
18140
B. | South Addition (935270) |  | 27000 | HR |  | - - - |  | P | 2200 | HR |  | - - - |  | 3/98 | Regents | 4/15/98
[8 empty] | W | 2700 | HR
[8 empty] | C | 22100 | HR
27000
C. | UC Davis Center for the Arts: |  | 15500 | X |  | - - - |  | P | 2305 | X | W | 2305 | X | 11/98 | Regents | pending | 5/98 |  | 1997-00 CIP | 2305
| Performance Hall (932120) |  | 15400 | LB | [6 empty] | C | 10890 | X |  |  |  |  | ( | "P" only)
|  |  | 22600 | G | [6 empty] | C | 15400 | LB
|  |  | 53500 | [7 empty] | C | 21423 | G
[11 empty] | E | 1177 | G
51195
D. | South Campus Development: |  | 16723 | LB |  | - - - |  | P | 518 | N | P | 414 | N | 11/98 | Regents | pending | 5/98 |  | 1997-00 CIP | 736
| Roadway and Parking Improvements |  | 1682 | N |  |  |  | P | 218 | X | W | 750 | N |  |  |  |  | ( | "P" only)
| (936591) |  | 1000 | X |  |  |  |  | 736 |  | W | 198 | X
|  |  | 19405 | [7 empty] | C | 584 | X
[11 empty] | C | 16723 | LB
18669
E. | Parking Lot 44 Relocation (936599) |  | 404 | X |  | - - - |  | P | 19 | X | C | 21 | X | 98/99 | Chancellor | delegated | N/A |  | 1997-00 CIP | 383
[8 empty] | W | 31 | X
[8 empty] | C | 333 | X
383
F. | Relocate Campus Data Center |  | 740 | X |  | - - - |  | P | 5 | X | C | 250 | X | 98/99 | Chancellor | delegated | N/A |  | 1997-00 CIP | 490
| (932220) | [6 empty] | W | 40 | X
[8 empty] | C | 445 | X
490
G. | Briggs Hall Molecular and Cell |  | 800 | X |  | - - - |  | P | 40 | X |  | - - - |  |  | Chancellor | delegated
| Biology Alterations (932200) | [6 empty] | W | 60 | X
[8 empty] | C | 700 | X
800
H. | UCDHS Hopsital Fire Installation |  | 338 | HR |  | - - - |  | P | 32 | HR |  | - - - |  |  | Chancellor | delegated
| Conduit Risers to N.S. & E. Wings | [6 empty] | W | 48 | HR
| (937979) | [6 empty] | C | 258 | HR
338
I. | UCDHS Administrative Support |  | 4977 | HR |  | - - - |  | P | 219 | HR |  | - - - |  |  | Chancellor | delegated
| Building Expansion Project (935570) | [6 empty] | W | 328 | HR
[8 empty] | C | 4430 | HR
4977
J. | UCDHS Central Plant Expansion, |  | 4334 | HR |  | - - - |  | P | 203 | HR |  | - - - |  |  | Chancellor | delegated
| Phase 1 (935670) | [6 empty] | W | 304 | HR
[8 empty] | C | 3827 | HR
4334
K. | UCDHS Housestaff Building Fire |  | 329 | HR |  | - - - |  | P | 28 | HR |  | - - - |  |  | Chancellor | delegated
| Alarm System (935720) | [6 empty] | W | 42 | HR
[8 empty] | C | 259 | HR
329
L. | UCDHS JACHO Fire Safety |  | 1000 | HR |  | - - - |  | P | 100 | HR |  | - - - |  |  | Chancellor | delegated
| Corrections, Phase 1 (935540) | [6 empty] | W | 150 | HR
[8 empty] | C | 750 | HR
1000
M. | UCDHS Hospital Fire Standpipe and |  | 681 | HR |  | - - - |  | P | 63 | HR | C | 154 | HR | 98/99 | Chancellor | delegated | N/A |  | 1997-00 CIP | 527
| Sprinkler Upgrade (935630) | [6 empty] | W | 95 | HR
[8 empty] | C | 369 | HR
527
N. | UCDHS Site and Drilling New Water |  | 1000 | HR |  | - - - |  | P | 42 | HR |  | - - - |  |  | Chancellor | delegated
| Well Project (935600) | [6 empty] | W | 63 | HR
[8 empty] | C | 895 | HR
1000
O. | UCDHS Dietary Remodel/Expansion |  | 760 | HR |  | - - - |  | P | 50 | HR |  | - - - |  |  | Chancellor | delegated
| (935450) | [6 empty] | W | 50 | HR
[8 empty] | C | 404 | HR
[8 empty] | E | 256 | HR
760
P. | UCDHS First Floor Corridor Upgrade |  | 2010 | HR |  | - - - |  | P | 205 | HR |  | - - - |  |  | Chancellor | delegated
| (937570) | [6 empty] | W | 307 | HR
[8 empty] | C | 1498 | HR
2010
Q. | Oakville Experimental Vineyard |  | 735 | X | P | 57 | X | P | 48 | G |  | - - - |  |  | Chancellor | delegated | 12/83 |  | 1983-84 CIP | NA
| Reseach Facility (931840) |  | 679 | G | W | 71 | X | [9 empty] | 12/94 |  | 1994-95 CIP | 1366
|  |  | 1414 |  | C | 607 | X
[5 empty] | C | 631 | G
1366
R. | Surge III Room 1309 Classroom |  | 200 | X | P | 26 | G | C | 15 | G |  | - - - |  |  | Chancellor | delegated | 12/83 |  | 1983-84 CIP | NA
| Renovations for Vet Med (935520) |  | 280 | G | W | 65 | G | [9 empty] | 12/94 |  | 1994-95 CIP | 1366
|  |  | 480 |  | C | 174 | G
[5 empty] | C | 200 | X
465
S. | UCDHS Pathology Support Building |  | 4200 | HR | P | 167 | HR | C | 350 | HR | C | 350 | HR | 98/99 | Chancellor | delegated | 3/97 |  | 1996-97 CIP | 465
| (935510) |  |  |  | W | 250 | HR | [9 empty] | N/A |  | 1997-98 CIP | 3850
[5 empty] | C | 3083 | HR
3500
T. | UCDHS Primary Care Center |  | 750 | HR | P | 90 | HR | C | 80 | HR |  | - - - |  |  | Chancellor | delegated | 5/97 |  | 1996-97 CIP | 3500
| Pharmacy/Pathology Renovation |  |  |  | W | 40 | HR
| (935420) |  |  |  | C | 540 | HR
670
U. | UCDHS South 3 LDRP (935400) |  | 1022 | HR | P | 80 | HR | C | 142 | HR |  | - - - |  |  | Chancellor | delegated | 5/97 |  | 1996-97 CIP | 670
[5 empty] | W | 120 | HR
[5 empty] | C | 680 | HR
880
V. | Walker Hall Seismic Replacement |  | 7603 | X | P | 510 | X | P | 352 | X |  | - - - |  | 11/97 | Regents' | N/A | 11/96 |  | 1997-00 CIP | 18997
| Facility (938723) | ( | 10784 | ) |  |  |  | (W | 522 | ) |  |  |  |  | Budget
|  |  | 18387 |  |  |  |  | W | 361 | X
[8 empty] | (C | 10262 | )
[8 empty] | C | 6380 | X
17877
W. | Plant and Environmental Sciences |  | 21248 | X |  |  |  | P | 1476 | X | (W | 1850 | ) | 11/97 | 98/99 Regents Budget
| Replacement Facility (932090) | ( | 21028 | ) | [6 empty] | W | 374 | X
|  |  | 42276 | [7 empty] | (C | 19178 | )
[11 empty] | C | 19178 | X
[11 empty] | E | 220 | X
40800
EE. | UCDHS Hazardous Rooms Upgrade |  | 763 | HR |  |  |  |  | 100 | HR | C | 219 | HR | 98/99 | Chancellor | delegated | N/A |  | 1997-98 CIP | 544
| (935560) | [7 empty] | 15 | HR
[9 empty] | 429 | HR
544
| Federal Funds (F) |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
| Gifts (G) |  | 23559 |  |  | 896 |  |  | 63 |  |  | 22600 |  |  | 0
| Hospital Reserve Funds (HR) |  | 67304 |  |  | 5050 |  |  | 61531 |  |  | 723 |  |  | 0
| Bank Loans or Bonds (LB) |  | 32123 |  |  | 0 |  |  | 0 |  |  | 32123 |  |  | 0
| Reserves other than Unversity | [13 empty] | 0
| Registration Fee (N) |  | 1682 |  |  | 0 |  |  | 518 |  |  | 1164 |  |  | 0
| University Registration Fee (R) |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
| Other (i.e. campus funds) (X) |  | 48230 |  |  | 1445 |  |  | 12765 |  |  | 34020 |  |  | 0
| TOTAL |  | 172898 |  |  | 7391 |  |  | 74877 |  |  | 90630 |  |  | 0
| STATE FUNDS | ( | 31812 | ) | ( | 0 | ) | ( | 10784 | ) | ( | 21028 | ) |  | 0

## Irvine
IRVINE CAMPUS
1997-98 NON-STATE CAPITAL BUDGET
($000)
[9 empty] | C U R R E N T S T A T U S | [7 empty] | PRIOR ACTION/COMMENTS
|  |  | Project | [8 empty] | Beyond |  |  |  | Approval
| Project |  | Cost |  |  | Prefunded |  |  | 1997-98 |  |  | 1997-98 |  | Action |  | Letter | Date | Action | Cost
A. | Undergraduate Housing |  | 37750 | LB |  | - - - |  | P | 2315 | LB |  | - - - |  | 6/98 | Regents | pending
| Expansion (996315) | [6 empty] | W | 892 | LB
[8 empty] | C | 33543 | LB
[8 empty] | E | 1000 | LB
37750
B. | High Field NMR Research |  | 1125 | G |  | - - - |  | P | 32 | G |  | - - - |  |  | Chancellor | delegated
| Facility (990240) |  | 275 | X |  |  |  | W | 30 | G
|  |  | 1400 |  |  |  |  | C | 276 | G
[8 empty] | C | 275 | X
[8 empty] | E | 787 | G
1400
C. | Central Plant Chiller |  | 844 | X |  | - - - |  | P | 30 | X |  | - - - |  |  | Chancellor | delegated
| Replacement (991945) | [6 empty] | W | 37 | X
[8 empty] | C | 777 | X
844
D. | Operating Room Chiller |  | 368 | HR |  | - - - |  | P | 13 | HR |  | - - - |  |  | Chancellor | delegated
| Replacement (994009) | [6 empty] | W | 16 | HR
[8 empty] | C | 339 | HR
368
E. | National Fuel Cell Research |  | 368 | X |  | - - - |  | P | 13 | X |  | - - - |  |  | Chancellor | delegated
| Center (NFCRC) (990079) | [6 empty] | W | 16 | X
[8 empty] | C | 339 | X
368
F. | UCIMC Academic Laboratory | ( | 19748 | ) | P | 1263 | X |  | - - - |  | (E | 548 | ) | 11/97 | Regents' | N/A | 11/96 | 1997-00 CIP | 23065
| Seismic Replacement Facility |  | 3317 | X | (W | 300 | ) |  |  |  | E | 2054 | X |  | Budget
| (994400) |  | 23065 |  | (C | 18900 | ) |  |  |  |  | 2602
20463
G. | Seismic Improvements - Med | ( | 2528 | ) |  | - - - |  | P | 187 | X | (W | 141 | ) | 11/97 | Regents' | N/A
| Surge I & II (994097) |  | 187 | X | [6 empty] | (C | 2387 | ) |  | Budget
|  |  | 2715 | [8 empty] | 2528
| Gifts (G) |  | 1125 | G |  | 0 |  |  | 1125 | G |  | 0 |  |  | 0
| Hospital Reserves (HR) |  | 368 | HR |  | 0 |  |  | 368 | HR |  | 0 |  |  | 0
| Bank Loans or Bonds (LB) |  | 37750 | LB |  | 0 |  |  | 37750 | LB |  | 0 |  |  | 0
| Reserves other than University | [10 empty] | 0 |  |  | 0
| Registration Fee (N) |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
| Other (i.e. campus funds) (X) |  | 4991 |  |  | 1263 |  |  | 1674 |  |  | 2054 |  |  | 0
0
|  |  | 44234 |  |  | 1263 |  |  | 40917 |  |  | 2054 |  |  | 0
0
| STATE FUNDS | ( | 22276 | ) | ( | 19200 | ) | ( | 0 | ) | ( | 3076 | ) |  | 0

## Los Angeles
LOS ANGELES CAMPUS
1997-98 NON-STATE CAPITAL BUDGET
($000)
[9 empty] | C U R R E N T S T A T U S | [7 empty] | PRIOR ACTION/COMMENTS
|  |  | Project | [8 empty] | Beyond |  |  |  | Approval
| Project |  | Cost |  |  | Prefunded |  |  | 1997-98 |  |  | 1997-98 |  | Action |  | Letter | Date | Action | Cost
A. | Tom Bradley International Center for |  | 8054 | LB | P | 494 | G | P | 69 | LB |  | - - - |  | 6/98 | Admin | 6/23/98 | 5/88 | 1987-90 CIP | 7052
| Students and Scholars (942300) |  | 2184 | N | P | 13 | LB | W | 104 | X | [6 empty] | 5/94 | 1993-96 CIP | 10200
|  |  | 2492 | G | W | 589 | G | C | 286 | X | [6 empty] | 11/94 | 1994-97 CIP | 10520
|  |  | 1550 | X | C | 773 | G | C | 356 | G | [6 empty] | 11/97 | 1997-98 CIP | 13994
|  |  | 14280 |  | C | 1160 | X | C | 2184 | N
[5 empty] | C | 4520 | LB | C | 3452 | LB
[5 empty] | E | 280 | G |  | 6451
7829
B. | Hedrick Hall Food Service |  | 5061 | LB | P | 131 | N | C | 754 | N |  | - - - |  | 6/98 | Admin | 6/23/98 | 3/97 | 1996-97 CIP | 5695
| Alterations Project (946400) |  | 1388 | N | W | 313 | N
|  |  | 6449 |  | C | 190 | N
[5 empty] | C | 3648 | LB
[5 empty] | E | 1413 | LB
5695
C. | Parking Structure 3 Expansion |  | 13880 | LB | P | 970 | LB | C | 515 | F |  | - - - |  | 6/98 | Admin | 6/23/98 | 1/89 | 1988-89 CIP | 14688
| (946710) |  | 515 | F | W | 262 | LB | [9 empty] | 9/94 | 1994-95 CIP | 13880
|  |  | 14395 |  | C | 12648 | LB
13880
D. | Bradley Audio-Visual Equipment |  | 282 | N |  | - - - |  | W | 10 | N | C | 76 | N | 98/99 | Chancellor | delegated | N/A | 1997-98 CIP | 520
| (942306) |  | 314 | G |  |  |  | C | 196 | N
|  |  | 596 |  |  |  |  | C | 314 | G
520
E. | Drake Stadium Track Replacement |  | 980 | G |  | - - - |  | P | 20 | G | C | 149 | G | 98/99 | Chancellor | delegated | N/A | 1997-98 CIP | 831
[8 empty] | W | 80 | G
[8 empty] | C | 731 | G
831
F. | Pubic Policy Building 3rd & 5th |  | 335 | X |  | - - - |  | P | 10 | X |  | - - - |  |  | Chancellor | delegated
| Floor Renovation (943484) | [6 empty] | W | 15 | X
[8 empty] | C | 310 | X
335
G. | SM - UCLA MC 6th Floor Nursing |  | 1395 | HR |  | - - - |  | P | 46 | HR |  | - - - |  |  | Chancellor | delegated
| Facility Renovation (948858) | [6 empty] | W | 62 | HR
[8 empty] | C | 1287 | HR
1395
H. | SM - UCLA Outpatient Radiology |  | 2541 | HR |  | - - - |  | P | 150 | HR |  | - - - |  |  | Chancellor | delegated
| Renovation (948855) | [6 empty] | W | 150 | HR
[8 empty] | C | 1881 | HR
[8 empty] | E | 360 | HR
2541
I. | SOD A0 - A3 Corridors Renovation |  | 1883 | X |  | - - - |  | P | 80 | X |  | - - - |  |  | Chancellor | delegated
| (945770) | [6 empty] | W | 129 | X
[8 empty] | C | 1535 | X
[8 empty] | E | 139 | X
1883
J. | SOM A2/A3 Cancer Center |  | 330 | X |  | - - - |  | P | 20 | X | C | 50 | X | 98/99 | Chancellor | delegated | 5/98 | 1997-98 CIP | 250
| Renovations (948871) | [6 empty] | W | 20 | X | E | 30 | X
[8 empty] | C | 200 | X |  | 80
[8 empty] | E | 10 | X
250
K. | SOM 32 - 031 Biomed Library |  | 348 | X |  | - - - |  | P | 50 | X | C | 44 | X | 98/99 | Chancellor | delegated | 5/98 | 1997-98 CIP | 275
| Renovation (944300) | [6 empty] | W | 50 | X | E | 29 | X
[8 empty] | C | 100 | X |  | 73
[8 empty] | E | 75 | X
275
L. | SOM 53 - 226, 268, 278 Physiology |  | 330 | X |  | - - - |  | P | 20 | X | C | 80 | X | 98/99 | Chancellor | delegated | 3/98 | 1997-98 CIP | 250
| Wet Lab Renovation | [6 empty] | W | 20 | X
[8 empty] | C | 210 | X
250
M. | SOM 73 - 124/142 and 73 - 152A |  | 480 | X |  | - - - |  | P | 20 | X | C | 70 | X | 98/99 | Chancellor | delegated | 4/98 | 1997-98 CIP | 410
| Neurobiology Lab Renovations | [6 empty] | W | 29 | X
[8 empty] | C | 340 | X
[8 empty] | E | 21 | X
410
N. | SOM 73 - 210A - 245 Neurobiology |  | 427 | X |  | - - - |  | P | 25 | X | C | 30 | X | 98/99 | Chancellor | delegated | 3/98 | 1997-98 CIP | 397
| Renovations (945780) | [6 empty] | W | 50 | X
[8 empty] | C | 238 | X
[8 empty] | E | 84 | X
397
O. | Parking Structure #5 |  | 160 | F |  | - - - |  | W | 20 | F |  |  |  |  | Chancellor | delegated
| Seismic - Repair (948728) | ( | 18 | ) |  |  |  | W | 28 | X
|  |  | 105 | X |  |  |  | C | 140 | F
|  |  | 283 |  |  |  |  | (C | 18 | )
[8 empty] | C | 77 | X
283
P. | Arthur Ashe Student Health & |  | 1505 | G | P | 72 | G | C | 257 | R |  |  |  |  | Chancellor | delegated
| Wellness Center |  | 257 | R | W | 127 | G | C | 147 | X
|  |  | 147 | X | C | 1306 | G |  | 404
|  |  | 424 | N | C | 424 | N
|  |  | 2333 |  |  | 1929
Q. | SM - UCLA Medical Center |  | 443 | HR | W | 57 | HR | C | 152 | HR |  |  |  |  | Chancellor | delegated
| Radiographic Fluoroscopic Room |  |  |  | C | 234 | HR
| (947871) |  |  |  |  | 291
R. | Warren Hall 24 - 124/24 - 186 |  | 745 | X | W | 50 | X | C | 75 | X |  |  |  |  | Chancellor | delegated
| (942130) |  |  |  | C | 400 | X
[5 empty] | E | 220 | X
670
S. | Chancellor's Residence Renovation |  | 230 | X | P | 16 | G | C | 230 | X |  |  |  |  | Chancellor | delegated
| (942230) |  | 850 | G | W | 40 | G
|  |  | 1080 |  | C | 794 | G
850
T. | Campus Fire Alarm System | ( | 1815 | ) | P | 75 | X | (W | 77 | ) |  |  |  | 11/96 | Regents'
| Upgrade Phase 2 (946224) |  | 75 | X |  |  |  | (C | 1738 | ) |  |  |  |  | Budget
|  |  | 1890 | [5 empty] | 1815
U. | Campus High-rise Fire Safety | ( | 4377 | ) |  | 0 |  | P | 75 | X | (W | 261 | ) | 11/97 | Regents'
| (946263) |  | 75 | X | [6 empty] | (C | 4116 | ) |  | Budget
|  |  | 4452 | [8 empty] | 4377
| Gifts (G) |  | 6141 |  |  | 4491 |  |  | 1501 |  |  | 149 |  |  | 0
| Federal Funds (F) |  | 675 |  |  | 0 |  |  | 675 |  |  | 0 |  |  | 0
| Hospital Reserves (HR) |  | 4379 |  |  | 291 |  |  | 4088 |  |  | 0 |  |  | 0
| Bank Loans or Bonds (LB) |  | 26995 |  |  | 23474 |  |  | 3521 |  |  | 0 |  |  | 0
| Registration Fees (R) |  | 257 |  |  | 0 |  |  | 257 |  |  | 0 |  |  | 0
| Reserves other than Unversity | [13 empty] | 0
| Registration Fee (N) |  | 4278 |  |  | 1058 |  |  | 3144 |  |  | 76 |  |  | 0
| Other (i.e. campus funds) (X) |  | 7060 |  |  | 1905 |  |  | 4822 |  |  | 333 |  |  | 0
| TOTAL |  | 49785 |  |  | 31219 |  |  | 18008 |  |  | 558 |  |  | 0
0
| STATE FUNDS | ( | 6210 | ) | ( | 0 | ) | ( | 1833 | ) | ( | 4377 | ) |  | 0

## Riverside
RIVERSIDE CAMPUS
1997-98 NON-STATE CAPITAL BUDGET
($000)
[9 empty] | C U R R E N T S T A T U S | [7 empty] | PRIOR ACTION/COMMENTS
|  |  | Project | [8 empty] | Beyond |  |  |  | Approval
| Project |  | Cost |  |  | Prefunded |  |  | 1997-98 |  |  | 1997-98 |  | Action |  | Letter | Date | Action | Cost
A. | Housing Office Remodel (956274) |  | 590 | X |  | - - - |  | P | 20 | X |  | - - - |  |  | Chancellor | delegated
[8 empty] | W | 42 | X
[8 empty] | C | 528 | X
590
| Banks Loans or Bonds (LB) |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
| Federal Funds (F) |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
| Other (i.e. Campus Funds) (X) |  | 590 | X |  | 0 |  |  | 590 | X |  | 0 |  |  | 0
| Gifts (G) |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
| TOTAL |  | 590 |  |  | 0 |  |  | 590 |  |  | 0 |  |  | 0
| STATE FUNDS | ( | 0 | ) | ( | 0 | ) | ( | 0 | ) | ( | 0 | ) |  | 0

## San Diego
SAN DIEGO CAMPUS
1997-98 NON-STATE CAPITAL BUDGET
($000)
[9 empty] | C U R R E N T S T A T U S | [7 empty] | PRIOR ACTION/COMMENTS
|  |  | Project | [8 empty] | Beyond |  |  |  | Approval
| Project |  | Cost |  |  | Prefunded |  |  | 1997-98 |  |  | 1997-98 |  | Action |  | Letter | Date | Action | Cost
A. | Campus Services Complex, Phase 2 |  | 5062 | LB |  | 0 |  | P | 208 | LB |  | 0 |  | 12/97 | Admin | 12/02/97
| (966593) |  | 593 | N |  |  |  | P | 26 | N
|  |  | 5655 |  |  |  |  | W | 257 | LB
[8 empty] | W | 32 | N
[8 empty] | C | 4597 | LB
[8 empty] | C | 535 | N
5655
B. | Gilman Drive Parking Structure |  | 14979 | LB |  | 0 |  | P | 589 | LB |  | 0 |  | 11/97 | Regents | 12/23/97
| (966591) | [6 empty] | W | 736 | LB
[8 empty] | C | 13654 | LB
14979
C. | Argo/Blake Residence Halls |  | 1321 | N |  | 0 |  | P | 59 | N |  | 0 |  |  | Chancellor | delegated
| Upgrades (966340) | [6 empty] | W | 72 | N
[8 empty] | C | 1190 | N
1321
D. | Campus Central Utilities Plant |  | 453 | X |  | 0 |  | P | 20 | X |  | 0 |  |  | Chancellor | delegated
| Underground Storage Tanks | [6 empty] | W | 35 | X
| Replacement (966139) | [6 empty] | C | 398 | X
453
E. | Campus Services Complex, Phase 2 |  | 921 | N |  | 0 |  | P | 35 | N |  | 0 |  |  | Chancellor | delegated
| Building D Addition (962590) | [6 empty] | W | 44 | N
[8 empty] | C | 842 | N
921
F. | High Bay Physics Addition (962540) |  | 2100 | X |  | 0 |  | P | 84 | X |  | 0 |  |  | Chancellor | delegated
[8 empty] | W | 105 | X
[8 empty] | C | 1911 | X
2100
G. | Muir College Apartments Renovations |  | 386 | X |  | 0 |  | P | 17 | X |  | 0 |  |  | Chancellor | delegated
| (966530) | [6 empty] | W | 21 | X
[8 empty] | C | 348 | X
386
H. | Reclaimed Water Extension |  | 748 | X |  | 0 |  | P | 20 | X |  | 0 |  |  | Chancellor | delegated
| (966140) | [6 empty] | W | 42 | X
[8 empty] | C | 686 | X
748
I. | San Deigo Supercomputer Chiller |  | 358 | X |  | 0 |  | P | 16 | X |  | 0 |  |  | Chancellor | delegated
| Upgrade (966138) | [6 empty] | W | 20 | X
[8 empty] | C | 322 | X
358
J. | SIO Nierenberg Hall/Scripps Ladder |  | 333 | X |  | 0 |  | P | 13 | X |  | 0 |  |  | Chancellor | delegated
| Improvements (962820) | [6 empty] | W | 17 | X
[8 empty] | C | 303 | X
333
K | UCSDMC Hillcrest: 12KV - 4.14KV |  | 432 | HR |  | 0 |  | P | 10 | HR | C | 30 | HR | 98/99 | Chancellor | delegated | 12/97 | 1997-98 CIP | 402
| Substation Replacement (966249) | [6 empty] | W | 50 | HR
[8 empty] | C | 342 | HR
402
L. | UCSDMC Hillcrest: 2nd Floor Lab |  | 321 | HR |  | 0 |  | P | 34 | HR | C | 27 | HR | 98/99 | Chancellor | delegated | 2/98 | 1997-98 CIP | 294
| Consolidation (965460) | [6 empty] | W | 20 | HR
[8 empty] | C | 240 | HR
294
M. | UCSDMC Hillcrest: 2nd Floor |  | 1806 | HR |  | 0 |  | P | 133 | HR | P | 30 | HR | 98/99 | Chancellor | delegated | 2/98 | 1997-98 CIP | 1254
| Operating Room Upgrade (965480) | [6 empty] | W | 92 | HR | W | 36 | HR
[8 empty] | C | 1029 | HR | C | 486 | HR
[9 empty] | 1254 |  |  | 552
N. | UCSDMC Hillcrest: 8th Floor |  | 1651 | HR |  | 0 |  | P | 52 | HR | P | 135 | HR | 98/99 | Chancellor | delegated | 3/98 | 1997-98 CIP | 735
| Pediatrics Renovations (965500) | [6 empty] | W | 81 | HR | W | 165 | HR
[8 empty] | C | 602 | HR | C | 616 | HR
[9 empty] | 735 |  |  | 916
O. | UCSDMC Hillcrest: Chilled Water |  | 2396 | HR |  | 0 |  | P | 258 | HR |  | 0 |  |  | Chancellor | delegated
| System Upgrade (966185) | [6 empty] | W | 136 | HR
[8 empty] | C | 2002 | HR
2396
P. | UCSDMC Hillcrest South Wing ICU |  | 4553 | HR |  | 0 |  | P | 481 | HR |  | 0 |  |  | Chancellor | delegated
| Enhancement (965430) | [6 empty] | W | 344 | HR
[8 empty] | C | 3728 | HR
4553
Q. | UCSDMC Hillcrest: Telecomm Riser |  | 1364 | HR |  | 0 |  | P | 25 | HR |  | 0 |  |  | Chancellor | delegated
| and TV Distribution (966184) | [6 empty] | W | 75 | HR
[8 empty] | C | 1264 | HR
1364
R. | UCSDMC Labor and Delivery |  | 502 | HR |  | 0 |  | P | 20 | HR |  | 0 |  |  | Chancellor | delegated
| Remodel (965440) | [6 empty] | W | 25 | HR
[8 empty] | C | 457 | HR
502
S. | UCSDMC Pulmonary Rehabilitation |  | 550 | HR |  | 0 |  | P | 22 | HR |  | 0 |  |  | Chancellor | delegated
| Clinic Renovations (965430) | [6 empty] | W | 28 | HR
[8 empty] | C | 500 | HR
550
T. | UCSDMC Thornton Hospital: 2nd |  | 376 | HR |  | 0 |  | P | 55 | HR |  | 0 |  |  | Chancellor | delegated
| Floor Pain Clinic (965470) | [6 empty] | W | 37 | HR
[8 empty] | C | 284 | HR
376
U. | UCSDMC Thornton: 2nd Floor |  | 530 | HR |  | 0 |  | P | 18 | HR |  | 0 |  |  | Chancellor | delegated
| Patient Room Remodel (965400) | [6 empty] | W | 43 | HR
[8 empty] | C | 469 | HR
530
V. | UCSDMC Thornton Hospital: |  | 491 | HR |  | 0 |  | P | 67 | HR |  | 0 |  |  | Chancellor | delegated
| Repiratory Therapy Remodel (965450) | [6 empty] | W | 44 | HR
[8 empty] | C | 380 | HR
491
W. | York Hall Undergraduate Chemistry |  | 293 | X |  | 0 |  | P | 12 | X |  | 0 |  |  | Chancellor | delegated
| Laboratory Renovations (962690) | [6 empty] | W | 15 | X
[8 empty] | C | 266 | X
293
X. | Coast Apartments Renovations |  | 4213 | N | P | 163 | N | C | 30 | N |  | 0 |  |  | Chancellor | delegated
| (966300) |  |  |  | W | 204 | N
[5 empty] | C | 3716 | N
[5 empty] | E | 100 | N
4183
Y. | Dance Studio Facility (961820) |  | 3054 | X | P | 125 | X | C | 5 | X |  | 0 |  |  | Chancellor | delegated
[5 empty] | W | 150 | X
[5 empty] | C | 2774 | X
3049
Z. | Engineering Building Unit-1, 7th Floor |  | 1154 | X | P | 21 | X | P | 17 | X |  | 0 |  |  | Chancellor | delegated
| Addition (962470) |  |  |  | W | 50 | X | C | 37 | X
[5 empty] | C | 1029 | X |  | 54
1100
AA. | Muir Cafeteria Renovation (966310) |  | 1270 | N | P | 37 | N | C | 96 | N |  | 0 |  |  | Chancellor | delegated
[5 empty] | W | 46 | N
[5 empty] | C | 939 | N
[5 empty] | E | 152 | N
1174
BB. | Ritter Hall Replacement - Basement |  | 1041 | X | W | 123 | X | C | 99 | X |  | 0 |  |  | Chancellor | delegated
| Addition (962700) |  |  |  | C | 819 | X
942
CC. | UCSDMC Arbor Parking Structure |  | 669 | N | P | 34 | N | C | 60 | N |  | 0 |  |  | Chancellor | delegated
| Finish (966585) |  |  |  | W | 50 | N
[5 empty] | C | 525 | N
609
| Federal Funds (F) |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
| Gifts (G) |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
| Hospital Reserves (HR) |  | 14972 |  |  | 0 |  |  | 13447 |  |  | 1525 |  |  | 0
| Bank Loans or Bonds (LB) |  | 20041 |  |  | 0 |  |  | 20041 |  |  | 0 |  |  | 0
Reserves other than University
| Registration Fee (N) |  | 8987 |  |  | 5966 |  |  | 3021 |  |  | 0 |  |  | 0
| Other (i.e. campus funds) (X) |  | 9920 |  |  | 5091 |  |  | 4829 |  |  | 0 |  |  | 0
| TOTAL |  | 53920 |  |  | 11057 |  |  | 41338 |  |  | 1525 |  |  | 0
| STATE FUNDS | ( | 0 | ) | ( | 0 | ) | ( | 0 | ) | ( | 0 | ) |  | 0

## San Francisco
SAN FRANCISCO CAMPUS
1997-98 NON-STATE CAPITAL BUDGET
($000)
[9 empty] | C U R R E N T S T A T U S | [7 empty] | PRIOR ACTION/COMMENTS
|  |  | Project | [8 empty] | Beyond |  |  |  | Approval
| Project |  | Cost |  |  | Prefunded |  |  | 1997-98 |  |  | 1997-98 |  | Action |  | Letter | Date | Action | Cost
A. | HSW-13 Anatomy Lab |  | 6229 | X |  | - - - |  | P | 321 | X |  | - - - |  | 12/97 | Admin | 12/02/97
| Renovation (921780) | [6 empty] | W | 465 | X
[8 empty] | C | 5443 | X
6229
B. | Mission Bay Off-Site Building 1A |  | 2400 | LB |  | - - - |  | P | 2400 | LB |  | - - - |  | 1/98 | Regents | 4/15/98
| (922100) | [13 empty] | CIP amended for "P"
C. | HSW-11, Center for Diabetes/ |  | 6050 | X |  | - - - |  | P | 339 | X |  | - - - |  | 6/98 | Admin | 6/29/98
| Metabolic Research Unit | [6 empty] | W | 475 | X
| Renovation (921580) | [6 empty] | C | 5236 | X
6050
D. | MC L-G Radiation Oncology CT |  | 430 | HR |  | - - - |  | P | 30 | HR |  | - - - |  |  | Chancellor | delegated
| Scanner Installation (921210) | [6 empty] | W | 36 | HR
[8 empty] | C | 364 | HR
430
E. | MC L; M-1 PREPARE |  | 525 | HR |  | - - - |  | P | 24 | HR |  | - - - |  |  | Chancellor | delegated
| Renovation (921550) | [6 empty] | W | 39 | HR
[8 empty] | C | 462 | HR
525
F. | MC MCB-3 Federated |  | 344 | HR |  | - - - |  | P | 14 | HR |  | - - - |  |  | Chancellor | delegated
| Accounting Relocation (921740) | [6 empty] | W | 23 | HR
[8 empty] | C | 307 | HR
344
G. | MC MtZ 1701 Divisadero Lobby |  | 3670 | HR |  | - - - |  | P | 141 | HR |  | - - - |  |  | Chancellor | delegated
| 2, 4 Tenant Improvements | [6 empty] | W | 200 | HR
| (921860) | [6 empty] | C | 3329 | HR
3670
H. | MU-G ENS Operating Center & |  | 713 | X |  | - - - |  | P | 40 | X |  | - - - |  |  | Chancellor | delegated
| Help Desk, Project 9 (921760) | [6 empty] | W | 120 | X
[8 empty] | C | 553 | X
713
I. | S ENS Improvements to IAIMS |  | 1324 | X |  | - - - |  | P | 40 | X |  | - - - |  |  | Chancellor | delegated
| Stds., Project 8 (921230) | [6 empty] | W | 60 | X
[8 empty] | C | 1224 | X
1324
J. | S/D D-2 Dental Clinics |  | 843 | X |  | - - - |  | P | 23 | X |  | - - - |  |  | Chancellor | delegated
| Modernization (921910) | [6 empty] | W | 40 | X
[8 empty] | C | 780 | X
843
K. | S/M HSE-13 CVRI Phase 2 Lab |  | 4230 | X |  | - - - |  | P | 215 | X |  | - - - |  |  | Chancellor | delegated
| Renovation (921900) | [6 empty] | W | 309 | X
[8 empty] | C | 3706 | X
4230
L. | S/M LPPI Butler Building Lab |  | 377 | X |  | - - - |  | P | 19 | X |  | - - - |  |  | Chancellor | delegated
| Renovation (922150) | [6 empty] | W | 27 | X
[8 empty] | C | 331 | X
377
M. | S/M M-11W Cardiology |  | 1440 | X |  | - - - |  | P | 109 | X |  | - - - |  |  | Chancellor | delegated
| Academic Offices Renovation |  | 448 | G |  |  |  | W | 179 | X
| (921620) |  | 1888 |  |  |  |  | C | 1152 | X
[8 empty] | C | 448 | G
1888
N. | S/M M-4 Vascular Surgery |  | 374 | X |  | - - - |  | P | 28 | X |  | - - - |  |  | Chancellor | delegated
| Admin. Office Remodel (921690) | [6 empty] | W | 42 | X
[8 empty] | C | 299 | X
[8 empty] | E | 5 | X
374
O. | S/M MCB-2 Neurology Surge |  | 1010 | X |  | - - - |  | P | 56 | X |  | - - - |  |  | Chancellor | delegated
| Lab Renovation (921640) | [6 empty] | W | 82 | X
[8 empty] | C | 872 | X
1010
P. | S/M S-13 Anatomy |  | 562 | X |  | - - - |  | P | 39 | X |  | - - - |  |  | Chancellor | delegated
| Administration Offices | [6 empty] | W | 73 | X
| Renovation (921800) | [6 empty] | C | 450 | X
562
Q. | S/M S-14 Anatomy Lab |  | 980 | X |  | - - - |  | P | 57 | X |  | - - - |  |  | Chancellor | delegated
| Remodel (921250) |  | 1020 | G |  |  |  | P | 59 | G
|  |  | 2000 |  |  |  |  | W | 74 | X
[8 empty] | W | 77 | G
[8 empty] | C | 849 | X
[8 empty] | C | 884 | G
2000
R. | S/M SFGH 3-3 Animal Care |  | 1290 | X |  | - - - |  | P | 83 | X |  | - - - |  |  | Chancellor | delegated
| Facility Remodel (921960) | [6 empty] | W | 127 | X
[8 empty] | C | 1080 | X
1290
S. | S/N N-7 Skills Lab Renovation |  | 398 | X |  | - - - |  | P | 48 | X |  | - - - |  |  | Chancellor | delegated
| (921960) | [6 empty] | W | 48 | X
[8 empty] | C | 302 | X
398
T. | S/P S-9 Pharmaceutical |  | 544 | X |  | - - - |  | P | 73 | X |  | - - - |  |  | Chancellor | delegated
| Chemistry Renovation (921670) |  | 131 | G |  |  |  | W | 104 | X
|  |  | 675 |  |  |  |  | C | 367 | X
[8 empty] | C | 131 | G
675
U. | VCA&F MCB-1 Reprographics |  | 593 | X |  | - - - |  | P | 40 | X |  | - - - |  |  | Chancellor | delegated
| Renovation (921680) | [6 empty] | W | 55 | X
[8 empty] | C | 498 | X
593
V. | UC Hall Seismic Replacement, |  | 70000 | LB |  |  |  | P | 5900 | X | P | 3698 | X | 3/99 | Regents | 6/10/99 | 11/97 | Regents' Budget | 87890
| Mission Bay (922030) |  | 21038 | X | [6 empty] | (W | 2094 | )
|  |  | 110000 | G | [6 empty] | W | 8784 | G
|  | ( | 21362 | ) | [6 empty] | (C | 19268 | )
|  |  | 222400 | [7 empty] | C | 2340 | X
[11 empty] | C | 101216 | G
[11 empty] | C | 70000 | LB
[11 empty] | E | 9100 | X
216500
| Gifts (G) |  | 111599 |  |  | 0 |  |  | 1599 |  |  | 110000 |  |  | 0
| Hospital Reserve Funds (HR) |  | 4969 |  |  | 0 |  |  | 4969 |  |  | 0 |  |  | 0
| Bank Loans or Bonds (LB) |  | 72400 |  |  | 0 |  |  | 2400 |  |  | 70000 |  |  | 0
Reserves other than University
| Registration Fees (N) |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
| Other (i.e. campus funds) (X) |  | 47995 |  |  | 0 |  |  | 32857 |  |  | 15138 |  |  | 0
| TOTAL |  | 236963 |  |  | 0 |  |  | 41825 |  |  | 195138 |  |  | 0
| STATE FUNDS | ( | 21362 | ) | ( | 0 | ) | ( | 0 | ) | ( | 21362 | ) |  | 0

## Santa Barbara
SANTA BARBARA CAMPUS
1997-98 NON-STATE CAPITAL BUDGET
($000)
[9 empty] | C U R R E N T S T A T U S | [7 empty] | PRIOR ACTION/COMMENTS
|  |  | Project | [8 empty] | Beyond |  |  |  | Approval
| Project |  | Cost |  |  | Prefunded |  |  | 1997-98 |  |  | 1997-98 |  | Action |  | Letter | Date | Action | Cost
A | San Rafael Student Housing Addition |  | 43951 | LB |  | 0 |  | P | 1941 | N | C | 1951 | LB | 1/98 | Regents | 7/09/98
| (986255) |  | 3000 | N |  |  |  | W | 1059 | N
|  |  | 46951 |  |  |  |  | W | 878 | LB
[8 empty] | C | 38607 | LB
[8 empty] | E | 2515 | LB
45000
B. | Art Museum Alterations (980420) |  | 1158 | G |  | 0 |  | P | 111 | G |  | - - - |  |  | Chancellor | delegated
|  |  | 1000 | X |  |  |  | W | 186 | G
|  |  | 2158 |  |  |  |  | C | 861 | G
[8 empty] | C | 1000 | X
2158
C. | Modular Classoom Project (981160) |  | 342 | X |  | 0 |  | P | 11 | X |  | - - - |  |  | Chancellor | delegated
[8 empty] | W | 30 | X
[8 empty] | C | 301 | X
342
D. | Environmental Sciences Building | ( | 23386 | ) |  | 0 |  | (P | 783 | ) | (W | 1343 | ) | 11/98 | Regents' |  | 11/97 | 1997-00 CIB | 26789
| (980850) |  | 3365 | X |  |  |  | P | 268 | X | W | 151 | X |  | Budget
|  |  | 26751 | [5 empty] | 1051 |  | (C | 19672 | )
[11 empty] | C | 2845 | X
[11 empty] | (E | 1588 | )
[11 empty] | E | 101 | X
25700
| Gifts (G) |  | 1158 |  |  | 0 |  |  | 1158 | G |  | 0 |  |  | 0
| Bank Loans or Bonds (LB) |  | 43951 |  |  | 0 |  |  | 42000 | LB |  | 1951 |  |  | 0
Reserves other than University
| Registration Fee (N) |  | 3000 |  |  | 0 |  |  | 3000 | N |  | 0 |  |  | 0
University Registration Fee
| Reserves (R) |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
| Other/Campus Funds (X) |  | 4707 |  |  | 0 |  |  | 1610 | X |  | 3097 |  |  | 0
| TOTAL |  | 52816 |  |  | 0 |  |  | 47768 |  |  | 5048 |  |  | 0
| STATE FUNDS | ( | 23386 | ) | ( | 0 | ) | ( | 783 | ) | ( | 22603 | ) |  | 0

## Santa Cruz
SANTA CRUZ CAMPUS
1997-98 NON-STATE CAPITAL BUDGET
($000)
[9 empty] | C U R R E N T S T A T U S | [7 empty] | PRIOR ACTION/COMMENTS
|  |  | Project | [8 empty] | Beyond |  |  |  | Approval
| Project |  | Cost |  |  | Prefunded |  |  | 1997-98 |  |  | 1997-98 |  | Action |  | Letter | Date |  | Action | Cost
A. | Bay Tree Bookstore (976405) |  | 6966 | LB |  | - - - |  | P | 394 | N |  | - - - |  | 9/97 | Regents | 9/29/97
|  |  | 2840 | N |  |  |  | P | 68 | R
|  |  | 1000 | R |  |  |  | W | 526 | N
|  |  | 10806 |  |  |  |  | W | 129 | R
[8 empty] | C | 1746 | N
[8 empty] | C | 6966 | LB
[8 empty] | C | 803 | R
[8 empty] | E | 700 | N
11332
B. | College Nine Apartments |  | 14171 | LB | P | 355 | N | P | 178 | N |  | - - - |  | 9/97 | Regents | 9/29/97 | 1/91 |  | 1990-93 CIP | 9467
| (976290) |  | 2416 | N | W | 328 | N | W | 831 | LB | [6 empty] | 8/91 |  | 1991-94 CIP | 9730
|  |  | 16587 |  | C | 6426 | LB | C | 6914 | LB | [6 empty] | 5/92 |  | 1991-94 CIP | 10280
[5 empty] | C | 1005 | N |  | 7923 | [7 empty] | 10/93 |  | 1993-97 CIP* | 10280
[5 empty] | E | 550 | N | [10 empty] | ( | *admin - change of fund source)
8664
C. | Colleges Nine & Ten Bus Stop |  | 268 | N |  | - - - |  | P | 60 | X |  | - - - |  |  | Chancellor | delegated
| (976582) |  | 267 | X |  |  |  | W | 50 | X
|  |  | 535 |  |  |  |  | C | 157 | X
[8 empty] | C | 268 | N
535
D. | Coolidge Drive/Campus Facilities |  | 154 | F |  | - - - |  | P | 38 | F |  | - - - |  |  | Chancellor | delegated
| Intersection Improvements |  | 95 | N |  |  |  | P | 12 | X
| (977100) |  | 202 | X |  |  |  | W | 23 | F
|  |  | 451 |  |  |  |  | W | 7 | X
[8 empty] | C | 93 | F
[8 empty] | C | 95 | N
[8 empty] | C | 183 | X
451
E. | Graduate Commons (970740) |  | 814 | LB |  | - - - |  | P | 82 | X |  | - - - |  |  | Chancellor | delegated
|  |  | 1190 | N |  |  |  | W | 89 | X
|  |  | 16 | R |  |  |  | W | 42 | N
|  |  | 187 | X |  |  |  | C | 16 | X
|  |  | 2207 |  |  |  |  | C | 985 | N
[8 empty] | C | 814 | LB
[8 empty] | C | 16 | R
[8 empty] | E | 163 | N
2207
F. | Infant & Toddler Care Modular |  | 70 | N |  | - - - |  | P | 10 | N |  | - - - |  |  | Chancellor | delegated
| Unit (976406) |  | 208 | X |  |  |  | W | 20 | N
|  |  | 278 |  |  |  |  | C | 30 | N
[8 empty] | C | 208 | X
[8 empty] | E | 10 | N
278
G. | Kresge College Residence Hall |  | 350 | X |  | - - - |  | P | 10 | X |  | - - - |  |  | Chancellor | delegated
| R-5 Renovation (976410) | [6 empty] | W | 40 | X
[8 empty] | C | 300 | X
350
H. | Long Marine Lab Infrastructure |  | 500 | X |  | - - - |  | P | 35 | X |  | - - - |  |  | Chancellor | delegated
| Improvements (970941) | [6 empty] | W | 20 | X
[8 empty] | C | 445 | X
500
I. | Oiled Seabird Facility (977015) |  | 250 | X |  | - - - |  | P | 12 | X |  | - - - |  |  | Chancellor | delegated
[8 empty] | W | 12 | X
[8 empty] | C | 226 | X
250
J. | Primary Power Conversion |  | 757 | X |  | - - - |  | P | 9 | X |  | - - - |  |  | Chancellor | delegated
| (976142) | [6 empty] | W | 50 | X
[8 empty] | C | 698 | X
757
K. | LML Discorvery Center (970940) |  | 4350 | G | P | 23 | X | P | 217 | G |  | - - - |  |  | Chancellor | delegated | 5/92 |  | 1991-94 CIP | 550
|  |  | 550 | X | W | 28 | X | W | 218 | G
|  |  | 4900 |  | C | 489 | X | C | 3915 | G
[5 empty] | E | 10 | X |  | 4350
550
L. | UC MBEST Center Building |  | 2900 | F | P | 100 | X | W | 40 | LB | P | 149 | F | 98/99 | Chancellor | delegated | 3/97 |  | 1996-99 CIP | 1111
| (970992) |  | 1300 | LB | W | 11 | X | C | 1260 | LB | W | 223 | F | [5 empty] | 1997-98 CIP | 1300
|  |  | 611 | X | W | 89 | F |  | 1300 |  | C | 1528 | F
|  |  | 4811 |  | C | 840 | F |  |  |  | C | 500 | X
[5 empty] | E | 71 | F |  |  |  |  | 2400
1111
M. | Interdisciplinary Sciences | ( | 16623 | ) |  |  |  | P | 874 | X | (W | 624 | ) | 11/97 | Regents'
| Building (970260) |  | 874 | X | [6 empty] | (C | 14240 | ) |  | Budget
|  |  | 17497 | [7 empty] | (E | 1759 | )
16623
| Federal Funds (F) |  | 3054 |  |  | 1000 |  |  | 154 |  |  | 1900 |  |  | 0
| Gift Funds (G) |  | 4350 |  |  | 0 |  |  | 4350 |  |  | 0 |  |  | 0
| Bank Loans or Bonds (LB) |  | 23251 |  |  | 6426 |  |  | 16825 |  |  | 0 |  |  | 0
University Registration
| Fee Reserves (R) |  | 1016 |  |  | 0 |  |  | 1016 |  |  | 0 |  |  | 0
Reserves other than University
| Registration Fee (N) |  | 6879 |  |  | 2238 |  |  | 4641 |  |  | 0 |  |  | 0
| Other (i.e. Campus Funds) (X) |  | 4756 |  |  | 661 |  |  | 3595 |  |  | 500 |  |  | 0
| TOTAL |  | 43306 |  |  | 10325 |  |  | 30581 |  |  | 2400 |  |  | 0
| STATE FUNDS | ( | 16623 | ) | ( | 0 | ) | ( | 0 | ) | ( | 16623 | ) |  | 0

## U-Wide
DIVISION OF
AGRICULTURE AND NATURAL RESOURCES
1997-98 NON-STATE CAPITAL BUDGET
($000)
[9 empty] | C U R R E N T S T A T U S | [7 empty] | PRIOR ACTION/COMMENTS
|  |  | Project | [8 empty] | Beyond |  |  |  | Approval
| Project |  | Cost |  |  | Prefunded |  |  | 1997-98 |  |  | 1997-98 |  | Action |  | Letter | Date | Action | Cost
A. | Alternative Pest Control | ( | 19148 | ) | (S | 100 | ) | C | 7837 | F | (C | 13442 | ) | 11/98 | Regents' |  | 5/93 | 1993-96 CIP | 35000
| Quarantine and Containment |  | 16552 | F | S | 300 | X |  |  |  | (E | 540 | ) |  | Budget |  | 11/93 | 1994-97 CIP | 35954
| Facilities for California (L939118) |  | 695 | G | (P | 165 | ) |  |  |  | E | 695 | G |  |  |  | 11/94 | 1995-98 CIP | 37572
|  |  | 7376 | X | P | 1295 | F |  |  |  | C | 7076 | X |  |  |  | 11/96 | 1997-00 CIP | 38194
|  |  | 43771 |  | C | 7420 | F |  |  |  |  | 21753 |  |  |  |  | 11/97 | 1998-01 CIP | 38746
[5 empty] | (C | 4901 | )
14181
| Federal Funds (F) |  | 16552 | F |  | 8715 | F |  | 7837 | F |  | 0 |  |  | 0
| Gifts (G) |  | 695 | G |  | 0 |  |  | 0 |  |  | 695 | G |  | 0
| Other (X) |  | 7376 | X |  | 300 | X |  | 0 |  |  | 7076 | X |  | 0
| TOTAL |  | 24623 |  |  | 9015 |  |  | 7837 |  |  | 7771 |  |  | 0
| STATE FUNDS | ( | 19148 | ) | ( | 5166 | ) | ( | 0 | ) | ( | 13982 | ) |  | 0