SECTION 01012

INFORMATION & PROCEDURES INSTRUCTIONS (RFI)

1.		DESCRIPTION

1.1		This Section contains the procedures to be followed by Contractor upon discovery of any apparent conflicts, omissions, or errors in the Contract Documents or upon having any question concerning interpretation.

2.		PROCEDURES

2.1		Notification by Contractor:

2.1.1		Submit all requests for clarification or additional information in writing to University's Representative using the Request for Information (RFI) form provided by University's Representative or a similar form approved by University's Representative.

2.1.2		Number RFIs sequentially.  Follow RFI number with sequential alphabetical suffix as necessary for each resubmission.  For example, the first RFI would be “001.”  The second RFI would be “002.”  The first resubmittal of RFI “002” would be “002a.”

2.1.3		Limit each RFI to one subject.

2.1.4		Submit a RFI if one of the following conditions occur:

.1		Contractor discovers an unforeseen condition or circumstance that is not described in the Contract Documents.

.2		Contractor discovers an apparent conflict or discrepancy between portions of the Contract Documents that appears to be inconsistent or is not reasonably inferred from the intent of the Contract Documents.

.3		Contractor discovers what appears to be an omission from the Contract Documents that cannot be reasonably inferred from the intent of the Contract Documents.

2.1.5		Contractor shall not:

.1		Submit an RFI as a request for substitution.

.2		Submit an RFI as a submittal.

.3		Submit an RFI under the pretense of a Contract Documents discrepancy or omission without thorough review of the Documents.

.4		Submit an RFI in a manner that suggests that specific portions of the Contract Documents are assumed to be excluded or by taking an isolated portion of the Contract Documents in part rather than whole.

.5		Submit an RFI in an untimely manner without proper coordination and scheduling of Work of related trades.

If Contractor submits an RFI contrary to the above, Contractor shall pay the cost of any review, which cost shall be deducted from the Contract Sum.

2.1.6		Contractor shall submit  request for information or clarification immediately upon discovery.  Contractor shall submit RFIs within a time frame so as not to delay the Contract Schedule while allowing the full response time described below.

2.2		Response Time:

2.2.1		University's Representative, whose decision will be final and conclusive, shall resolve such questions and issue instructions to Contractor within a reasonable time frame.  In most cases, RFIs will receive a response within 14 days.  If in the opinion of University’s Representative more than 14 days is required to prepare a response to an RFI, Contractor will be notified in writing.

2.2.2		Should Contractor proceed with the Work affected before receipt of a response from University's Representative, within the response time described above, any portion of the Work which is not done in accordance with University's Representative's interpretations, clarifications, instructions, or decisions is subject to removal or replacement and Contractor shall be responsible for all resultant losses.

2.2.3		Failure to Agree:  In the event of failure to agree as to the scope of the Contract requirements, Contractor shall follow procedures set forth in Article 4 of the General Conditions.

*****