SECTION 01340

SHOP DRAWINGS, PRODUCT DATA, AND SAMPLES

1.		REQUIREMENTS INCLUDED

1.1		Shop Drawings, Product Data, and Samples, other than in connection with proposed substitutions, shall be submitted to University's Representative only when specifically required; and University's Representative will not review any other such submittals. Product Data and Samples for proposed substitutions shall be submitted to University's Representative in accordance with SECTION 01630.  Contractor shall be responsible for obtaining such copies of Shop Drawings, Product Data, and Samples as it may require for its own use.

2.		RELATED REQUIREMENTS

2.1		Definitions:

2.1.1		The terms “Shop Drawings” and “Product Data” as used herein also include, but are not limited to, fabrication, erection, layout and setting drawings, manufacturers' standard drawings, descriptive literature, catalogues, brochures, performance and test data, wiring and control diagrams, all other drawings and descriptive data pertaining to materials, equipment, piping, duct and conduit systems, and methods of construction as may be required to show that the materials, equipment, or systems and the positions thereof conform to the Contract Documents.

2.1.2		As used herein, the term “manufactured” applies to standard units usually mass-produced.  The term “fabricated” means items specifically assembled or made out of selected materials to meet individual design requirements.  Shop Drawings shall establish the actual detail of all manufactured or fabricated items, indicate proper relation to adjoining Work, and amplify design details of mechanical and electrical equipment in proper relation to physical spaces in the structure.

2.2		Manufacturers' Instructions:

2.2.1		Where any item of Work is required by the Contract Documents to be furnished, installed, or performed in accordance with a specified product manufacturer's instructions, Contractor shall procure and distribute the necessary copies of such instructions to University's Representative and all other concerned parties; and Contractor shall furnish, install, or perform the Work in strict accordance therewith.

2.3		Submittal Schedule:

2.3.1		A schedule for submission of Shop Drawings, Product Data, and Samples by Contractor (the “Submittal Schedule”), and their processing and return by University's Representative, shall be agreed upon by both parties in order that the items covered by these submittals will be available when needed by the construction process and so that each party can plan its workload in an orderly manner.

2.3.2		Contractor shall prepare the Submittal Schedule in the form contained in the Exhibits and coordinate it with the Contract Schedule.  No submittals will be processed before the Submittal Schedule has been submitted  to and accepted by University's Representative, except in such cases where the processing of submittals is required before the acceptance of the Submittal Schedule.

2.3.3		In preparing the Submittal Schedule, Contractor must first determine from the Contract Schedule the date the particular item is needed for the Work.  Working backwards, Contractor will add the required number of days for shipment, time for fabrication, and similar items to determine the date of the first submittal.

2.3.4		The Submittal Schedule shall be adjusted to meet the needs of the construction process and the Contract Schedule.  Submit 2 copies of the Submittal Schedule after it is completed and each time it is updated by Contractor.

3.		SHOP DRAWINGS

3.1		Present information required on Shop Drawings in a clear and thorough manner.  Identify details by reference to drawing and detail, schedule, or room numbers shown and specified.

4.		PRODUCT DATA

4.1		Preparation:

4.1.1		Clearly mark each copy to identify pertinent products or models.

4.1.2		Show performance characteristics and capacities.

4.1.3		Show dimensions and clearances required.

4.1.4		Show wiring or piping diagrams and controls.

4.2		Manufacturers' standard schematic drawings and diagrams:

4.2.1		Modify the standard schematic drawings and other diagrams to delete information which is not applicable to the Work.

4.2.2		Supplement standard information to provide information specifically applicable to the Work.

5.		SAMPLES

5.1		Office Samples shall be of sufficient size and quality to clearly illustrate the following:

5.1.1		Functional characteristics of the products, with integrally related parts and attachment devices.

5.1.2		Full ranges of color, texture, and pattern.

5.2		Field Samples and mock-ups:

5.2.1		Erect at the Project site, at a location as directed by University's Representative.

5.2.2		Size:  As specified.

5.2.3		Fabricate each Sample and mock-up to be complete and fully finished.

5.2.4		Remove mock-ups at conclusion of the Work.

6.		CONTRACTOR'S REVIEW OF SUBMITTALS

6.1		Review, mark up as appropriate, and stamp Shop Drawings, Product Data, and Samples prior to submission.  Submittals shall clearly show that they have been reviewed by Contractor for conformance with the requirements of the Contract Documents and for coordination with other SECTIONS.

6.2		Determine and verify:

6.2.1		Field measurements.

6.2.2		Field construction criteria.

6.2.3		Catalog numbers and similar data.

6.2.4		Conformance with Contract Documents.

6.3		Coordinate each submittal with requirements of the Work and of the Contract Documents.

6.4		Notify University's Representative in writing, at time of submission, of any changes in the submittals from requirements of the Contract Documents.

6.5		Begin no fabrication or Work which requires submittals until the return of University's Representative's final reviewed submittals.

7.		SUBMISSION REQUIREMENTS

7.1		Make submittals promptly in accordance with the Submittal Schedule and in such sequence as to cause no delay in the Work or in the work of any Separate Contractor.

7.2		Number of Submittals Required:

7.2.1		Shop Drawings:  Submit 1 reproducible transparency and 2 opaque reproductions.  After checking, University's Representative will make prints for itself, University, and their consultants and then return the reproducible copy to Contractor.  Contractor may make prints as it requires for its use and for Subcontractors' use.

7.2.2		Product Data and Non-Reproducible Submittals:  Submit the number of copies which Contractor will need, plus 3 copies which will be retained by University's Representative.

7.2.3		Samples:  Submit the number specified in the SECTION which requires them.

7.3		Submittals shall contain:

7.3.1		Date of submission and dates of any previous submissions.

7.3.2		Project name and number.

7.3.3		Contract identification.

7.3.4		The names of:

.1		Contractor.

.2		Subcontractor.

.3		Supplier.

.4		Manufacturer.

7.3.5		Identification of the product, with the Specification SECTION number.

7.3.6		Field dimensions, clearly identified as such.

7.3.7		Relation to adjacent or critical features of the Work or materials.

7.3.8		Reference standards, such as ASTM or Federal Specification numbers.

7.3.9		Identification of changes from requirements of the Contract Documents.

7.3.10	Identification of revisions on resubmittals.

7.3.11	An 8-inch x 3-inch blank space for review stamps.

7.3.12	Contractor's stamp, initialed or signed, certifying to the review of the submittal; verification of materials and field measurements and conditions; and compliance of the information within the submittal with requirements of the Work and of the Contract Documents.

7.4		Resubmission Requirements

7.4.1		Shop Drawings and Product Data:

.1		Revise Shop Drawings or Product Data, and resubmit as specified for the initial submittal.

.2		Identify any changes which have been made other than those requested.

.3		Note any departures from the Contract Documents or changes in previously reviewed submittals which were not commented upon by University's Representative.

7.4.2		Samples:  Submit new samples as required for initial submittal.

7.5		Distribution

7.5.1		Reproduce and distribute copies of Shop Drawings and Product Data, which carry University's Representative's review stamp, to the following locations:

.1		Contractor's Project site file.

.2		Record documents file maintained by Contractor.

.3		Separate Contractors.

.4		Subcontractors.

.5		Supplier or manufacturer.

7.5.2		Distribute Samples which carry University's Representative's review stamp as directed.

7.6		University's Representative's Review

7.6.1		University's Representative will review Contractor's submittals, such as Shop Drawings, Product Data, and Samples, for the limited purpose of checking for conformance with information given and the design concept expressed in the Contract Documents.  Review of such submittals is not conducted for the purpose of determining the accuracy and completeness of other details such as dimensions and quantities, or for substantiating instructions for installation or performance of equipment or systems, all of which remain the responsibility of Contractor as required by the Contract Documents.

*****