## Overview and Risk Assessment
|  |  | Expected Mitigating Control Elements |  |  |  |  | Are the Mitigating Control Elements, or Equivalent Practices, Present (check Yes or No)? |  |  | Judgment as to Residual Risk of Project Failure (Check High, Medium, Low)
Item# | Topic | Risk | Control Environment | Risk Assessment | Control Activities | Monitoring | Information and Communication | Yes | No | Comment and/or ARC Reference | High | Medium | Low | Comment and/or ARC Reference
1 | Business-IT Alignment | The objectives of the IT project are not aligned with the overall mission-oriented strategy of the campus, medical center, or laboratory, and therefore entity resources are being mis-allocated by allowing them to flow to the project. | 1. Management expects that IT projects will serve, or will be essential components of programs that serve, the campus, medical center, or laboratory's mission. 2. Responsibility for IT projects includes a role assigned at an organizational level that is able to view proposed IT projects in the context of campus-, medical center-, or laboratory-level mission-oriented strategy. |  | There is a campus, medical center, or laboratory-level process within which IT projects are identified, defined, evaluated, prioritized, and selected so as to ensure strategic alignment with the entity's mission. |  | The expectation that IT projects will serve, or will be essential components of programs that serve, the campus, medical center, or laboratory's mission, is communicated to the appropriate recipients.
2 | Application Acquisition, Development, or Maintenance | Within IT projects, IT solutions that involve application acquisition, development, or maintenance, emerge in an uncontrolled way, and thus do not end up meeting the originating needs. | Management expects that in the case of application acquisition, development, or maintenance, all necessary natural sub-steps will be followed. |  | A consistent approach, compliant with IS-10, to IT solutions that involve application acquisition, development, or maintenance, is followed. |  | The expectation that application acquisition, development, or maintenance solutions will follow a naturally phased process, is communicated to the appropriate recipients.
3 | Project Execution--Defined, Consistent Approach | Extra time, and/or failure to achieve deliverables consistently, because the execution process is re-invented with each project. | 1. Management expects that IT projects will be managed in accordance with an explicitly defined approach that addresses project initiation, planning, executing, controlling, and closing. 2. IT project management is assigned at an organizational level that ensures a consistent approach for all projects. |  | An explicit project management approach that addresses project initiation, planning, executing, controlling, and closing is used campus-, medical center-, or laboratory-wide. |  | The expectation that IT projects will be managed in accordance with an explicitly defined approach, is communicated to the appropriate recipients.
4 | Project Execution--Stakeholder Commitment | Unclear responsibilities and accountabilities for ensuring cost control and project success; insufficient stakeholder participation in defining requirements and reviewing deliverables; reduced understanding and delivery of business benefits | The commitment and participation of key stakeholders, including management of the affected user department and key end users in the initiation, definition and authorization of a project, is obtained. |  | Ongoing involvement includes, but is not limited to, project approval, project phase approval, project checkpoint reporting, project representation at the campus-, medical center-, or laboratory-level of governance, project planning, product testing, user training, user procedures documentation and project communication material development. |  | During project initiation, ongoing key stakeholder commitment and roles and responsibilities for the duration of the project life cycle are outlined.
5 | Project Execution--Scope Statement | Misunderstanding of project objectives and requirements; failure of projects to meet business and user requirements; misunderstanding of the impact of this project with other related projects |  |  | It is ensured that key stakeholders and program and project sponsors within the organization and IT agree upon and accept the requirements for the project, including definition of project success (acceptance) criteria and key performance indicators. |  | 1.Stakeholders are provided with a clear, written statement defining the nature, scope and business benefit of every project to create a common understanding of project scope. 2. The project definition describes the requirements for a project communication plan that identifies internal and external project communications. 3. With the approval of stakeholders, the project definition is maintained throughout the project, reflecting changing requirements.
6 | Project Execution--Phase Initiation | Lack of alignment of projects to the organization’s vision; wrong prioritization of projects; undetected deviations from the overall project plan; poor utilization of resources | Criteria for acceptance of project phase deliverables are agreed to by key stakeholders prior to the phase work, and there is an acceptance process based on these criteria. |  | Approval and sign-off on the deliverables produced in each project phase is obtained from designated managers and customers of the affected business and IT functions. | It is assessed whether the project is on schedule, within budget and aligned with the agreed-upon scope. Identified variances are assessed and the impact on the project plan and realization of expected benefits is identified.
7 | Project Execution--Integrated Plan | Undetected errors in project planning and budgeting; lack of alignment of projects to the organization’s objectives and to other interdependent projects; undetected deviations from the project plan; project not completed on time and on budget. |  |  |  |  | 1. A project plan is developed that provides information to enable management to control project progress. The plan should include details of project deliverables, required resources and responsibilities, clear work breakdown structures and work packages, estimates of resources required, milestones, key dependencies, and identification of a critical path. Interdependencies of resources (e.g., key personnel) and deliverables with other projects are also identified. 2. The project plan and any dependent plans are maintained to ensure that they are up to date and reflect actual progress and material changes. 3. There is effective communication of project plans and progress reports amongst all projects and with campus-, medical center-, or laboratory-level objectives. Any changes made to individual plans are reflected in the other plans.
8 | Project Execution--Resources | Gaps in skills and resources jeopardizing critical project tasks; inefficient use of resources; contract disputes with outsourced resources | 1. Resource needs for the project are identified and roles and responsibilities are clearly mapped out, with escalation and decision-making authorities agreed upon and understood. 2. The roles and the responsibilities of other involved parties, including finance, legal, procurement, human resources, internal audit and compliance, are considered and clearly defined. 3. The responsibility for procurement and management of third-party products and services is clearly defined and agreed upon. |  | 1. Experienced project management and team leader resources with skills appropriate to the size, complexity and risk of the project, are utilized. 2. Third-party relationships are managed. |  | Required skills and time requirements for all individuals involved in the project phases are identified in relation to defined roles. Roles are staffed based on available skills information (e.g., IT skills matrix).
9 | Project Execution--Risk Management | Undetected project risks; lack of mitigating actions for identified risks; Undetected project showstoppers | 1. A formal project risk management framework that includes identifying, analyzing, responding to, mitigating, monitoring and controlling risks, is established. 2. Appropriately skilled personnel are assigned the responsibility for executing the organization’s project risk management framework within a project. | 1. Identifying and quantifying risks is performed continuously throughout the project. 2. Project risks are reassessed periodically, including at entry into each major project phase and as part of major change request assessments. | Risk owners oversee or themselves perform in accordance with their responses to risk communications. | The project issues log is analyzed periodically for trends and recurring problems, to ensure that root causes are corrected. | 1. Appropriate (i.e., consistent with the project governance structure) risk and issue owners are identified, for responses to avoid, accept or mitigate risks, and risks are communicated to them. 2. A project risk register of all potential project risks, and a log of all project issues and their resolution, are maintained and reviewed.
10 | Project Execution--Quality Plan | Project deliverables failing to meet business and user requirements; gaps in expected and delivered quality within the projects; inefficient and fragmented approach to quality assurance; implemented system or changes adversely impact existing systems and infrastructure | 1. To provide quality assurance for the project deliverables, ownership and responsibilities, quality review processes, success criteria and performance metrics are identified. 2. Any requirements for independent validation and verification of the quality of deliverables in the plan are defined.
11 | Project Execution--Change Control | Lack of control over project scope, cost and schedule; lost business focus; inability to manage resources | The individuals (business stakeholders, IT personnel) authorized to make project change requests have been designated by authority at the campus-, medical center-, or laboratory level. |  | 1. A standard change request form is established, as well as a request process requiring documentation of the requested change and the expected benefits of the change. 2. Change requests are reviewed and the potential effects on the project, including resource requirements and impact on schedule, are estimated. The estimated project impact is documented in the change request. 3. The completed change request is reviewed and the approval or denial of the request by key stakeholders, including business project sponsor and IT project manager, is documented. 4. All approved project change requests are considered and approved at the campus-, medical center-, or laboratory level based on an assessment of the effect the change will have on the other projects. If the requested change should not be implemented, the reasons are shared with the requesting project management team so they can evaluate alternative approaches. 5. For projects involving in-house software development, change control extends to that area, for example in the form of source code control, separation of test-QA-production environments, separation of duties and/or programmatic source code control systems. |  | The project and, as necessary, entity-level plans are updated for all approved changes, and approved changes are communicated to all business and IT stakeholders in a timely manner.
12 | Project Execution--Assurance Methods | Untrustworthy assurance activities; ineffective and/or inefficient assurance activities; accreditation and implementation delays | The assurance tasks required to ensure compliance with internal controls and security requirements that impact the systems or processes in the scope of the project are defined. Key compliance stakeholders are included in the definition and approval of assurance tasks. |  | Appropriate subject matter specialists (e.g., audit, security or compliance) are included in the process. |  | How the assurance tasks will be performed is detemined and documented.
13 | Project Execution--Performance Measurement, Reporting, and Monitoring | Ineffective reporting on project progress and unidentified issues; lack of control over project progress; loss of focus on customer expectations and business needs. Project financial information is not reflected in the campus, medical center, or laboratory financial reports. | Campus-, medical center-, or laboratory-level criteria exist for project scope, schedule, quality, cost, and level of risk. |  | 1. Remedial action is implemented as necessary to maintain project performance. 2. Project-related financial transactions are recorded in a way that fully integrates with the campus, medical center, or laboratory's official financial reporting system. Financial transactions are coded in a manner that allows all project related costs to be tracked and reports produced, for example, by establishing activity codes, unique fund or org code number, etc. (terminology may vary by location). If "shadow" systems are used for tracking project-related costs, processes occur that reconcile shadow system information to that in the campus, medical center, or laboratory's official financial reporting system. | 1. Project performance is measured against key project performance criteria. 2. Deviations from established key project performance criteria are analyzed for cause, and entity-level positive and negative effects are assessed. 3. Entity-level changes are monitored, and existing key project performance criteria are reviewed to determine if they still represent valid measures of progress. | 1. Project progress is reported to stakeholders, along with deviations from established key project performance criteria, and positive and negative entity-level effects. 2. Any necessary changes in project performance criteria are documented and submitted for stakeholders' approval before adoption. Revised criteria are communicated to project managers for use in future performance reports. 3. Remedial action is recommended where necessary.
14 | Project Execution--Closure | Undetected project management weaknesses; missed opportunities from lessons learned | Key steps for project closure, including post-implementation reviews that assess whether a project attained desired results and benefits, are defined. |  | 1. Key steps for project closure are applied. 2. Post-implementation reviews are planned and executed to determine if projects delivered expected benefits and to improve the project management and system development process methodology. 3. Any uncompleted activities required to achieve planned project results and benefits are identified, assigned, communicated, and tracked. |  | The lessons learned and key activities that led to delivered benefits are collected from the project participants and reviewers. The data is analyzed, and recommendations are made for improving the project management method for future projects.